## Summary
Spinney External Works — Budget Summary
Last updated: | 2026-08-12 | All figures gross (as payable). Invoiced / Paid pull automatically from the Invoice Register; Contingency remaining pulls from the Drawdown sheet.
Cost centre | Supplier | Committed £ | Invoiced £ | Paid £ | Remaining vs committed £ | Notes
Decking materials | V4 Wood Flooring Ltd | 32228.99 | 32228.99 | 32228.99 | 0 | Order amended to all Ashwood + flexible bullnose (1 Jul). PAID IN FULL 9 Jul, ref V4FQ-15584. 25% restocking on over-ordering — unlikely given curved design + offcuts project, but noted.
Decking labour | LG Building and Roofing Ltd | 17600 | 6400 | 6400 | 11200 | Labour £17,600 (no VAT). Stage 1 (£4,400) invoiced/paid 20 Aug, full price. Cash instalment (£2,000, 4 Sep) — CORRECTED: cash payments DO get the 10% discount (same as chimney/coping), retiring £2,222.22 of quoted value. £6,400 cash paid to date, equivalent to £6,622.22 of quoted value — £10,977.78 quoted value remaining. Rubbish removal (£1,200) transferred 10 Aug to pooled skip fund — see that row, not double-counted here.
Contingency | — | 5000 | 480.98 | 480.98 | 4519.02 | Covers: fence move/repair labour; soakaway fix before decking; drainage by garage; extra curved-decking labour; cement & bricks; coping condensation-prep (£250, PAID 14 Aug via bank transfer, INV-0288). Luke's labour drawn from this pot attracts the 10% discount (extended 20 Jul) — note the condensation-prep item was paid by bank transfer, not cash, so discount doesn't apply there. See Contingency Drawdown sheet.
Chimney repair | LG Building and Roofing Ltd | 4700 | 4700.01 | 4700.01 | -0.01 | Quoted 2 Jun: £3,200 labour (invoiced full price, INV-0286) + £1,500 scaffold share. Cowl upgrade (£62.90) and TP account materials reclassified out 17 Aug — see Contingency and Materials (pooled) rows. This is now a clean quote-vs-actual labour figure.
Coping stones repair | LG Building and Roofing Ltd | 5310 | 5310 | 5310 | 0 | Quoted 3 Jun: £3,800 labour, confirmed 7 Aug as £3,610 blended (50% cash @10% disc. + 50% invoiced) + £1,700 scaffold share. Condensation-prep (£276.42) and TP account materials share (£277.29) reclassified out — see Contingency and Materials (pooled) rows. RISK: coping-stone damage on removal could substantially increase cost.
Materials (pooled) | Merchant trade accounts | 1130 | 1120.69 | 1120.69 | 9.31 | Pooled chimney (£480) + coping (£650) materials budget — decision 20 Jul. Purchased via merchant trade accounts (Dry Lining Supplies, Travis Perkins etc.), cleared on receipts. Detail on Materials Receipts sheet.
Rubbish removal (pooled skips) | Skip Hire Comparison Ltd / future providers | 1360 | 780 | 780 | 580 | Transferred 10 Aug from chimney/coping/decking rubbish-removal quotes (£80+£80+£1,200). Original skip (Skip Hire Comparison Ltd) cancelled 11 Aug, refunded — replaced same-day by Elmbridge Mini Skips (2 skips, £780 total, settled 12 Aug). Provisional — more skips expected, especially during decking. Detail on Skip Hire Log sheet.
Core project (Luke's ~£56,800 outline) |  | 54828.99 | 39109.97 | 39109.97 | 15719.02
Chimney + coping incl. pooled materials |  | 11140 | 11130.7 | 11130.7 | 9.3
PROJECT TOTAL |  | 67328.99 | 51020.67 | 51020.67 | 16308.32
Contingency remaining: | 4519.02

## Budget vs Actual
Spinney External Works — Budget vs Actual
Snapshot as of 17 Aug 2026 (Week 5) — refresh narrative each batched update session; table figures pull from Summary sheet.
Snapshot
Week 5 — overall, we are running close to plan. Chimney, coping, and decking materials all landed on or under quote; decking labour's first stage matches the quoted rate exactly. Materials pool is back under its cap after a refund. Contingency is barely touched. Nothing here suggests a budget problem.
• Chimney | £0 variance — labour invoiced at the full quoted £3,200, no discount applied (non-cash terms).
• Coping | £190 UNDER quote — half the labour was settled in cash at the agreed 10% discount (£1,710 vs £1,900), the other half invoiced at full price. This is the one place the discount policy shows up as a measurable saving.
• Decking (labour + V4 materials) | Materials fully paid to the V4 proforma exactly. Labour: Stage 1 (£4,400) invoiced full price, plus a £2,000 cash instalment (4 Sep, 10% discount applies) — £6,400 paid so far, £11,200 quoted value remaining across future stages.
• Scaffold (pooled, chimney + coping combined) | £0 variance — this was never split-quoted per workstream, just one £3,200 job (£2,000 paid on erection, £1,200 due on strike). Treating it as its own pooled line avoids implying a false per-workstream comparison.
• Materials (pooled, chimney + coping) | Back under the £1,130 cap — a £72.23 refund from Dry Lining Supplies (unused monocouche + other returned items) landed 19 Aug, more than offsetting the earlier £62.90 overage from pooling Luke's Travis Perkins account purchases.
• Rubbish removal (pooled, all 3 workstreams) | £780 spent of £1,360 so far — looks healthy, but this needs a caveat: decking's £1,200 share (88% of the pool) hasn't been tested yet, and the two skips used so far carried spoil from chimney, coping, AND the soakaway/decking-prep groundworks, not cleanly attributable to any one workstream.
• Contingency | £480.98 drawn of the £5,000 pot (condensation-prep £276.42 + chimney cowl upgrade £62.90 + V4 screw top-up £141.66) — £4,519.02 remaining. All three are genuine scope additions beyond the original quotes, which is exactly what this pot is for.
Budget vs Actual — detail
Cost centre | Quote / Budget £ | Actual £ | Variance £ | Note
Chimney (labour) | 3200 | 3200 | 0 | Invoiced full price (INV-0286) — non-cash, no discount
Coping (labour) | 3800 | 3610 | -190 | 50% cash @10% disc. + 50% invoiced — favourable
Decking (labour) | 17600 | 6400 | -11200 | Stage 1 (£4,400, invoiced, full price) + cash instalment (£2,000, 10% discount, retires £2,222.22 of quoted value) — £11,200 quoted value remaining, mix of future cash/invoice TBC.
Decking materials (V4) | 32228.99 | 32228.99 | 0 | Proforma matched exactly, paid in full 9 Jul
Scaffold (pooled, chimney+coping) | 3200 | 3200 | 0 | Never split-quoted — one combined job. £2,000 paid, £1,200 due on strike
Materials (pooled, chimney+coping) | 1130 | 1120.69 | -9.31 | Back under the £1,130 cap after a £72.23 refund from Dry Lining Supplies (unused monocouche + other returned items) landed 19 Aug — was £62.92 over before the refund.
Rubbish removal (pooled, all 3 workstreams) | 1360 | 780 | -580 | Decking's £1,200 share largely untested — see snapshot caveat
Contingency | 5000 | 480.98 | -4519.02 | £480.98 drawn (condensation-prep £276.42 + chimney cowl £62.90 + V4 screw top-up £141.66) — £4,519.02 remaining. Variance here just means 'not yet drawn', not a saving.
TOTAL (as spent/committed to date) | 67518.99 | 51020.66 | -16498.33 | Contingency now included at its £5,000 named budget value, matching Summary's convention.
Reconciliation check
Summary's PROJECT TOTAL uses each cost centre's committed/ceiling figure — for Chimney, Coping, and Decking that's the real actual; for Materials, Rubbish, and Contingency (all pooled/reserve buckets) it's the provisional cap, not what's been spent so far. Recomputed on that same basis below to confirm nothing here is missing or double-counted against Summary.
Chimney (actual) |  | 4700
Coping (actual) |  | 5310
Decking labour (actual) |  | 17600
Decking materials (actual) |  | 32228.99
Materials pooled (at £1,130 cap, per Summary) |  | 1130
Rubbish removal pooled (at £1,360 cap, per Summary) |  | 1360
Contingency (at £5,000 cap, per Summary) |  | 5000
Recomputed total (Summary basis) |  | 67328.99
Summary PROJECT TOTAL (committed) |  | 67328.99
Difference — should be £0.00 |  | 0

## Invoicing Schedule
Invoicing Schedule — expected invoice events
Terms: 10% labour discount on all Luke phases except decking labour and scaffolding. Chimney & coping settle as SINGLE CASH PAYMENTS on phase completion (agreed Lara/Ryan 20 Jul; TBC with Luke 21 Jul). Log every payment on the Invoice Register — this sheet is expectations, the Register is the record.
# | Cost centre | Trigger event | Payee | Basis | Est. £ | Status | Notes
1 | Decking materials | Order placed — PAID IN FULL 9 Jul | V4 Wood Flooring Ltd | Invoice V4FQ-15584 | 32228.99 | Paid
2 | Chimney + Coping (scaffold) | Erection complete (17–18 Jul) — PAID | Scaffolder (via Trevor) | £2,000 cash (of £3,200 combined) | 2000 | Paid | Logged in Register: £937.50 chimney + £1,062.50 coping
3 | Chimney + Coping (scaffold) | Strike, after Gate 1 sign-off | Scaffolder (via Trevor) | £1,200 cash balance on strike | 1200 | Agreed | Log in Register: £562.50 chimney + £637.50 coping
4 | Chimney repair | INVOICED & PAID 24 Jul (non-cash) | LG Building and Roofing Ltd | £3,200 labour less £111.70 prepaid = £3,088.30. Full price — no discount. | 3200 | Paid | £3,200 labour invoiced & paid 24 Jul (£3,088.30 after £111.70 prepayment deduction). Rubbish removal (£80) transferred 10 Aug to pooled skip fund — no longer owed to Luke.
5 | Coping stones repair | 50% CASH — PAID 7 Aug | LG Building and Roofing Ltd | 50% of base labour (£1,710.00), 10% cash discount. Based on original £3,800 quote only. | 1710 | Paid | Excludes condensation-prep addition — price not yet finalised (see separate row).
6 | Coping stones repair | 50% INVOICED — due next week | LG Building and Roofing Ltd | 50% of base labour (£1,900.00) full price. Rubbish removal transferred to pooled skip fund 10 Aug. | 1900 | Paid 14 Aug | INVOICED 13 Aug as part of Luke's INV-0288 (£2,150 total, due 14 Aug) — that invoice also includes the £250 condensation-prep item, now tracked separately under Contingency. No longer includes rubbish removal — see Rubbish removal (pooled skips) row.
7 | Coping stones repair | Additional scope — condensation-escape prep (price TBC) | LG Building and Roofing Ltd | Combined labour + materials, Luke's estimate — price NOT yet finalised | 250 | Price TBC — not finalised (7 Aug) | Terms confirmed 7 Aug: 100% cash (labour + materials) once priced. Separate from the base coping 50/50 split.
8 | Decking labour | Stage 1 (25%, INV-0289) PAID 20 Aug — 4 stages confirmed, flat 25% each | LG Building and Roofing Ltd | £17,600 labour total across stages, at quoted rates. CORRECTED 4 Sep: cash payments DO get the 10% discount (same as chimney/coping) — only invoiced stages are full price. Rubbish removal transferred to pooled skip fund. | 17600 | Stage 1 paid, 25% down | Stage 1 (£4,400) invoiced/paid 20 Aug, full price. Cash top-up (£2,000, 4 Sep) retires £2,222.22 of quoted value at the 10% discount. Remaining quoted value: £10,977.78. Exact milestone triggers for future stages still TBC.
9 | Materials (pooled) | Periodic — on receipts | Merchant trade accounts (Dry Lining Supplies, TP etc.) | Pooled £1,130 budget (chimney £480 + coping £650) | 1130 | Agreed in principle | Log each receipt in Register + Materials Receipts sheet
10 | Contingency | Rainy-day tasks 100% on completion; named extras as incurred | LG Building / merchants | £5,000 pot — fence labour, soakaway fix, garage drainage, curved-deck extras, cement & bricks. Labour at 10% discount | 5000 | Approved 20 Jul — first draw 14 Aug | Curved-decking extra labour discount TBC. First draw: coping condensation-prep (£250, named purpose #6), paid 14 Aug via bank transfer, INV-0288. £4,750 of the £5,000 pot remaining. Each drawdown also on Contingency Drawdown sheet.
11 | Chimney repair | Additional material — stainless steel cowl | StoveWorldUK (paid direct, project account) | Order #147399, 10 Aug 2026 | 62.9 | Paid | 5" stainless steel chimney pot hanger cowl — replaces original spec (decision logged 7 Aug), prevents rusting. Arrives Fri 14 Aug — likely last item before scaffold strike.
11 | Rubbish removal (pooled skips) | Periodic — as skips are needed | Skip Hire Comparison Ltd / future providers | Provisional £1,360 (transferred from chimney/coping/decking rubbish quotes) | 1360 | Approved 10 Aug | First skip £344.16 paid 10 Aug, delivery 11 Aug. More skips expected during decking — budget is provisional, watch like the materials pool. Log each skip in Register + Skip Hire Log sheet.
|  |  |  | SCHEDULE TOTAL (all rows): | 67641.89
|  |  |  | Summary tab committed total: | 67328.99
|  |  |  | Difference (must be £0.00): | 312.9

## Cost Lines
Cost Lines — every line item from LG estimates and the V4 invoice
Source documents: LG chimney estimate 2 Jun 2026 · LG coping estimate 3 Jun 2026 · LG decking estimate 3 Jun 2026 · V4 invoice V4FQ-15584, 9 Jul 2026.
Cost centre | Supplier | Line item | Qty | Unit £ | Line total £ | VAT | Payment route | Notes
Chimney repair | LG Building | Labour — remove render, k-rend sealer, base + top coat, render crown, storm-dry cream |  |  | 3200 | No VAT | LG invoice | INVOICED 24 Jul (INV-0286), full price £3,200 less £111.70 prepaid = £3,088.30. Non-cash, so 10% discount does not apply. Rubbish removal £80 outstanding.
Chimney repair | Scaffolder (direct) | Tubular scaffolding — all four sides of chimney and crown |  |  | 1500 | Inc VAT | Paid directly | Combined £3,200, cash terms (20 Jul): £2,000 paid following erection; £1,200 balance on strike.
Materials (pooled) | Merchant trade accounts | Materials (chimney estimate — pooled 20 Jul) |  |  | 480 | Inc VAT | Trade accounts — cleared on receipts
Chimney repair | LG Building | Rubbish removal |  |  | 0 | Inc VAT | LG invoice | TRANSFERRED 10 Aug to pooled Rubbish removal (skips) fund — family now supplies skips directly rather than Luke arranging disposal. No longer owed to Luke.
Coping stones repair | LG Building | Labour — remove/reset copings, slate cap, render, lead flashings to parapet rear |  |  | 3610 | No VAT | LG invoice | CONFIRMED 7 Aug, based on original £3,800 quote: 50% cash (£1710.00 @ 10% discount) due same day, 50% invoiced (£1900.00 full price) due next week, timed after back gutters are complete — see Invoicing Schedule. RISK: coping-stone damage on removal could substantially increase cost. Condensation-prep addition (£250) reclassified to Contingency 13 Aug — no longer part of this total.
Coping stones repair | Scaffolder (direct) | Tubular scaffolding with winch system |  |  | 1700 | Inc VAT | Paid directly | Combined £3,200, cash terms (20 Jul): £2,000 paid following erection; £1,200 balance on strike.
Materials (pooled) | Merchant trade accounts | Materials (coping estimate — pooled 20 Jul) |  |  | 650 | Inc VAT | Trade accounts — cleared on receipts
Coping stones repair | LG Building | Rubbish removal |  |  | 0 | Inc VAT | LG invoice | TRANSFERRED 10 Aug to pooled Rubbish removal (skips) fund. Removed from next week's invoice (now £1,900, not £1,980).
Decking labour | LG Building | Labour — remove old decking & frame, construct composite frame, install deck to spec |  |  | 17600 | No VAT | LG invoice | RISK: pending structure/ground assessment. CORRECTED 4 Sep: cash payments DO get the 10% discount (same as chimney/coping) — only invoiced stages are full price. Progress: Stage 1 (£4,400) invoiced 20 Aug + £2,000 cash instalment 4 Sep (retires £2,222.22 of quoted value) — £6,400 cash paid to date, equivalent to £6,622.22 of quoted value — £10,977.78 quoted value remaining.
Decking labour | LG Building | Rubbish removal (8-yard skips ×2, possibly 3) |  |  | 0 | Inc VAT | LG invoice | TRANSFERRED 10 Aug to pooled Rubbish removal (skips) fund.
Decking materials | V4 Wood Flooring | Millboard Ashwood 176mm Moulded Lastane (144.90 m²) | 230 | 66.49 | 15292.7 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MFN360H | 18 | 58.09 | 1045.62 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MEBB360H (flexible bullnose) | 15 | 72.25 | 1083.75 | In net | V4 invoice — PAID | For curved upper level
Decking materials | V4 Wood Flooring | Millboard Step Edge — Ashwood Moulded Lastane | 15 | 59.89 | 898.35 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Stainless steel screws 45mm — boxes | 24 | 32.08 | 770 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Durafix Trimhead 35mm SS screws — box of 100 (FT35P100) | 6 | 10.25 | 61.5 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Plas-Pro bearer/joist black 3.0m 50×125mm composite (P1205B300) | 266 | 28.4 | 7554.4 | In net | V4 invoice — PAID | Subframe — the bulk of the tonnage
Decking materials | V4 Wood Flooring | Subframe hexhead screws — box of 50 (FH90P050) | 16 | 7.87 | 125.92 | In net | V4 invoice — PAID | Original 16 boxes delivered in full, confirmed 12 Aug. TOP-UP REQUESTED 20 Aug: Luke has asked for 15 more boxes (same item, FH90P050) — substructure screw consumption running ahead of the original estimate. Not yet ordered/invoiced. Estimated cost £141.66 inc VAT (15 x £7.87 + 20% VAT, matching original per-unit price) — treat as V4 Phase 3 once ordered. Not yet added to committed total.
Decking materials | V4 Wood Flooring | Millboard touch-up paint — Ashwood (AP500H) | 1 | 15 | 15 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard multi-spacer — pack of 10 (FP36P010) | 1 | 10.25 | 10.25 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | VAT on order |  |  | 5371.5 | VAT | V4 invoice — PAID | Net £26,857.49 + VAT = £32,228.99
Contingency | TBC | Contingency pot — fence labour, garage drainage, curved-deck labour, cement & bricks, coping condensation-prep (£250, reclassified 13 Aug). Soakaway fix cancelled 1 Sep, nothing drawn. Pipe investigation resolved 4 Sep — no leak, no repair needed, no draw required. |  |  | 5000 | — | As incurred | Track on Contingency Drawdown sheet. Labour invoices from this pot at 10% discount (extended 20 Jul); materials (cement/bricks) full price. Curved-decking extra labour: discount status TBC with Luke. Coping condensation-prep (£250) added as named purpose #6, 13 Aug — payment method (cash vs invoice) pending confirmation.
Contingency | LG Building and Roofing Ltd | Named purpose #6 — Coping condensation-escape prep: re-bed 3 bricks; reinforce parapet corners with fibreglass mesh; fit 4 weep holes to front face above internal damp-course membrane (slate DPC capped in plastic DPM). Reclassified from Coping 13 Aug — same item, moved to keep coping's committed total accurate rather than inflate it. |  |  | 250 | TBC | Contingency drawdown | PRICED 13 Aug via Luke's invoice INV-0288: £250. Terms originally agreed as 100% cash; confirmed 14 Aug instead paid via bank transfer, bundled with the coping £1,900 balance. PAID 14 Aug.
Contingency | StoveWorldUK | Named purpose #7 — Chimney cowl upgrade: 5" Stainless Steel Chimney Pot Hanger Cowl (order #147399), replaces original spec | 1 | 62.9 | 62.9 | Inc VAT | Paid direct by Ryan (project account) | Decision logged 7 Aug (stainless steel, prevent rusting). Cost finalised 10 Aug, received 12 Aug, fitted 17 Aug. RECLASSIFIED 17 Aug from Chimney to Contingency — genuine scope addition beyond the original quote, same treatment as coping condensation-prep (#6). Paid direct by Ryan.
Materials (pooled) | LG Building and Roofing Ltd (Travis Perkins account) | Luke's Travis Perkins account materials, 3 invoices 17 Jul-5 Aug (render/masonry consumables + lead flashing) — pooled with chimney+coping materials, same simplified treatment as Dry Lining Supplies. |  |  | 481.26 | Inc VAT | Reimbursement to Luke | SIMPLIFIED 18 Aug: previously split chimney/coping 50/50 — now pooled as one line, consistent with how Dry Lining Supplies purchases were always treated (not split by workstream). DPC roll (£26.42) stays separately in Contingency (purpose #6, condensation-prep) as it's additional scope, not pool materials.
|  | (merged into row above, 18 Aug) |  |  | 0 | Inc VAT | Reimbursement to Luke | RECLASSIFIED 17 Aug: lead flashing reattributed from chimney to coping (original quote explicitly scopes 'lead flashings to parapet rear' under coping's labour). Both items within originally-quoted scope, so routed through Materials pool per agreed rule rather than Coping's own Cost Lines.
Contingency | V4 Wood Flooring Ltd | Named purpose #8 — V4 screw top-up: 15 more boxes of Timberfix structural subframe screws (FH90P050), quote V4FQ-17702 |  |  | 141.66 | Inc VAT | Bank transfer | Requested by Luke 20 Aug, ordered 24 Aug, PAID. Substructure screw consumption ran ahead of the original 16-box estimate. Same item/supplier as the original V4 order, but treated as an additional-scope purchase per Ryan's direction — routed through Contingency rather than inflating the Decking materials (V4) line, which stays matched to its original proforma.
Rubbish removal (pooled skips) | Skip Hire Comparison Ltd / future providers | Provisional pooled budget — transferred from chimney (£80) + coping (£80) + decking (£1,200) rubbish-removal quotes, 10 Aug. Family now supplies skips directly. |  |  | 1360 | — | Paid direct by Ryan (project account) | First skip ordered 10 Aug (£344.16, 8yd, delivery 11 Aug). More skips expected during decking — budget is provisional, to be watched like the materials pool. Detail on Skip Hire Log sheet.
|  | TOTAL (all lines) |  |  | 68264.81

## Invoice Register
Invoice & Payment Register — add a row per invoice received
Yellow cells are inputs. Cost centre must match the Summary sheet names exactly (dropdown-free by design — copy from row 5). Paid date empty = outstanding.
Invoice date | Cost centre | Supplier | Reference | Description | Amount £ (gross) | Paid date | Method | Notes
2026-07-09 | Decking materials | V4 Wood Flooring Ltd | V4FQ-15584 | Millboard Ashwood decking + Plas-Pro subframe, fixings (144.9 m²) | 32228.99 | 2026-07-09 | Amex | Paid in full at order
2026-07-20 | Materials (pooled) | Dry Lining Supplies Ltd | RECB000NNIVB49XWEXOG | Render materials (shared chimney+coping): mesh, Weberend Aid ×6, beads, SBR, rubble sacks | 311.98 | 2026-07-20 | Pay By Link | Project-materials share of £423.69 receipt
2026-07-20 | Chimney repair | Dry Lining Supplies Ltd | RECB000NNIVB49XWEXOG | Folding work platform 600mm — Luke's equipment, non-project | 111.71 | 2026-07-20 | Pay By Link | PREPAYMENT vs chimney phase-start invoice: pay £1,528.29 of the £1,640 when it lands
2026-07-20 | Chimney repair | Scaffolder (via Trevor) | Cash | Scaffold erection payment — chimney share (pro-rata of £2,000 cash) | 937.5 | 2026-07-20 | Cash | £2,000 paid following erection 17–18 Jul; amend date cell if payment day differed
2026-07-24 | Chimney repair | LG Building and Roofing Ltd | INV-0286 | Chimney labour, invoiced (£3,200 less £111.70 work-platform prepayment). Rubbish removal £80 NOT included — outstanding. | 3088.3 | 2026-07-24 | Bank transfer | Invoiced (non-cash) — full price, no 10% discount. £80 rubbish removal still outstanding.
2026-07-22 | Materials (pooled) | Dry Lining Supplies | 914751798 | Weber Pral M Silver Pearl x10, Plastic 15mm Stop Bead 3m x3 (shared render finish) | 162.96 | 2026-07-22 | Pay By Link | Second pooled-materials trip
2026-08-04 | Materials (pooled) | Dry Lining Supplies Ltd | RECB000NNIVB6DIPDFCW | Weberend Ocr x3, Weber Pral M Silver Pearl x4, Stop Bead x6, Drip Bead x2, Sikabond SBR x1 (coping render) | 148.53 | 2026-08-04 | Pay By Link | Coping stones render materials. Receipt received 4 Aug (till David, 07:31).
2026-08-07 | Coping stones repair | LG Building and Roofing Ltd | Cash | Coping 50% cash labour payment (base labour only, 10% discount). Condensation-prep addition NOT included — price not yet finalised. | 1710 | 2026-08-07 | Cash | Confirmed 7 Aug: 50% cash / 50% invoice split on original £3,800 quote. Remainder £1,980.00 (incl. rubbish) to be invoiced next week. £250 addition separate, price TBC.
2026-08-10 | Contingency | StoveWorldUK | Order #147399 | 5" Stainless Steel Chimney Pot Hanger Cowl — replaces original spec | 62.9 | 2026-08-10 | Card (Ryan, project account) | Named purpose #7 (chimney cowl upgrade). RECLASSIFIED 17 Aug from Chimney repair — genuine scope addition beyond original quote.
2026-08-10 | Rubbish removal (pooled skips) | Skip Hire Comparison Ltd | D81F29CE-0002 | 8 cubic yard skip, delivery 11 Aug | 344.16 | 2026-08-10 | Card (Ryan, project account) | First skip. Replaces chimney/coping/decking rubbish-removal quotes — transferred to this pooled fund 10 Aug. CANCELLED 11 Aug — original supplier delayed delivery; refunded in full (receipt 3362-9782), see row below.
2026-08-11 | Rubbish removal (pooled skips) | Skip Hire Comparison Ltd | Refund 3362-9782 (orig. inv. D81F29CE-0002) | Refund — original skip cancelled after supplier delivery delay | -344.16 | 2026-08-13 | — | Refund confirmed received 13 Aug 2026 — cleared in 2 working days, faster than the 5-10 day estimate.
2026-08-11 | Rubbish removal (pooled skips) | Elmbridge Mini Skips | INV-11373 / ref 25996 | 8 cubic yard skip — delivery, replaces cancelled Skip Hire Comparison booking | 390 | 2026-08-12 | TBC | Settled 12 Aug 2026. Skip delivered filled 11 Aug; collected and swapped for empty 12 Aug.
2026-08-12 | Rubbish removal (pooled skips) | Elmbridge Mini Skips | INV-11375 / ref 26030 | 8 cubic yard skip — exchange (collects filled skip, delivers empty) | 390 | 2026-08-12 | TBC | Settled 12 Aug 2026.
2026-08-13 | Coping stones repair | LG Building and Roofing Ltd | INV-0288 | 50% invoiced balance — coping base labour | 1900 | 2026-08-14 | Bank transfer | Paid as part of INV-0288 (£2,150 total, also includes the £250 condensation-prep item — see Contingency row below).
2026-08-13 | Contingency | LG Building and Roofing Ltd | INV-0288 | Named purpose #6 — coping condensation-escape prep (re-bed 3 bricks, fibreglass mesh, 4 weep holes) | 250 | 2026-08-14 | Bank transfer | Reclassified from Coping 13 Aug. Terms were originally agreed as 100% cash — confirmed 14 Aug this is instead paid via bank transfer as part of INV-0288, bundled with the £1,900 coping balance.
2026-08-16 | Materials (pooled) | SoftWash UK | Order F4UJ62VLQ | Render Cleaner Gel X Pro, 5 Litres | 47.99 | 2026-08-16 | Card (Mastercard ...4597) | Paid at checkout, order confirmed 16 Aug. Also logged on Materials Receipts sheet — pool detail.
2026-08-17 | Materials (pooled) | LG Building and Roofing Ltd (Travis Perkins account) | TP invoices 1047678330 / 1047972816 / 1048887075 | Render/masonry consumables + lead flashing — pooled, not split by workstream | 481.28 | 2026-08-18 | Bank transfer | PAID 18 Aug, confirmed as part of the full £547.88 TP account settlement (all 4 invoices). £0.02 rounding absorbed here so the three allocations reconcile exactly to the confirmed total.
2026-08-19 | Materials (pooled) | Dry Lining Supplies Ltd | Refund against 4 Aug order | Refund — 5 bags unused monocouche + other returned items, against original £148.53 order | -72.23 | 2026-08-19 | Bank transfer | Refund confirmed received 19 Aug — £72.23, slightly more than the £63.10 estimate (5 bags x £12.62), likely covered a few additional returned items beyond the monocouche. Actual figure used, not the estimate.
2026-08-17 | Contingency | LG Building and Roofing Ltd (Travis Perkins account) | TP invoice 1048887075 | Damplas DPC roll — coping condensation-prep material (named purpose #6) | 26.42 | 2026-08-18 | Bank transfer | PAID 18 Aug, part of the full £547.88 TP account settlement. Adds to the existing purpose #6 draw (£250 labour) — total now £276.42.
2026-08-10 | Materials (pooled) | LG Building and Roofing Ltd (Travis Perkins account) | TP invoice 1049120278 | Cleaning/finishing consumables — pooled, not split by workstream | 40.18 | 2026-08-18 | Bank transfer | PAID 18 Aug, part of the full £547.88 TP account settlement.
2026-08-18 | Decking labour | LG Building and Roofing Ltd | INV-0289 | Decking labour — stage 1 (25% of £17,600 quoted labour) | 4400 | 2026-08-20 | Bank transfer | First stage payment — resolves the earlier open question about 4-5 stage triggers: appears to be a flat 25% per stage. 3 stages remaining (£13,200).
2026-07-20 | Coping stones repair | Scaffolder (via Trevor) | Cash | Scaffold erection payment — coping share (pro-rata of £2,000 cash). CAUGHT 18 Aug: paid at the time, only now logged in the Register. | 1062.5 | 2026-07-20 | Cash | Matches chimney's already-logged share (row 8) — total £2,000 split £1,500/£1,700 chimney/coping ratio.
2026-08-18 | Chimney repair | Scaffolder (via Trevor) | — | Scaffold final balance — chimney share (pro-rata of £1,200) | 562.5 | 2026-08-18 | TBC | Scaffold strike complete 18 Aug, final balance paid. Full £3,200 now settled: £1,500 chimney + £1,700 coping.
2026-08-18 | Coping stones repair | Scaffolder (via Trevor) | — | Scaffold final balance — coping share (pro-rata of £1,200) | 637.5 | 2026-08-18 | TBC | Scaffold strike complete 18 Aug, final balance paid.
2026-08-24 | Contingency | V4 Wood Flooring Ltd | V4FQ-17702 | V4 screw top-up — 15 boxes structural subframe screws (named purpose #8) | 141.66 | 2026-08-24 | Bank transfer | Requested by Luke 20 Aug, ordered and paid 24 Aug.
2026-09-04 | Decking labour | LG Building and Roofing Ltd | Cash | Decking labour — cash instalment (10% discount applies) | 2000 | 2026-09-04 | Cash | Retires £2,222.22 of quoted value at the 10% cash discount (£2,000 paid = 90%). Not a full 25% stage — partial/interim payment. Total paid to date: £6,400 (Stage 1 £4,400 invoiced + this £2,000 cash). Quoted value remaining: £10,977.78.

## Skip Hire Log
Skip Hire Log — pooled rubbish-removal drawdown
Provisional pooled budget £1,360 (transferred 10 Aug from chimney £80 + coping £80 + decking £1,200 rubbish-removal quotes). Family now supplies skips directly rather than Luke arranging disposal. Log every skip here AND on the Invoice Register (cost centre: Rubbish removal (pooled skips)) — this sheet is skip detail, the Register is the money record. Unlike the materials pool, more skips are expected — budget may need topping up.
Opening pool: | 1360 | Remaining: | 580
Date | Provider | Skip details | Phase / use | Amount £ | Running remaining £
2026-08-10 | Skip Hire Comparison Ltd | 8 cubic yard, general waste, delivery 11 Aug (ref D81F29CE-0002) — CANCELLED 11 Aug (supplier delayed), refunded in full (receipt 3362-9782) | Above-ground works (chimney/coping) | 344.16 | 1015.84
2026-08-11 | Skip Hire Comparison Ltd | Refund — cancelled booking, receipt 3362-9782, 5-10 working days to clear | Refund (cancelled skip) | -344.16 | 1360
2026-08-11 | Elmbridge Mini Skips | 8 cubic yard, delivery — filled, awaiting exchange (INV-11373, ref 25996) | Above-ground works (chimney/coping) | 390 | 970
2026-08-12 | Elmbridge Mini Skips | 8 cubic yard, exchange — collects filled skip, delivers empty (INV-11375, ref 26030) | Above-ground works (chimney/coping) | 390 | 580

## Materials Receipts
Materials Receipts — pooled budget drawdown
Pooled budget £1,130 (chimney £480 + coping £650, pooled 20 Jul). Log every merchant receipt here AND on the Invoice Register (cost centre: Materials (pooled)) — this sheet is the pool detail, the Register is the money record. NOTE: pool is over cap after adding Luke's Travis Perkins account materials (now paid in full, 18 Aug) — flagged deliberately, not hidden; cap left at £1,130 rather than raised. PENDING 18 Aug: 5 bags of unused monocouche (Weber Pral M) returned to Dry Lining Supplies — refund expected within a couple of working days. Calculated from receipts: Weber Pral M Silver Pearl consistently £12.62/bag inc VAT (£126.20/10 on 22 Jul, £50.48/4 on 4 Aug) × 5 bags = £63.10 expected refund. Not yet logged as received — add Paid date once the credit note actually lands.
Opening pool: | 1130 | Remaining: | -62.9
Date | Merchant | Items (summary) | Phase / use | Amount £ | Running remaining £
2026-07-20 | Dry Lining Supplies Ltd | Render mesh, Weberend Aid ×6, angle/stop beads, rubble sacks, Bond It SBR 5l (project share; £111.71 platform excluded — Luke's equipment) | Render (chimney + coping, shared) | 311.98 | 818.02
2026-07-22 | Dry Lining Supplies | Weber Pral M Silver Pearl x10 (£126.20), Plastic 15mm Stop Bead 3m x3 (£9.60), inc VAT | Render finish (chimney + coping, shared) | 162.96 | 655.06
2026-08-04 | Dry Lining Supplies Ltd | Weberend Ocr x3 (£29.13), Weber Pral M Silver Pearl x4 (£50.48), Stop Bead x6 (£19.20), Drip Bead x2 (£7.42), Sikabond SBR (£17.54), inc VAT | Render (coping stones) | 148.53 | 506.53
2026-08-16 | SoftWash UK | Render Cleaner Gel X Pro, 5 Litres (order F4UJ62VLQ) | Render cleanup (chimney + coping, shared) | 47.99 | 458.54
2026-08-17 | LG Building and Roofing Ltd (Travis Perkins account) | Render/masonry consumables + lead flashing, 3 invoices 17 Jul-5 Aug (1047678330 / 1047972816 / 1048887075) — pooled, not split by workstream | Render (chimney + coping, pooled) | 481.26 | -22.72
2026-08-10 | LG Building and Roofing Ltd (Travis Perkins account, INV 1049120278) | Cleaning/finishing consumables (trigger spray, decorating cloth) — pooled, not split by workstream | Render (chimney + coping, pooled) | 40.18 | -62.9

## Contingency Drawdown
Contingency Drawdown — £5,000 pot (agreed Lara/Luke, 1 Jul 2026)
Named purposes: fence move/repair labour · ~~soakaway fix before decking~~ CANCELLED 1 Sep, cost-benefit not worth it, nothing drawn · drainage by the garage · additional curved-decking labour · cement & bricks · coping condensation-prep (£276.42, purpose #6) · chimney cowl upgrade (£62.90, purpose #7) · V4 screw top-up (£141.66, purpose #8). Luke's labour from this pot invoiced at 10% discount (extended 20 Jul) — condensation-prep, the cowl, and the screw top-up were all bank transfer/direct paid, not cash, so no discount applied to any of them. Curved-decking extra labour discount status TBC. Pipe investigation (task 2.2) RESOLVED 4 Sep: no leaking pipe found — damp ground was condensation trapped under old decking, not a plumbing fault. No repair needed, purpose #9 not required. Excavation continues for decking widening (straight-line, distinct from curved-decking-labour purpose above), tracked under decking substructure, not contingency.
Opening pot: | 5000 | Remaining: | 4519.02
Date | Purpose | Supplier / detail | Amount £ | Running remaining £
2026-08-14 | Coping condensation-escape prep (named purpose #6) | LG Building and Roofing Ltd (INV-0288) | 250 | 4750
2026-08-17 | Coping condensation-prep material (Damplas DPC roll, named purpose #6) | LG Building and Roofing Ltd (Travis Perkins account) | 26.42 | 4723.58
2026-08-17 | Chimney cowl upgrade — stainless steel (named purpose #7) | StoveWorldUK (order #147399) | 62.9 | 4660.68
2026-08-24 | V4 screw top-up — 15 boxes structural subframe screws (named purpose #8) | V4 Wood Flooring Ltd (V4FQ-17702) | 141.66 | 4519.02