## Gantt
Spinney External Works — Project Gantt (v8 — 17 Oct: roofline works and driveway channel complete; V4 delivery Tue 20 Oct; Millboard site visit planned Thu 22 Oct)
Last updated: | 2026-10-17 | Crew basis: Luke +1. Works now running in PARALLEL (chimney/coping/soakaway simultaneously), superseding the original one-phase-at-a-time model. Luke's 22–29 Aug holiday is the binding constraint on decking start, not sequential dependencies.
Legend: teal bar = task · gold = milestone / stage gate · grey column = Luke holiday · blue text on yellow = edit these cells (Start / End dates drive the bars)
ID | Task | Owner | Depends on | Days | Status | Start | End | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30
PHASE 1 — SCAFFOLD & AT-HEIGHT WORKS
1.0 | Site setup & garden segregation fencing (family access preserved) | Luke +1 | — | 2 | Complete | 2026-07-13 | 2026-07-14
1.1 | Scaffold A + B erection (incl. discrete decking demolition at footing points) | Trevor | 1.0 | 2 | Complete | 2026-07-17 | 2026-07-18
1.2 | Chimney repair — cut render to substrate, realign, re-render. Cowl fitted 17 Aug. Sealant applied 18 Aug — COMPLETE. | Luke +1 | 1.1 | 7 | Complete | 2026-07-20 | 2026-08-18
1.3 | Coping stones — cut back, lead flashing, replace stones, watertight. Sealant applied 18 Aug — COMPLETE. | Luke +1 | 1.2 | 10 | Complete | 2026-08-03 | 2026-08-18
1.4 | Scaffold strike (A + B) — COMPLETE 18 Aug. Final £1,200 payment paid — full £3,200 now settled (£1,500 chimney + £1,700 coping). | Trevor | G1 | 3 | Complete | 2026-08-18 | 2026-08-18
G1 | STAGE GATE 1 — At-height works sign-off: cowl fitted, chimney + coping complete | Family | 1.2, 1.3 |  | CLEARED 18 Aug — chimney + coping both complete | 2026-08-17 | 2026-08-17
1.5 | Roofline works — own £2,140 estimate (4 Sep): replace gutters (both parapet sides + lower rear), extend fascia/soffit, replace broken slates (incl. front tile repairs), barge board trim. No front-of-house gutters. MERGED 4 Oct from old 1.5, 1.7 and 3.2. Started 29 Sep; main works done the week of 5 Oct; remaining works finished Fri 16 Oct, ahead of the whole-house soft wash (Mon 19 Oct). COMPLETE Fri 16 Oct, including the lead flashing. Gates board-laying via Gate 2. | Luke +1 | 1.4 | 5 | Complete — finished Fri 16 Oct (including the lead flashing) | 2026-09-29 | 2026-10-16
1.5a | Additional lead flashing, back-of-house gutters — lead chased into the walls so the new gutters work properly. EXTRA SCOPE, est. about £200 (Luke, 2 Oct), drawn from contingency. COMPLETE Fri 16 Oct (lead flashing confirmed included). Awaiting Luke's invoice (est. £200). Part of Gate 2. | Luke +1 | 1.5 | TBC | Complete — Fri 16 Oct (lead flashing confirmed included) | 2026-10-16 | 2026-10-16
1.6 | Whole-house soft wash by Gorgeous Cleaning Services — gutters, soffits, roof tiles, roof solar panels, render, windows etc. £1,200 cash, drawn from contingency. REPLACES the chimney + coping-only soft wash (cheaper to use a previous supplier for the whole house than to spot clean with Luke). Starts Mon 19 Oct; all roofline works must be complete first. Must also complete before decking boards go down (chemical residue risk to new boards). Duration TBC. | Gorgeous Cleaning | 1.5, 1.5a | TBC | Booked — confirmed, starts Mon 19 Oct | 2026-10-19 | 2026-10-19
G2 | STAGE GATE 2 — Roofline works, additional lead work and whole-house soft wash completed, before decking boards are laid. Roofline works and lead flashing complete Fri 16 Oct; only the whole-house soft wash (from Mon 19 Oct) remains | Family | 1.5, 1.5a, 1.6 |  | Not yet cleared — roofline works and lead flashing complete Fri 16 Oct; waiting only on the whole-house soft wash (from Mon 19 Oct) | TBC | TBC
PHASE 2 — GROUNDWORKS & DECKING
2.1 | Soakaway drainage, side (a) — CANCELLED 1 Sep 2026. Family + Luke decision: cost-benefit ratio not worth it. Investigation phase (completed 18 Aug) feeds directly into the pipe investigation (2.2) instead. | Luke +1 | — | 5 | Cancelled | 2026-08-10
V1 | V4 Phase 1 — COMPLETE 12 Aug (notified 10 Aug): all items received, including joists (Plas-Pro Bearer/Joist — confirmed via two deliveries same day). Only 228 decking boards (Milboard Enhanced Grain) outstanding, rolled into Phase 2, as planned. | Ryan | — | — | Complete | 2026-08-10 | 2026-08-12
V2 | V4 Phase 2 — 228 decking boards (Milboard Enhanced Grain), only outstanding item from Phase 1. To be ordered on request when needed. UPDATE 24 Sep: if roofline works (task 1.5, formerly 1.7) go ahead as planned next week, request delivery of these boards — currently held by V4. | V4 Flooring | On request | — | Floating | 2026-09-01 | 2026-09-17
2.2 | Decking side (a) — strip out, new substructure (incl. weed-stop membrane below). PIPE INVESTIGATION RESOLVED: no leaking waste pipe, damp ground was condensation under old decking. Excavation continues to widen decking, straight-line. Digger + barrow loader on hire until 10 Sep (est. £530, mixed purpose with new shed area — see 2.6). Earth reused as buttress-wall infill on side (b). RE-PLAN 8 Sep: all decking substructure (this + 2.3 + 2.6) now estimated to take 2 more weeks, ~22 Sep. Board-laying tracked separately at 2.5. RE-PLAN 17 Sep: w/c 15 Sep spent exclusively on substructure, w/c 22 Sep the same — completion pushed a further week, to ~29 Sep. RE-PLAN 24 Sep: w/c 22 Sep spent exclusively on substructure top level. All other pre-board-laying tasks pushed a further week. UPDATE 3 Oct: substructure build started w/c 21 Sep; end date TBC — awaiting Luke's estimate (bar shown to date only). | Luke +1 | — | TBC | In progress — substructure under way; Luke's team on the extended decking area; V4 delivery Tue 20 Oct to complete the substructure; end date TBC | 2026-09-03 | 2026-10-17
2.3 | Decking side (b) — strip out, new substructure (incl. weed-stop membrane below). Old boards + substructure removed 17-18 Aug. Both lower and upper layer substructure under way. Buttress walls infilled with earth excavated from side (a)'s dig (2.2). Travis Perkins order (F49820): ballast, sand, 72x solid dense blocks — two deliveries received, invoice still pending. RE-PLAN 8 Sep: all decking substructure (this + 2.2 + 2.6) now estimated to take 2 more weeks, ~22 Sep. Board-laying tracked separately at 2.5. RE-PLAN 17 Sep: w/c 15 Sep spent exclusively on substructure, w/c 22 Sep the same — completion pushed a further week, to ~29 Sep. RE-PLAN 24 Sep: w/c 22 Sep spent exclusively on substructure top level. All other pre-board-laying tasks pushed a further week. UPDATE 3 Oct: substructure build started w/c 21 Sep; end date TBC — awaiting Luke's estimate (bar shown to date only). | Luke +1 | 3.3 | TBC | In progress — substructure under way; Luke's team on the extended decking area; V4 delivery Tue 20 Oct to complete the substructure; end date TBC | 2026-08-17 | 2026-10-17
2.4 | Outside tap/pipework check (utility room to Summer house, under decking substructure) — check all connections before decking boards are laid; ensure extra pipe insulation; query whether the elbow needs supporting. | Luke +1 | 2.2, 2.3 | TBC | Not started — start TBC (follows the substructure; previously est. w/c 29 Sep) | TBC | TBC
G3 | STAGE GATE 3 — Outside tap/pipework insulated, and weed-stop membrane installed, before decking boards go down | Family | 2.4 |  | Not started — TBC (follows 2.4; previously est. 2 Oct) | TBC | TBC
G3B | STAGE GATE 3B — Substructure sign-off by Millboard's technical area manager (Jon, V4 Flooring, also invited) before any boards are laid. Validates the warranty; photos for the project record and PR. Millboard site visit planned Thu 22 Oct (sign-off not yet given). | Ryan | 2.2, 2.3, 2.6, G3 |  | Millboard site visit planned Thu 22 Oct — sign-off pending | 2026-10-22 | 2026-10-22
2.5 | Lay Millboard decking per design, all sides (gate a and gate b access as applicable) — INCLUDES the new decking area leading up to the shed, perpendicular to side (a). Combined into one task for simplicity. Gated on G2 (gutters/slate) and G3 (tap/pipework/weed membrane) AND substructure (2.2/2.3/2.6) completing. RE-PLAN 8 Sep: pushed back from 15 Sep — substructure now estimated to take 2 more weeks. UPDATE 3 Oct: cannot start Tue 6 Oct — render soft wash only starts Mon 5 Oct and the tap/pipework check (G3) has not started; dates TBC until Luke gives revised estimates. UPDATE 4 Oct: also gated by Gate 3B (substructure sign-off by Millboard / V4) — cannot start until G2, G3 and G3B have all cleared. | Luke +1 | G2, G3, G3B | 13 | Not started — start TBC: needs G2, G3 and the substructure complete (previously est. 6 Oct – 4 Nov) | TBC | TBC
G4 | STAGE GATE 4 — Decking sign-off, all sides | Family | 2.5 |  | Not started — TBC (previously est. 4 Nov) | TBC | TBC
2.6 | New shed area, perpendicular to side (a) — TRIMMED 8 Sep to excavation + substructure only, for BOTH the shed base and the new decking area leading up to it. Millboard board-laying for that decking area is now tracked at 2.5 (gated on G2/G3). Shed relocation onto its own base is NOT dependent on board-laying — only on its own substructure — so it can happen as soon as substructure completes (~22 Sep), independent of G2/G3/2.5. CORRECTED 11 Sep: the related boundary/fence work is 2.7 (side a, chimney side — now complete), NOT 3.3 (side b) as first logged 8 Sep. RE-PLAN 17 Sep: w/c 15 Sep spent exclusively on substructure, w/c 22 Sep the same — completion pushed a further week, to ~29 Sep. RE-PLAN 24 Sep: w/c 22 Sep spent exclusively on substructure top level. All other pre-board-laying tasks pushed a further week. UPDATE 3 Oct: substructure build started w/c 21 Sep; end date TBC — awaiting Luke's estimate (bar shown to date only). UPDATE 9 Oct: substructure work continued w/c 5 Oct; end date still TBC, bar shown to 9 Oct. UPDATE 13 Oct: Luke's team is working on the extended decking area; Luke was off site Mon 12 Oct. Bar shown to 13 Oct. | Luke +1 | G4 |  | In progress — substructure under way; Luke's team on the extended decking area; V4 delivery Tue 20 Oct to complete the substructure; end date TBC | 2026-09-08 | 2026-10-17
V5 | V4 Phase 4 — materials order for the shed-area decking scope (side a), including the curved sections (see 2.2/purpose #4 labour). LIST SENT 24 Sep (Luke to Jon, V4): sub frame for 12m x 2.5m, decking for 8m x 2.5m, bull nose 8m, x5 flexible board for the curves, x5 extra joist, 99mm Duospan Flexible Brackets, Plas Pro to Duospan screws 25mm. QUOTE RECEIVED 28 Sep (#QUO-0031): £5,322.74 inc VAT — 35x Enhanced Grain boards, 44x Plas-Pro bearers, 5x Hexhead screws, 3x Bullnose board, 2x DuoSpan flexible bracket sets, 1x DuoSpan-to-Plas-Pro screws, 3x Flexible Bullnose Step Edge. Qty differs slightly from the original request (3 flexible bullnose vs 5 asked for; no distinct 'extra joist' line — likely = the 44 bearers). ACTIONED via phone with Jon 29 Sep — ordered and paid. Tracked in Budget Tracker as Contingency named purpose #24 (expanded scope, not the base decking quote). Delivery expected 30 Sep or 1 Oct. | V4 Flooring | £5,322.74 | Paid | Ordered & paid 29 Sep — delivery expected 30 Sep/1 Oct
2.7 | Fence move — chimney side (side a), boundary reclaimed from neighbour to enable the wider decking area, repositioned at new extended height. COMPLETE 11 Sep. NOT the same as 3.3 (side b, concrete spurs, still pending) or 3.5 (TPO/tree-dependent relocation). CORRECTED 11 Sep: this is the fence the 8 Sep boundary/scope-increase note was actually describing, not 3.3. | Luke +1 | — | 1 | Complete | 2026-09-11 | 2026-09-11
G5 | PROJECT COMPLETION — snagging & final sign-off | All | All |  | Not started — TBC (previously est. 11 Nov) | TBC | TBC
PHASE 3 — FLOATING / RAINY-DAY POOL (pivot here when weather or hold-ups stall the spine)
3.1 | Driveway channel — COMPLETE Wed 14 Oct (started and finished the same day; half a day, Luke and Max). Cobbles lifted, waste channel dug, water-softener discharge connected to natural drainage (confirmed working) and cobbles reinstated. £350, drawn from contingency (LG INV-0294, paid 17 Oct). | Luke +1 | — | 0.5 (est. 4) | Complete — Wed 14 Oct | 2026-10-14 | 2026-10-14
3.3 | Fence spurring, side (b) — concrete spurs, should complete before decking board-laying (2.5) starts; not blocking substructure work (2.3), which is already under way (propped temporarily). CORRECTED 11 Sep: unrelated to the shed/boundary issue — that's 2.7 (side a, chimney side, now complete), a separate fence. The 'new extended height' detail logged 8 Sep belonged to 2.7, not here. 3.3 itself still not done; propped temporarily, deferred to wet weather for the actual fix — no height change involved. | Luke +1 | → before 2.5 | 3 | Propped temporarily — repair/reposition targeted end of w/c 14 Sep, new extended height
3.4 | Tree / bush clearing back to fence boundary — EXTERNAL company; scope & cost outside this project | External co. | — | — | External
3.5 | Fence relocation — route per TPO outcome (original line or divert around tree) | Luke +1 | 3.4 + TPO | 4 | Floating
3.6 | Skip 2 — triggered by Luke's request when decking work needs it (not on a fixed cycle; skip 1 arrived 11 Aug) | Skip Hire Comparison Ltd | On request | — | Floating
T1 | TPO appeal decision — date TBC (branch point for 3.5) | External | — |  | Floating | TBC
V3 | V4 Phase 3 — 15 more boxes of Timberfix structural subframe screws (FH90P050), requested by Luke 20 Aug. ORDERED & PAID 24 Aug (V4FQ-17702, £141.66) — routed through Contingency (purpose #8), not this cost centre. | V4 Flooring | On request | £141.66 est. | Complete
V4 | V4 screw top-up #2 — 15 more boxes of Timberfix structural subframe screws (FH90P050), separate order from V3/purpose #8. Invoice received and PAID 10 Sep (£141.66, matching purpose #8 rate) — routed through Contingency (purpose #9), not this cost centre. Delivery scheduled 11 Sep. | V4 Flooring | On request | £141.66 est. | Paid, delivery scheduled 11 Sep
V6 | V4 delivery — materials to complete the decking substructure. Expected Tue 20 Oct. Invoice pending, amount unknown; nothing is logged in the budget tracker until the invoice arrives. | V4 Flooring | — | TBC | Delivery expected Tue 20 Oct — invoice pending | 2026-10-20 | 2026-10-20
Non-working: Luke holiday w/c 27 Jul & w/c 24 Aug (grey columns); UK bank holiday Mon 31 Aug (w/c 31 Aug is a 4-day week).
Rule: work proceeds only with Luke onsite. As of 10 Aug, works run in PARALLEL (chimney/coping/soakaway simultaneously) — the original one-phase-at-a-time model has been superseded by faster real-world pace. Rainy-day pool absorbs weather losses on render/roof work.
Decking start (1 Sep) is set by Luke's 22–29 Aug holiday, not by sequential dependencies — at-height works, gutters, strike and soakaway all complete well ahead of that date. | Board-laying (2.5) is set by G2 (roofline works, lead work, soft wash), G3 (tap/pipework/weed membrane) and G3B (substructure sign-off by Millboard) clearing, and by Luke's 22–29 Aug holiday — not by the old sequential model. Soakaway cancelled 1 Sep; excavation (2.2) and side (b) substructure (2.3) are running in parallel, well ahead of the original plan.
V4 Phase 1 (substructure, fixings, 2 boards) notified and delivered 10–12 Aug, ahead of the old formula-driven milestone. V4 Phase 2 (remaining boards) is ordered on request when needed, mirroring Skip 2's trigger logic.
Luke's outline (1 Jul): render, coping and roofing ~3 working weeks total — v1 durations are more conservative; await his corrections before compressing.

## Task Register
Task Register — locations, access discipline & pivot flags
Access rule: side (a) works use gate (a) exclusively (top-left entrance, lower/green deck); side (b) works use gate (b) exclusively (bottom-right entrance). No material movement over newly laid Millboard. Orange = upper level to summer house (see Decking_plan.pdf).
ID | Workstream | Task | Location | Access route | Weather-sensitive | Rainy-day eligible | Est. days | Notes / assumptions
1.0 | Site setup | Garden segregation fencing & site setup | Garden (both sides) | n/a | N | N | 2 | Keeps garden usable by family through Summer — working areas fenced, not a building site.
1.1 | Scaffolding | Erect Scaffold A (chimney) + Scaffold B (coping/gutters); discrete decking demolition at footing points | Roof perimeter, two locations | n/a | Y | N | 2 | Trevor's team. Fixed: Fri 17 – Sat 18 Jul. Both towers up together; remain until Gate 1 sign-off.
1.2 | Chimney | Cut render back to substrate, fix alignment, re-render | Chimney (Scaffold A) | Scaffold A | Y | N | 7 | Render weather-sensitive: no rain, not too hot. Target: complete before 22 Aug — first in queue to protect this.
1.3 | Coping stones | Cut back, lead flashing, replace coping stones, make watertight | Separate elevation (Scaffold B) | Scaffold B | Y | N | 10 | Independent scaffold structure from chimney.
1.4 | Scaffolding | Strike Scaffold A + B | Both locations | n/a | N | N | 1 | Only after Gate 1 sign-off (Lara/Neels/Ryan).
1.5 | Roofline works | Replace gutters (parapet both sides + lower rear elevation), extend fascia/soffit, replace various broken slates (incl. front tile repairs), white uPVC trim to barge boards | Roofline, both sides + rear | Ladder (Luke's own; no scaffold tower needed) | Y | N | 5 | MERGED 4 Oct from old 1.5 (back-gutter realign), 1.7 (this estimate) and 3.2 (front gutters/tile repairs). The estimate has no front-of-house gutters; front tile repairs are covered by 'replace various broken slates'. Own £2,140 estimate (4 Sep). Started 29 Sep, finishing Mon 5 Oct. Gates board-laying via Gate 2. UPDATE 9 Oct: roofline works concluded this week (w/c 5 Oct). UPDATE 13 Oct: reopened — remaining roofline works due Fri 16 Oct. UPDATE 17 Oct: COMPLETE Fri 16 Oct, including the lead flashing; ahead of the soft wash (Mon 19 Oct).
1.5a | Roofline works (extra) | Additional lead flashing — chase lead into the walls so the new back-of-house gutters work properly | Back of house, by the gutters | Ladder | Y | N | TBC | EXTRA SCOPE found during the roofline works; Luke's estimate about £200 (2 Oct), drawn from contingency. Part of Gate 2 — must finish before decking boards are laid. UPDATE 13 Oct: due Fri 16 Oct. UPDATE 17 Oct: COMPLETE Fri 16 Oct; lead flashing confirmed included. Awaiting Luke's invoice.
1.6 | Render treatment | Whole-house soft wash — Gorgeous Cleaning Services (gutters, soffits, roof tiles, solar panels, render, windows) | Whole house | n/a | N | N | TBC | Must complete before decking boards go down — chemical residue risk to new boards. Likely contingency-funded. Gates board-laying via Gate 2. UPDATE 9 Oct: status to confirm (was planned for Mon 5 Oct). UPDATE 13 Oct: REPLACED by a whole-house soft wash by Gorgeous Cleaning Services (£1,200 cash, contingency), starting Mon 19 Oct. UPDATE 17 Oct: Gorgeous Cleaning Services start Mon 19 Oct confirmed; all roofline works finished Fri 16 Oct.
2.1 | Drainage (soakaway) | Partial demolition of existing decking, new pipework off downpipes, reposition existing pipe | Back garden, side (a) | Gate (a) | Y | N | 5 | CANCELLED 1 Sep 2026 — family + Luke decision, cost-benefit ratio not worth it. Investigation phase (completed 18 Aug) is proceeding instead as part of the pipe investigation (3.7). No money was ever drawn against this from Contingency (named purpose #2) — clean cancellation, nothing to reverse.
2.2 | Decking (a) | Remove existing decking & substructure; install new substructure (board-laying now tracked separately at 2.5). Includes pipe investigation/excavation (folded in from former 3.7) — dual purpose: expose leaking waste pipe, widen decking area (straight lines). | Soakaway side (a) — green lower + share of orange upper | Gate (a) ONLY | N | N | 13 | IN PROGRESS from 3 Sep. PIPE RESOLVED: no leak found — damp ground was condensation trapped under old decking, not a plumbing fault. No repair needed, no contingency draw required. Earth reused as buttress-wall infill on side (b). Entrance = top-left of green deck on plan. UPDATE 9 Oct: substructure work continued w/c 5 Oct; end date TBC. UPDATE 13 Oct: Luke's team working on the extended decking area. UPDATE 17 Oct: Luke's team continued on the extended decking area; V4 delivery expected Tue 20 Oct to complete the substructure. Millboard site visit planned Thu 22 Oct (Gate 3B).
2.3 | Decking (b) | Remove existing decking & substructure; install new substructure (board-laying now tracked separately at 2.5) | Driveway side (b) | Gate (b) ONLY | N | N | 13 | IN PROGRESS — both lower and upper substructure layers under way as of 3 Sep. Entrance = bottom-right of green deck on plan. No crossing over side (a) new boards. UPDATE 9 Oct: substructure work continued w/c 5 Oct; end date TBC. UPDATE 13 Oct: Luke's team working on the extended decking area. UPDATE 17 Oct: Luke's team continued on the extended decking area; V4 delivery expected Tue 20 Oct to complete the substructure. Millboard site visit planned Thu 22 Oct (Gate 3B).
2.4 | Decking prep | Outside tap/pipework check (utility room to Summer house, under substructure) — check connections, extra pipe insulation, elbow support | Under decking substructure, both sides | n/a | N | N | TBC | Gates board-laying (2.5) via Gate 3.
2.5 | Decking (a+b) | Lay Millboard decking per design, all sides — combined into one task, including the new decking area leading up to the shed (perpendicular to side a) | Gate (a) and gate (b) as applicable | Gate a / Gate b | N | N | 13 | Gated on G2 (gutters/slate) and G3 (tap/pipework/weed membrane) clearing, plus substructure (2.2/2.3/2.6) completing.
2.6 | Decking (bonus) | New shed area, perpendicular to side (a) — excavation + substructure only (shed base and the new decking area's substructure). Board-laying tracked separately at 2.5. | Side (a) | Gate (a) | N | Y | 3 | CORRECTED 11 Sep: the related fence work is 2.7 (side a, chimney side, now complete), NOT 3.3 (side b) as first logged 8 Sep. Shed relocation onto its own base is NOT gated by board-laying — only by this task's own substructure completing (RE-PLAN 17 Sep: now ~29 Sep, was ~22 Sep). UPDATE 9 Oct: substructure work continued w/c 5 Oct; end date TBC. UPDATE 13 Oct: Luke's team working on the extended decking area. UPDATE 17 Oct: Luke's team continued on the extended decking area; V4 delivery expected Tue 20 Oct to complete the substructure. Millboard site visit planned Thu 22 Oct (Gate 3B).
3.1 | Driveway channel | Lift bricks/cobbles, dig waste channel, connect water-softener discharge to natural drainage, reinstate cobbles | Front driveway | Front | N | Y | 4 | COMPLETE Wed 14 Oct — started and finished in one day (half a day, Luke and Max). Water-softener discharge connected to natural drainage and confirmed working; cobbles reinstated. £350 from contingency (LG INV-0294, paid 17 Oct). Previously an active problem (softener free-flooding the driveway).
3.3 | Fencing | Fence spurring, side (b) first | Garden boundary | Garden | N | Y | 3 | HARD CONSTRAINT (as designed): side (b) spurring should complete before decking board-laying (2.5) begins. STATUS 8 Sep: not yet done, propped temporarily, deferred to wet weather. CORRECTED 11 Sep: unrelated to the shed/boundary issue — that's 2.7, a separate fence. The 'extended height' note logged 8 Sep belonged there, not here.
3.4 | Fencing | Tree / bush clearing back to fence boundary — EXTERNAL company | Garden boundary | Garden | N | Y | 2 | Outside project scope and budget; details and costs handled separately. Prerequisite for fence relocation (3.5) only.
3.5 | Fencing | Fence relocation — original line (TPO appeal succeeds) or divert around tree (fails) | Garden boundary | Garden | N | Y | 4 | Gated on TPO decision (T1, date TBC). Both routes pre-planned.
2.7 | Fence move, chimney side | Boundary reclaimed from neighbour, side a, to enable the wider decking area; repositioned at new extended height | Chimney side / side a | n/a | N | N | 1 | COMPLETE 11 Sep. This is the fence the 8 Sep boundary/scope-increase note referred to — not 3.3 (side b spurs) or 3.5 (TPO-dependent).

## Reference
Reference — contacts, rules, assumptions, sign-off log
CONTACTS (fill in yellow cells — phone / email are placeholders)
Name | Role | Team | Phone | Email
EXAMPLE — Jane Doe | Example row — format guide | — | 07700 900123 | jane.doe@example.com
Lara | Key Decision Maker & Budget Holder | Family | 07791 528837 | larakriek@gmail.com
Neels | Project management support | Family | 07880 688027 | neels.kriek@gmail.com
Ryan | Project manager | Family | 07851 601499 | ryanbishop23@gmail.com
Luke | Chief builder, head of company | L.G Building and Roofing Ltd | 07799 748123
Ross | Right-hand man | L.G Building and Roofing Ltd
Max | Right-hand man | L.G Building and Roofing Ltd
Roy | Right-hand man | L.G Building and Roofing Ltd
Trevor | Scaffold team contact | L.G Building and Roofing Ltd
V4 Flooring | Decking materials storage & delivery | V4 Flooring | 01276 488099
WORKING RULES
• Work proceeds only if Luke is onsite.
• SUPERSEDED 10 Aug: works now run in PARALLEL (chimney, coping, soakaway simultaneously) — the original one-phase-at-a-time model no longer reflects actual practice.
• Crew planning basis: Luke +1 (conservative). Additional hands = schedule upside, never assumed.
• Working days: Monday–Friday, excluding Luke's holidays and UK bank holidays.
• Luke holidays: 25 Jul – 1 Aug and 22 – 29 Aug 2026. Bank holiday: Mon 31 Aug 2026.
• Stage gates signed off by Lara, Ryan and Neels before the next stage begins.
• Weather rule: if render/roof work is unfavourable (rain, or too hot to render), crew pivots to the rainy-day pool (Phase 3).
• Access discipline: side (a) via gate (a) only; side (b) via gate (b) only. No materials over new Millboard.
• V4 Flooring: notify 2 weeks (14 calendar days) before decking materials are required onsite.
KEY ASSUMPTIONS (open — to be confirmed)
• A1 RESOLVED (10 Aug): scaffold erection found wet ground at the chimney tower — not a soakaway pipe-run obstruction, but evidence suggesting a leaking house waste pipe beneath the chimney. See new finding below.
• NEW (10 Aug): Wet ground beneath chimney scaffold suggests a leaking waste pipe from the house. Investigation can only happen once scaffold is struck AND old decking/substructure removed in that specific area — timing depends on which decking side (a/b) sits beneath the chimney (TBC with Ryan). Cost: contingency-funded, no figure yet — would be named purpose #7 (coping condensation-prep took #6, 13 Aug).
• A2: All durations are planning estimates pending Luke's review of this v1.
• A3: Decking (a)/(b) split ≈ 2.5 weeks each within the 5-week decking ceiling.
• A4: V4 landing zone to be agreed with Luke without breaching gate segregation.
• A5: TPO appeal decision date unknown — fence relocation (3.5) floats until known.
STAGE GATE SIGN-OFF LOG
Gate | Description | Date signed | Lara | Neels | Ryan
G1 | At-height works (chimney, coping) — scaffold may strike | 2026-08-18
G2 | Roofline works (incl. slates), additional lead flashing and whole-house soft wash completed, before decking boards are laid — roofline works and lead flashing complete Fri 16 Oct; whole-house soft wash (from Mon 19 Oct) outstanding
G3 | Outside tap/pipework insulated, and weed-stop membrane installed, before decking boards go down
G3B | Substructure sign-off — Millboard technical area manager (and Jon, V4 Flooring) view and sign off the completed substructure before any boards are laid — Millboard site visit planned Thu 22 Oct (sign-off not yet given)
G4 | Decking sign-off, all sides
G5 | Project completion — snagging & final sign-off
HOW TO UPDATE THIS WORKBOOK
• Edit only blue-on-yellow cells: task Start/End dates (Gantt), Last updated, contact details, and the sign-off log.
• Gantt bars redraw automatically from Start/End dates — never colour grid cells by hand.
• V4 Phase 1 (V1) and Phase 2 (V2) are fixed/on-request entries, not formulas, since the 10 Aug replan — Phase 1 delivered 12 Aug; Phase 2 ordered on request when needed.
• To activate a floating task: give it Start/End dates and change Status from 'Floating' to 'In progress'.
• Status values: Not started / In progress / Complete / Blocked / Floating.
• Back gutters & front tile repairs (10 Aug): an earlier WhatsApp confirmed both as included in Luke's overall roof-work scope, no separate charge. SUPERSEDED 4 Oct: the roofline works estimate (4 Sep, £2,140) replaces the gutter work; it has no front-of-house gutters, and front tile repairs are covered by 'replace various broken slates'. Tasks 1.5, 1.7 and 3.2 are merged into 1.5 (numbers not reused).
• EXCLUDED from Luke's scope (per same WhatsApp): work to the summer house ("out house") at the top deck — Luke made no assessment/notes on it. Distinct from the new decking build (separately quoted, proceeding). Do not assume any summer-house fabric work is covered.
• Gate 3B (substructure sign-off): Ryan will invite Millboard's technical area manager and Jon (V4 Flooring) to view and sign off the completed substructure before any boards are laid — validates the warranty; photos for the project record and PR. Site visit planned Thu 22 Oct.