## Tolerance log
Spinney — Bullnose board calliper log, 27 Oct 2026
Millboard Ashwood bullnose (MEBB360H), 19 boards measured by calliper (mm). Readings are the handwritten record of 27/10/26; crossed-out values resolved by Ryan: #1 right back 31.65, #2 left back 31.73, #7 left width 150.63, #11 left back 31.95.
Nominal width (mm) |  | 150 | Assumed nominals — edit if the manufacturer figures differ; all deviations and pass/fail below recalculate.
Nominal thickness (mm) |  | 32
Tolerance, ± (mm) — manufacturer guideline |  | 2
Board # | Batch | Status | Left width | Left back | Left bullnose | Right width | Right back | Right bullnose | Δ L width | Δ L back | Δ L bullnose | Δ R width | Δ R back | Δ R bullnose | Worst ¦Δ¦ | Result
1 | — | Fixed in place (fence edge) | 149.48 | 31.23 | 30.28 | 150.12 | 31.65 | 31.29 | -0.52 | -0.77 | -1.72 | 0.12 | -0.35 | -0.71 | 1.72 | Pass
2 | — | Fixed in place (fence edge) | 151.27 | 31.73 | 30.5 | 150.99 | 31.73 | 31 | 1.27 | -0.27 | -1.5 | 0.99 | -0.27 | -1 | 1.5 | Pass
3 | — | Fixed in place (fence edge) | 151.04 | 31.76 | 30.7 | 150.04 | 30.7 | 32.02 | 1.04 | -0.24 | -1.3 | 0.04 | -1.3 | 0.02 | 1.3 | Pass
4 | — | Fixed in place (fence edge) | 151.21 | 30.97 | 31.17 | 150.5 | 31.31 | 31.42 | 1.21 | -1.03 | -0.83 | 0.5 | -0.69 | -0.58 | 1.21 | Pass
5 | — | Fixed in place (fence edge) | 150.64 | 31.04 | 31.05 | 149.64 | 31.04 | 31.05 | 0.64 | -0.96 | -0.95 | -0.36 | -0.96 | -0.95 | 0.96 | Pass
6 | — | Fixed in place (fence edge) | 151.08 | 31.6 | 30.87 | 151.24 | 31.6 | 31.47 | 1.08 | -0.4 | -1.13 | 1.24 | -0.4 | -0.53 | 1.24 | Pass
7 | 1011 030626 | Uncut | 150.63 | 31.06 | 31.07 | 149.46 | 30.75 | 31.34 | 0.63 | -0.94 | -0.93 | -0.54 | -1.25 | -0.66 | 1.25 | Pass
8 | 1008 030626 | Uncut | 150.64 | 32.45 | 31.45 | 149.33 | 31.48 | 31.31 | 0.64 | 0.45 | -0.55 | -0.67 | -0.52 | -0.69 | 0.69 | Pass
9 | 1830 03082026 | Uncut | 150.69 | 31.76 | 31.86 | 149.49 | 31.86 | 32.17 | 0.69 | -0.24 | -0.14 | -0.51 | -0.14 | 0.17 | 0.69 | Pass
10 | 1739 03082026 | Uncut | 151.4 | 30.89 | 31.81 | 150.7 | 31.74 | 31.87 | 1.4 | -1.11 | -0.19 | 0.7 | -0.26 | -0.13 | 1.4 | Pass
11 | 1739 03082026 | Uncut | 150.25 | 31.95 | 31.47 | 150.11 | 32.37 | 31.27 | 0.25 | -0.05 | -0.53 | 0.11 | 0.37 | -0.73 | 0.73 | Pass
12 | 0741 030626 | Uncut | 151.04 | 31.4 | 31.1 | 150.35 | 31.58 | 31.52 | 1.04 | -0.6 | -0.9 | 0.35 | -0.42 | -0.48 | 1.04 | Pass
13 | 1029 030626 | Uncut | 149.72 | 31.59 | 31.12 | 150.28 | 31.84 | 31.32 | -0.28 | -0.41 | -0.88 | 0.28 | -0.16 | -0.68 | 0.88 | Pass
14 | 1012 030626 | Uncut | 150.4 | 31.61 | 31.39 | 150.25 | 31.53 | 31 | 0.4 | -0.39 | -0.61 | 0.25 | -0.47 | -1 | 1 | Pass
15 | 1020 030626 | Uncut | 150.45 | 31.06 | 31.04 | 150.25 | 31.57 | 31.69 | 0.45 | -0.94 | -0.96 | 0.25 | -0.43 | -0.31 | 0.96 | Pass
16 | 1025 030626 | Uncut | 150.61 | 31.24 | 31.21 | 149.65 | 31.29 | 31.81 | 0.61 | -0.76 | -0.79 | -0.35 | -0.71 | -0.19 | 0.79 | Pass
17 | 1018 030626 | Uncut | 150.29 | 31.09 | 31.06 | 149.43 | 31.2 | 31.16 | 0.29 | -0.91 | -0.94 | -0.57 | -0.8 | -0.84 | 0.94 | Pass
18 | — (Gate step) | Fixed in place (gate step) | 150.44 | 31.43 | 31.16 | 150.77 | 31.18 | 31.42 | 0.44 | -0.57 | -0.84 | 0.77 | -0.82 | -0.58 | 0.84 | Pass
19 | — (Diagonal to upper level) | Fixed in place (diagonal to upper level) | 150.17 | 31.33 | 31.87 | 149.99 | 31.33 | 31.29 | 0.17 | -0.67 | -0.13 | -0.01 | -0.67 | -0.71 | 0.71 | Pass
Summary
Boards measured |  |  | 19
Boards passing |  |  | 19
Boards failing |  |  | 0
Largest deviation from nominal (mm) |  |  | 1.72
Smallest width reading (mm) |  |  | 149.33
Largest width reading (mm) |  |  | 151.4
Smallest thickness reading (mm) |  |  | 30.28
Largest thickness reading (mm) |  |  | 32.45
Boards #1–6, #18 and #19 carry no batch code: they were measured before being cut to shape and fixed. Boards #7–17 are uncut with batch code underneath. 18 full-length equivalents in total (7 cut + 11 uncut).

## Laying order
Optimal laying order — 11 uncut bullnose boards, one continuous edge, laid left to right
Method: a joint is the RIGHT end of one board meeting the LEFT end of the next. Mismatch = absolute difference between those two readings. Every possible order of the 11 boards was tested (exact, not a heuristic); the order with the smallest total mismatch wins. First board joins on its right only; last board joins on its left only.
Four scenarios: optimise for width, bullnose face thickness, back-edge thickness, or all three together (worst of the three at each joint). Boards are laid in the orientation measured (left end to the left); no board is turned round. Boards already fixed (#1–6, #18, #19) are excluded.
Mismatch figures are live formulas against the Tolerance log sheet. Lower is better; a smaller mismatch means less visible step at the joint.
Summary — best order by scenario
Scenario | Best laying order (board numbers, left → right) | Total mismatch (mm) | Worst single joint (mm) | Typical random order (mm) | Improvement vs random
Width | 10 → 12 → 7 → 9 → 11 → 14 → 15 → 16 → 13 → 17 → 8 | 4.75 | 1.23 | 7.09 | 33%
Bullnose face | 17 → 7 → 14 → 15 → 8 → 12 → 11 → 13 → 16 → 10 → 9 | 0.95 | 0.24 | 3.85 | 75.32%
Back edge | 7 → 10 → 9 → 11 → 8 → 12 → 14 → 16 → 17 → 15 → 13 | 1.09 | 0.29 | 5.04 | 78.37%
Combined (worst of the three) | 10 → 9 → 11 → 8 → 13 → 12 → 16 → 15 → 14 → 7 → 17 | 5.2 | 0.83 | 9 | 42.22%
"Typical random order" is the average total mismatch over all possible orders, for comparison. Combined scenario scores each joint by its worst of the three differences.
Scenario: Width
Best order | 10 → 12 → 7 → 9 → 11 → 14 → 15 → 16 → 13 → 17 → 8
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 10 | 1739 03082026 | 150.70 → 151.04 | 12 | 0.34
2 | 12 | 0741 030626 | 150.35 → 150.63 | 7 | 0.28
3 | 7 | 1011 030626 | 149.46 → 150.69 | 9 | 1.23
4 | 9 | 1830 03082026 | 149.49 → 150.25 | 11 | 0.76
5 | 11 | 1739 03082026 | 150.11 → 150.40 | 14 | 0.29
6 | 14 | 1012 030626 | 150.25 → 150.45 | 15 | 0.2
7 | 15 | 1020 030626 | 150.25 → 150.61 | 16 | 0.36
8 | 16 | 1025 030626 | 149.65 → 149.72 | 13 | 0.07
9 | 13 | 1029 030626 | 150.28 → 150.29 | 17 | 0.01
10 | 17 | 1018 030626 | 149.43 → 150.64 | 8 | 1.21
11 | 8 | 1008 030626 | (end of edge)
Total mismatch | 4.75 | Worst joint | 1.23
2nd-best alternative | 10 → 12 → 7 → 9 → 11 → 14 → 15 → 16 → 17 → 13 → 8
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 10 | 1739 03082026 | 150.70 → 151.04 | 12 | 0.34
2 | 12 | 0741 030626 | 150.35 → 150.63 | 7 | 0.28
3 | 7 | 1011 030626 | 149.46 → 150.69 | 9 | 1.23
4 | 9 | 1830 03082026 | 149.49 → 150.25 | 11 | 0.76
5 | 11 | 1739 03082026 | 150.11 → 150.40 | 14 | 0.29
6 | 14 | 1012 030626 | 150.25 → 150.45 | 15 | 0.2
7 | 15 | 1020 030626 | 150.25 → 150.61 | 16 | 0.36
8 | 16 | 1025 030626 | 149.65 → 150.29 | 17 | 0.64
9 | 17 | 1018 030626 | 149.43 → 149.72 | 13 | 0.29
10 | 13 | 1029 030626 | 150.28 → 150.64 | 8 | 0.36
11 | 8 | 1008 030626 | (end of edge)
Total mismatch | 4.75 | Worst joint | 1.23
3rd-best alternative | 10 → 12 → 7 → 9 → 11 → 14 → 15 → 17 → 13 → 16 → 8
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 10 | 1739 03082026 | 150.70 → 151.04 | 12 | 0.34
2 | 12 | 0741 030626 | 150.35 → 150.63 | 7 | 0.28
3 | 7 | 1011 030626 | 149.46 → 150.69 | 9 | 1.23
4 | 9 | 1830 03082026 | 149.49 → 150.25 | 11 | 0.76
5 | 11 | 1739 03082026 | 150.11 → 150.40 | 14 | 0.29
6 | 14 | 1012 030626 | 150.25 → 150.45 | 15 | 0.2
7 | 15 | 1020 030626 | 150.25 → 150.29 | 17 | 0.04
8 | 17 | 1018 030626 | 149.43 → 149.72 | 13 | 0.29
9 | 13 | 1029 030626 | 150.28 → 150.61 | 16 | 0.33
10 | 16 | 1025 030626 | 149.65 → 150.64 | 8 | 0.99
11 | 8 | 1008 030626 | (end of edge)
Total mismatch | 4.75 | Worst joint | 1.23
Scenario: Bullnose face
Best order | 17 → 7 → 14 → 15 → 8 → 12 → 11 → 13 → 16 → 10 → 9
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 17 | 1018 030626 | 31.16 → 31.07 | 7 | 0.09
2 | 7 | 1011 030626 | 31.34 → 31.39 | 14 | 0.05
3 | 14 | 1012 030626 | 31.00 → 31.04 | 15 | 0.04
4 | 15 | 1020 030626 | 31.69 → 31.45 | 8 | 0.24
5 | 8 | 1008 030626 | 31.31 → 31.10 | 12 | 0.21
6 | 12 | 0741 030626 | 31.52 → 31.47 | 11 | 0.05
7 | 11 | 1739 03082026 | 31.27 → 31.12 | 13 | 0.15
8 | 13 | 1029 030626 | 31.32 → 31.21 | 16 | 0.11
9 | 16 | 1025 030626 | 31.81 → 31.81 | 10 | 0
10 | 10 | 1739 03082026 | 31.87 → 31.86 | 9 | 0.01
11 | 9 | 1830 03082026 | (end of edge)
Total mismatch | 0.95 | Worst joint | 0.24
2nd-best alternative | 17 → 7 → 14 → 15 → 8 → 13 → 12 → 11 → 16 → 10 → 9
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 17 | 1018 030626 | 31.16 → 31.07 | 7 | 0.09
2 | 7 | 1011 030626 | 31.34 → 31.39 | 14 | 0.05
3 | 14 | 1012 030626 | 31.00 → 31.04 | 15 | 0.04
4 | 15 | 1020 030626 | 31.69 → 31.45 | 8 | 0.24
5 | 8 | 1008 030626 | 31.31 → 31.12 | 13 | 0.19
6 | 13 | 1029 030626 | 31.32 → 31.10 | 12 | 0.22
7 | 12 | 0741 030626 | 31.52 → 31.47 | 11 | 0.05
8 | 11 | 1739 03082026 | 31.27 → 31.21 | 16 | 0.06
9 | 16 | 1025 030626 | 31.81 → 31.81 | 10 | 0
10 | 10 | 1739 03082026 | 31.87 → 31.86 | 9 | 0.01
11 | 9 | 1830 03082026 | (end of edge)
Total mismatch | 0.95 | Worst joint | 0.24
3rd-best alternative | 17 → 7 → 14 → 15 → 11 → 12 → 8 → 13 → 16 → 10 → 9
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 17 | 1018 030626 | 31.16 → 31.07 | 7 | 0.09
2 | 7 | 1011 030626 | 31.34 → 31.39 | 14 | 0.05
3 | 14 | 1012 030626 | 31.00 → 31.04 | 15 | 0.04
4 | 15 | 1020 030626 | 31.69 → 31.47 | 11 | 0.22
5 | 11 | 1739 03082026 | 31.27 → 31.10 | 12 | 0.17
6 | 12 | 0741 030626 | 31.52 → 31.45 | 8 | 0.07
7 | 8 | 1008 030626 | 31.31 → 31.12 | 13 | 0.19
8 | 13 | 1029 030626 | 31.32 → 31.21 | 16 | 0.11
9 | 16 | 1025 030626 | 31.81 → 31.81 | 10 | 0
10 | 10 | 1739 03082026 | 31.87 → 31.86 | 9 | 0.01
11 | 9 | 1830 03082026 | (end of edge)
Total mismatch | 0.95 | Worst joint | 0.22
Scenario: Back edge
Best order | 7 → 10 → 9 → 11 → 8 → 12 → 14 → 16 → 17 → 15 → 13
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 7 | 1011 030626 | 30.75 → 30.89 | 10 | 0.14
2 | 10 | 1739 03082026 | 31.74 → 31.76 | 9 | 0.02
3 | 9 | 1830 03082026 | 31.86 → 31.95 | 11 | 0.09
4 | 11 | 1739 03082026 | 32.37 → 32.45 | 8 | 0.08
5 | 8 | 1008 030626 | 31.48 → 31.40 | 12 | 0.08
6 | 12 | 0741 030626 | 31.58 → 31.61 | 14 | 0.03
7 | 14 | 1012 030626 | 31.53 → 31.24 | 16 | 0.29
8 | 16 | 1025 030626 | 31.29 → 31.09 | 17 | 0.2
9 | 17 | 1018 030626 | 31.20 → 31.06 | 15 | 0.14
10 | 15 | 1020 030626 | 31.57 → 31.59 | 13 | 0.02
11 | 13 | 1029 030626 | (end of edge)
Total mismatch | 1.09 | Worst joint | 0.29
2nd-best alternative | 7 → 10 → 9 → 11 → 8 → 16 → 17 → 15 → 14 → 12 → 13
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 7 | 1011 030626 | 30.75 → 30.89 | 10 | 0.14
2 | 10 | 1739 03082026 | 31.74 → 31.76 | 9 | 0.02
3 | 9 | 1830 03082026 | 31.86 → 31.95 | 11 | 0.09
4 | 11 | 1739 03082026 | 32.37 → 32.45 | 8 | 0.08
5 | 8 | 1008 030626 | 31.48 → 31.24 | 16 | 0.24
6 | 16 | 1025 030626 | 31.29 → 31.09 | 17 | 0.2
7 | 17 | 1018 030626 | 31.20 → 31.06 | 15 | 0.14
8 | 15 | 1020 030626 | 31.57 → 31.61 | 14 | 0.04
9 | 14 | 1012 030626 | 31.53 → 31.40 | 12 | 0.13
10 | 12 | 0741 030626 | 31.58 → 31.59 | 13 | 0.01
11 | 13 | 1029 030626 | (end of edge)
Total mismatch | 1.09 | Worst joint | 0.24
3rd-best alternative | 15 → 14 → 16 → 17 → 7 → 10 → 9 → 11 → 8 → 12 → 13
Position | Board # | Batch | Right end → Next board left end | Next board # | Mismatch at joint (mm)
1 | 15 | 1020 030626 | 31.57 → 31.61 | 14 | 0.04
2 | 14 | 1012 030626 | 31.53 → 31.24 | 16 | 0.29
3 | 16 | 1025 030626 | 31.29 → 31.09 | 17 | 0.2
4 | 17 | 1018 030626 | 31.20 → 31.06 | 7 | 0.14
5 | 7 | 1011 030626 | 30.75 → 30.89 | 10 | 0.14
6 | 10 | 1739 03082026 | 31.74 → 31.76 | 9 | 0.02
7 | 9 | 1830 03082026 | 31.86 → 31.95 | 11 | 0.09
8 | 11 | 1739 03082026 | 32.37 → 32.45 | 8 | 0.08
9 | 8 | 1008 030626 | 31.48 → 31.40 | 12 | 0.08
10 | 12 | 0741 030626 | 31.58 → 31.59 | 13 | 0.01
11 | 13 | 1029 030626 | (end of edge)
Total mismatch | 1.09 | Worst joint | 0.29
Scenario: Combined (worst of the three)
Best order | 10 → 9 → 11 → 8 → 13 → 12 → 16 → 15 → 14 → 7 → 17
Position | Board # | Batch | Next board # | Width mismatch (mm) | Bullnose-face mismatch (mm) | Back-edge mismatch (mm) | Worst of three (mm)
1 | 10 | 1739 03082026 | 9 | 0.01 | 0.01 | 0.02 | 0.02
2 | 9 | 1830 03082026 | 11 | 0.76 | 0.7 | 0.09 | 0.76
3 | 11 | 1739 03082026 | 8 | 0.53 | 0.18 | 0.08 | 0.53
4 | 8 | 1008 030626 | 13 | 0.39 | 0.19 | 0.11 | 0.39
5 | 13 | 1029 030626 | 12 | 0.76 | 0.22 | 0.44 | 0.76
6 | 12 | 0741 030626 | 16 | 0.26 | 0.31 | 0.34 | 0.34
7 | 16 | 1025 030626 | 15 | 0.8 | 0.77 | 0.23 | 0.8
8 | 15 | 1020 030626 | 14 | 0.15 | 0.3 | 0.04 | 0.3
9 | 14 | 1012 030626 | 7 | 0.38 | 0.07 | 0.47 | 0.47
10 | 7 | 1011 030626 | 17 | 0.83 | 0.28 | 0.34 | 0.83
11 | 17 | 1018 030626 | (end of edge)
Total mismatch | 5.2 | Worst joint | 0.83
2nd-best alternative | 10 → 9 → 11 → 8 → 13 → 12 → 14 → 16 → 15 → 7 → 17
Position | Board # | Batch | Next board # | Width mismatch (mm) | Bullnose-face mismatch (mm) | Back-edge mismatch (mm) | Worst of three (mm)
1 | 10 | 1739 03082026 | 9 | 0.01 | 0.01 | 0.02 | 0.02
2 | 9 | 1830 03082026 | 11 | 0.76 | 0.7 | 0.09 | 0.76
3 | 11 | 1739 03082026 | 8 | 0.53 | 0.18 | 0.08 | 0.53
4 | 8 | 1008 030626 | 13 | 0.39 | 0.19 | 0.11 | 0.39
5 | 13 | 1029 030626 | 12 | 0.76 | 0.22 | 0.44 | 0.76
6 | 12 | 0741 030626 | 14 | 0.05 | 0.13 | 0.03 | 0.13
7 | 14 | 1012 030626 | 16 | 0.36 | 0.21 | 0.29 | 0.36
8 | 16 | 1025 030626 | 15 | 0.8 | 0.77 | 0.23 | 0.8
9 | 15 | 1020 030626 | 7 | 0.38 | 0.62 | 0.51 | 0.62
10 | 7 | 1011 030626 | 17 | 0.83 | 0.28 | 0.34 | 0.83
11 | 17 | 1018 030626 | (end of edge)
Total mismatch | 5.2 | Worst joint | 0.83
3rd-best alternative | 10 → 9 → 11 → 8 → 13 → 14 → 16 → 15 → 12 → 7 → 17
Position | Board # | Batch | Next board # | Width mismatch (mm) | Bullnose-face mismatch (mm) | Back-edge mismatch (mm) | Worst of three (mm)
1 | 10 | 1739 03082026 | 9 | 0.01 | 0.01 | 0.02 | 0.02
2 | 9 | 1830 03082026 | 11 | 0.76 | 0.7 | 0.09 | 0.76
3 | 11 | 1739 03082026 | 8 | 0.53 | 0.18 | 0.08 | 0.53
4 | 8 | 1008 030626 | 13 | 0.39 | 0.19 | 0.11 | 0.39
5 | 13 | 1029 030626 | 14 | 0.12 | 0.07 | 0.23 | 0.23
6 | 14 | 1012 030626 | 16 | 0.36 | 0.21 | 0.29 | 0.36
7 | 16 | 1025 030626 | 15 | 0.8 | 0.77 | 0.23 | 0.8
8 | 15 | 1020 030626 | 12 | 0.79 | 0.59 | 0.17 | 0.79
9 | 12 | 0741 030626 | 7 | 0.28 | 0.45 | 0.52 | 0.52
10 | 7 | 1011 030626 | 17 | 0.83 | 0.28 | 0.34 | 0.83
11 | 17 | 1018 030626 | (end of edge)
Total mismatch | 5.23 | Worst joint | 0.83