## Summary
Spinney External Works — Budget Summary
Last updated: | 2026-07-13 | All figures gross (as payable). Invoiced / Paid pull automatically from the Invoice Register; Contingency remaining pulls from the Drawdown sheet.
Cost centre | Supplier | Committed £ | Invoiced £ | Paid £ | Remaining vs committed £ | Notes
Decking materials | V4 Wood Flooring Ltd | 32228.99 | 32228.99 | 32228.99 | 0 | Order amended to all Ashwood + flexible bullnose (1 Jul). PAID IN FULL 9 Jul, ref V4FQ-15584. 25% restocking on over-ordering — unlikely given curved design + offcuts project, but noted.
Decking labour & rubbish | LG Building and Roofing Ltd | 18800 | 0 | 0 | 18800 | £17,600 labour (no VAT) + £1,200 rubbish removal. RISK: price 'fairly accurate' pending Luke's structure/ground assessment.
Contingency | — | 5000 | 0 | 0 | 5000 | Covers: fence move/repair labour; soakaway fix before decking; drainage by garage; extra curved-decking labour; cement & bricks. See Contingency Drawdown sheet.
Chimney repair | LG Building and Roofing Ltd | 5260 | 0 | 0 | 5260 | Quoted separately (2 Jun). £3,200 labour no VAT; scaffolding £1,500 and materials £480 paid directly; £80 rubbish.
Coping stones repair | LG Building and Roofing Ltd | 6230 | 0 | 0 | 6230 | Quoted separately (3 Jun). RISK: damage to coping stones on removal could substantially increase cost.
Core project (Luke's ~£56,800 outline) |  | 56028.99 | 32228.99 | 32228.99 | 23800
Quoted separately (chimney + coping) |  | 11490 | 0 | 0 | 11490
PROJECT TOTAL |  | 67518.99 | 32228.99 | 32228.99 | 35290
Contingency remaining: | 5000

## Cost Lines
Cost Lines — every line item from LG estimates and the V4 invoice
Source documents: LG chimney estimate 2 Jun 2026 · LG coping estimate 3 Jun 2026 · LG decking estimate 3 Jun 2026 · V4 invoice V4FQ-15584, 9 Jul 2026.
Cost centre | Supplier | Line item | Qty | Unit £ | Line total £ | VAT | Payment route | Notes
Chimney repair | LG Building | Labour — remove render, k-rend sealer, base + top coat, render crown, storm-dry cream |  |  | 3200 | No VAT | LG invoice
Chimney repair | Scaffolder (direct) | Tubular scaffolding — all four sides of chimney and crown |  |  | 1500 | Inc VAT | Paid directly
Chimney repair | Merchant (direct) | Materials |  |  | 480 | Inc VAT | Paid directly
Chimney repair | LG Building | Rubbish removal |  |  | 80 | Inc VAT | LG invoice
Coping stones repair | LG Building | Labour — remove/reset copings, slate cap, render, lead flashings to parapet rear |  |  | 3800 | No VAT | LG invoice | RISK: stone damage on removal could substantially increase cost
Coping stones repair | Scaffolder (direct) | Tubular scaffolding with winch system |  |  | 1700 | Inc VAT | Paid directly
Coping stones repair | Merchant (direct) | Materials |  |  | 650 | Inc VAT | Paid directly
Coping stones repair | LG Building | Rubbish removal |  |  | 80 | Inc VAT | LG invoice
Decking labour & rubbish | LG Building | Labour — remove old decking & frame, construct composite frame, install deck to spec |  |  | 17600 | No VAT | LG invoice | RISK: pending structure/ground assessment
Decking labour & rubbish | LG Building | Rubbish removal (8-yard skips ×2, possibly 3) |  |  | 1200 | Inc VAT | LG invoice
Decking materials | V4 Wood Flooring | Millboard Ashwood 176mm Moulded Lastane (144.90 m²) | 230 | 66.49 | 15292.7 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MFN360H | 18 | 58.09 | 1045.62 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MEBB360H (flexible bullnose) | 15 | 72.25 | 1083.75 | In net | V4 invoice — PAID | For curved upper level
Decking materials | V4 Wood Flooring | Millboard Step Edge — Ashwood Moulded Lastane | 15 | 59.89 | 898.35 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Stainless steel screws 45mm — boxes | 24 | 32.08 | 770 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Durafix Trimhead 35mm SS screws — box of 100 (FT35P100) | 6 | 10.25 | 61.5 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Plas-Pro bearer/joist black 3.0m 50×125mm composite (P1205B300) | 266 | 28.4 | 7554.4 | In net | V4 invoice — PAID | Subframe — the bulk of the tonnage
Decking materials | V4 Wood Flooring | Subframe hexhead screws — box of 50 (FH90P050) | 16 | 7.87 | 125.92 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard touch-up paint — Ashwood (AP500H) | 1 | 15 | 15 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard multi-spacer — pack of 10 (FP36P010) | 1 | 10.25 | 10.25 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | VAT on order |  |  | 5371.5 | VAT | V4 invoice — PAID | Net £26,857.49 + VAT = £32,228.99
Contingency | TBC | Contingency pot — fence labour, soakaway fix, garage drainage, curved-deck labour, cement & bricks |  |  | 5000 | — | As incurred | Track on Contingency Drawdown sheet
|  | TOTAL (all lines) |  |  | 67518.99

## Invoice Register
Invoice & Payment Register — add a row per invoice received
Yellow cells are inputs. Cost centre must match the Summary sheet names exactly (dropdown-free by design — copy from row 5). Paid date empty = outstanding.
Invoice date | Cost centre | Supplier | Reference | Description | Amount £ (gross) | Paid date | Method | Notes
2026-07-09 | Decking materials | V4 Wood Flooring Ltd | V4FQ-15584 | Millboard Ashwood decking + Plas-Pro subframe, fixings (144.9 m²) | 32228.99 | 2026-07-09 | Amex | Paid in full at order

## Contingency Drawdown
Contingency Drawdown — £5,000 pot (agreed Lara/Luke, 1 Jul 2026)
Named purposes: fence move/repair labour · soakaway fix before decking · drainage by the garage · additional curved-decking labour · cement & bricks for decking works.
Opening pot: | 5000 | Remaining: | 5000
Date | Purpose | Supplier / detail | Amount £ | Running remaining £