## Summary
Spinney External Works — Budget Summary
Last updated: | 2026-10-13 | All figures gross (as payable). Invoiced / Paid pull automatically from the Invoice Register; Contingency remaining pulls from the Drawdown sheet.
Cost centre | Supplier | Committed £ | Invoiced £ | Paid £ | Remaining vs committed £ | Notes
Decking materials (V4) | V4 Wood Flooring Ltd | 32228.99 | 32228.99 | 32228.99 | 0 | Order amended to all Ashwood + flexible bullnose (1 Jul). PAID IN FULL 9 Jul, ref V4FQ-15584. 25% restocking on over-ordering — unlikely given curved design + offcuts project, but noted. A separate, later V4 order (£5,322.74, quote #QUO-0031, 29 Sep) for the expanded shed-area/fence-move decking scope is tracked under Contingency (named purpose #24), not here — see that sheet.
Decking labour | LG Building and Roofing Ltd | 17600 | 8400 | 8400 | 9200 | Labour £17,600 (no VAT). Stage 1 (£4,400) invoiced/paid 20 Aug, full price. Two cash instalments since (£2,000 each, 4 Sep + 18 Sep) — 10% discount applies to both, retiring £2,222.22 of quoted value each. £8,400 cash paid to date, equivalent to £8,844.44 of quoted value — £8,755.56 quoted value remaining. Rubbish removal (£1,200) transferred 10 Aug to pooled skip fund — see that row, not double-counted here. The separate extra labour for the curves and additional deck (INV-0293, £1,850, 9 Oct) sits under Contingency, not here; it does not change the £8,755.56 remaining.
Contingency | — | 5000 | 12664.39 | 12664.39 | -7664.39 | Covers: fence move/repair labour; soakaway fix before decking; drainage by garage; extra curved-decking labour; cement & bricks; coping condensation-prep (£250, PAID 14 Aug via bank transfer, INV-0288). Luke's labour drawn from this pot attracts the 10% discount (extended 20 Jul) — note the condensation-prep item was paid by bank transfer, not cash, so discount doesn't apply there. See Contingency Drawdown sheet. NEW 29 Sep — named purpose #24: V4 materials for the expanded shed-area/fence-move decking scope, £5,322.74, PAID by phone. This single draw alone takes Contingency well over the £5,000 cap — flagged, not hidden, same treatment as the Rubbish removal pooled overage. NEW 3 Oct — named purposes #25–#30: six further TP invoices (£1,093.57). The £500 paid to TP on 11 Sep cleared #5 (£108.14), £247.01 of #6 and £144.85 of Luke's invoices for other jobs (not project spend — netted off in the agreed TP settlement). TP account SETTLED: £2,313.89 paid by card 5 Oct, Luke repaid £144.85 on 6 Oct (net £2,169.04). See TP Account tab. NEW 9 Oct — LG INV-0293 £1,850 (curves £800 = purpose #4; additional deck £1,050 = purpose #32), paid by bank transfer. PENDING, not yet drawn: additional lead work ~£200 (purpose #31, Luke's estimate 2 Oct, not started) — to come from Contingency once invoiced. Luke's further extended-deck labour is not yet agreed or logged. NEW 13 Oct — named purpose #33: Toolstation saw blades and drill bits £84.97 (bought by Luke on his card, repaid in cash 13 Oct). PENDING, not yet drawn: whole-house soft wash £1,200 cash (Gorgeous Cleaning Services, purpose #34, from Mon 19 Oct).
Chimney repair | LG Building and Roofing Ltd | 4700 | 4700.01 | 4700.01 | -0.01 | Quoted 2 Jun: £3,200 labour (invoiced full price, INV-0286) + £1,500 scaffold share. Cowl upgrade (£62.90) and TP account materials reclassified out 17 Aug — see Contingency and Materials (pooled) rows. This is now a clean quote-vs-actual labour figure.
Coping stones repair | LG Building and Roofing Ltd | 5310 | 5310 | 5310 | 0 | Quoted 3 Jun: £3,800 labour, confirmed 7 Aug as £3,610 blended (50% cash @10% disc. + 50% invoiced) + £1,700 scaffold share. Condensation-prep (£276.42) and TP account materials share (£277.29) reclassified out — see Contingency and Materials (pooled) rows. RISK: coping-stone damage on removal could substantially increase cost.
Materials (pooled) | Merchant trade accounts | 1130 | 1120.69 | 1120.69 | 9.31 | Pooled chimney (£480) + coping (£650) materials budget — decision 20 Jul. Purchased via merchant trade accounts (Dry Lining Supplies, Travis Perkins etc.), cleared on receipts. Detail on Materials Receipts sheet.
Rubbish removal (pooled skips) | Skip Hire Comparison Ltd / future providers | 1360 | 1460 | 1460 | -100 | Transferred 10 Aug from chimney/coping/decking rubbish-removal quotes (£80+£80+£1,200). Original skip (Skip Hire Comparison Ltd) cancelled 11 Aug, refunded — replaced same-day by Elmbridge Mini Skips (2 skips, £780 total, settled 12 Aug). Provisional — more skips expected, especially during decking. Detail on Skip Hire Log sheet. £40 Roofline works rubbish removal is expected but not yet incurred — not counted above; if incurred the pool would be £140 over.
Roofline works | LG Building and Roofing Ltd | 2100 | 1984.93 | 1984.93 | 115.07 | Own scope, own budget (estimate 4 Sep, £2,140 — unchanged; started 29 Sep, main works done the week of 5 Oct, remaining roofline works due Fri 16 Oct) — gutter replacement, fascia/soffit extension, slate replacement, barge board trim. Replaces the earlier 'gutters included in Luke's price' arrangement (back-gutter realignment and front gutters/tile repairs): on 4 Oct Gantt tasks 1.5, 1.7 and 3.2 were merged into one 'Roofline works' task (1.5). The estimate has no front-of-house gutters, and front tile repairs are covered by 'replace various broken slates'. Budget £2,100 = £1,600 labour (no VAT) + £150 scaffold tower + £350 materials; the £40 rubbish removal in the quote sits in the pooled Rubbish removal fund (not yet incurred). The tower was not needed (Luke used his own ladder) and that £150 benefit offsets the £40.40 of additional materials: net £109.60 under budget. LABOUR: INV-0291 £1,600 (2 Oct) confirmed correct and PAID 3 Oct by bank transfer, full price. MATERIALS: Graham SI19670857 £256.78 (£260 cash, paid 29 Sep); Graham SI19687572 £9.74 + TFP 0001458493 £78.01 (£90 cash) and TFP 0001458792 £40.40 (all paid in cash 2 Oct). This row shows £1,984.93 (invoices only); Cost Lines and Budget vs Actual use £1,990.40 actual, which includes £5.47 of coin top-ups. Additional lead work (~£200, Gantt task 1.5a, part of Gate 2) is outside this budget — see Contingency.
Core project (Luke's ~£56,800 outline) |  | 54828.99 | 53293.38 | 53293.38 | 1535.61
Chimney + coping incl. pooled materials |  | 11140 | 11130.7 | 11130.7 | 9.3
PROJECT TOTAL |  | 69428.99 | 56738.31 | 56738.31 | 1550.68
Contingency remaining: | -7664.39
Cost centre = which budget pays · Scope = what it was for (see Scope View tab) · 'Decking materials (V4)' = V4 orders only; Travis Perkins and other decking-related materials sit in Contingency.
Decking labour — quoted-value position (10% cash discount applied)
Quoted labour, stages 1–4 |  | 17600 |  |  |  | Luke's quote for the main decking labour.
Quoted value covered to date |  | 8844.4444 |  |  |  | Bank payments at face value; cash payments ÷ 0.9 because of the 10% cash discount (e.g. £2,000 cash covers £2,222.22 of quoted value).
Quoted value REMAINING |  | 8755.5556 |  |  |  | This is the figure to use. It matches Luke's own workings (£8,756). The 'Remaining' column above (£9,200) is a plain cash subtraction, and the older tracker view that showed £11,200 pre-dated the 18 Sep instalment.

## Budget vs Actual
Spinney External Works — Budget vs Actual
Snapshot as of 13 Oct 2026 (Week 12) — refresh narrative each batched update session; table figures pull from Summary sheet.
Snapshot
Week 12 — Contingency is well over cap: £12,664.39 drawn and paid against the £5,000 pot (£7,664.39 over). The main driver is the £5,322.74 V4 materials order for the expanded shed-area/fence-move decking scope (named purpose #24, paid by card 29 Sep). Since the last update, Luke's saw blades and drill bits (£84.97, bought on his card 6 Oct) were repaid in cash on 13 Oct. Nothing is invoiced but unpaid. Still to come from Contingency: the whole-house soft wash by Gorgeous Cleaning Services (£1,200 cash, from Mon 19 Oct), the ~£200 additional lead work and the V4 screw top-up #3 (£141.66). Chimney and coping are complete and settled. The main Roofline works were done the week of 5 Oct; the remaining roofline works are due Fri 16 Oct, ahead of the soft wash. Luke's team is working on the extended decking area.
• Chimney | COMPLETE (Gate 1, 18 Aug) — £0 variance, labour invoiced at the full quoted £3,200, no discount applied (non-cash terms).
• Coping | COMPLETE (Gate 1, 18 Aug) — £190 UNDER quote, half the labour was settled in cash at the agreed 10% discount, the other half invoiced at full price.
• Decking (labour + V4 materials) | Materials fully paid to the V4 proforma exactly (£32,228.99 — unchanged; the new £5,322.74 V4 order sits under Contingency, see below, not here). Labour: Stage 1 (£4,400) invoiced full price, plus two £2,000 cash instalments (4 Sep, 18 Sep, 10% discount each) — £8,844.44 quoted-value equivalent paid so far, £8,755.56 remaining across future stages.
• Scaffold (pooled, chimney + coping combined) | £0 variance — this was never split-quoted per workstream, just one £3,200 job (£2,000 paid on erection, £1,200 due on strike). Treating it as its own pooled line avoids implying a false per-workstream comparison.
• Materials (pooled, chimney + coping) | Back under the £1,130 cap — a £72.23 refund from Dry Lining Supplies (unused monocouche + other returned items) landed 19 Aug, more than offsetting the earlier £62.90 overage from pooling Luke's Travis Perkins account purchases.
• Rubbish removal (pooled, all 3 workstreams) | £1,460 spent against the £1,360 pool — £100 over. That is £780 for the two Elmbridge skips plus £680 for the old decking substructure wood collection, which was charged per trip and came in well above the £350 estimate. The skips and wood removal served chimney, coping and the soakaway/decking-prep groundworks, so the spend can't be attributed cleanly to one workstream. A further £40 for the Roofline works rubbish removal is expected but not yet incurred; if it is, the pool would be £140 over. Flagged, not hidden.
• Roofline works (new) | £1,600 labour + £150 scaffold tower + £350 materials = £2,100 budget (quote £2,140 unchanged; the £40 rubbish removal sits in the pooled fund). Started 29 Sep, main works done the week of 5 Oct; remaining roofline works due Fri 16 Oct. Labour INV-0291 (£1,600) paid 3 Oct by bank transfer. The tower was not needed — Luke used his ladder — and that £150 benefit offsets £40.40 of additional materials (four invoices, £390.40 cash, all reimbursed to Luke): net £109.60 under budget, actual £1,990.40. Additional lead work (~£200) will come from Contingency.
• Contingency | £12,664.39 drawn and PAID against the £5,000 pot — £7,664.39 OVER CAP. Main driver: £5,322.74 V4 materials order (purpose #24, paid 29 Sep). Travis Perkins invoices were settled 5 Oct, LG INV-0293 (£1,850) was paid 9 Oct and Luke's Toolstation saw blades and drill bits (£84.97, purpose #33) were repaid in cash 13 Oct. Flagged, not hidden. Pending, not yet drawn: whole-house soft wash £1,200 cash (purpose #34, from Mon 19 Oct), ~£200 additional lead work (purpose #31) and V4 screw top-up #3 (£141.66).
Budget vs Actual — detail
Cost centre | Quote / Budget £ | Actual £ | Variance £ | Note
Chimney (labour) | 3200 | 3200 | 0 | Invoiced full price (INV-0286) — non-cash, no discount
Coping (labour) | 3800 | 3610 | -190 | 50% cash @10% disc. + 50% invoiced — favourable
Decking (labour) | 17600 | 8400 | -9200 | Stage 1 (£4,400 invoiced) + two £2,000 cash instalments (4 Sep, 18 Sep, 10% discount each) — £8,844.44 quoted value retired, £8,755.56 remaining, mix of future cash/invoice TBC.
Decking materials (V4) | 32228.99 | 32228.99 | 0 | Proforma matched exactly, paid in full 9 Jul
Scaffold (pooled, chimney+coping) | 3200 | 3200 | 0 | Never split-quoted — one combined job. £2,000 paid, £1,200 due on strike
Materials (pooled, chimney+coping) | 1130 | 1120.69 | -9.31 | Back under the £1,130 cap after a £72.23 refund from Dry Lining Supplies (unused monocouche + other returned items) landed 19 Aug — was £62.92 over before the refund.
Rubbish removal (pooled, all 3 workstreams) | 1360 | 1460 | 100 | £100 OVER the £1,360 cap — the wood removal correction (£350 est. → £680 actual, charged per trip) pushed it over. Flagged, not hidden; cap left as-is per the same approach used for Materials pooled. Plus £40 expected (Roofline works rubbish removal, not yet incurred) — not counted above; if incurred the pool would be £140 over.
Roofline works (new, 4 Sep estimate) | 2100 | 1990.4 | -109.6 | Quote £2,140 (4 Sep) unchanged = £2,100 here + £40 rubbish removal in the pooled fund (not yet incurred). Started 29 Sep, main works done the week of 5 Oct; remaining roofline works due Fri 16 Oct. The £150 scaffold tower was not needed (Luke used his ladder) — that benefit offsets the £40.40 of additional materials (£390.40 cash vs £350 allowance), net £109.60 under. ACTUAL £1,990.40 = £1,600 labour (INV-0291, paid 3 Oct by bank transfer) + £390.40 materials (paid in cash). Additional lead work (~£200) sits in Contingency.
Contingency | 5000 | 12664.39 | 7664.39 | £12,664.39 drawn and PAID against the £5,000 pot, which is £7,664.39 over. Main driver: the £5,322.74 V4 materials order for the extended deck / shed area (named purpose #24, paid by phone 29 Sep), larger than the whole pot on its own. Travis Perkins settled 5 Oct; LG INV-0293 paid 9 Oct; Toolstation saw blades and drill bits (£84.97) repaid in cash 13 Oct. Still to come: £1,200 whole-house soft wash (cash, from Mon 19 Oct). See the Contingency explained tab. Flagged, not hidden — same treatment as the Rubbish removal overage.
TOTAL (as spent/committed to date) | 69618.99 | 67874.47 | -1744.52
Reconciliation check
Summary's PROJECT TOTAL uses each cost centre's committed/ceiling figure — for Chimney, Coping, and Decking that's the real actual; for Materials, Rubbish, and Contingency (all pooled/reserve buckets) it's the provisional cap, not what's been spent so far. Recomputed on that same basis below to confirm nothing here is missing or double-counted against Summary.
Chimney (actual) |  | 4700
Coping (actual) |  | 5310
Decking labour (actual) |  | 17600
Decking materials (actual) |  | 32228.99
Materials pooled (at £1,130 cap, per Summary) |  | 1130
Rubbish removal pooled (at £1,360 cap, per Summary) |  | 1360
Contingency (at £5,000 cap, per Summary) |  | 5000
Roofline works (actual, per estimate) |  | 2100
Recomputed total (Summary basis) |  | 69428.99
Summary PROJECT TOTAL (committed) |  | 69428.99
Difference — should be £0.00 |  | 0

## Contingency Explained
Contingency explained — why the £5,000 pot has been exceeded
As at 13 Oct 2026. Amounts inc VAT. Pulls live from the Contingency Drawdown, Summary and Cost Lines tabs. Scope tags on Travis Perkins invoices are inferred from invoice dates (confirm with Luke).
Short answer: Contingency has £12,664.39 drawn against a £5,000 pot — £7,664.39 over. About 64% of it is a new area of decking (the extended deck and shed base) that was not in the pot's original purposes.
1. The headline
Pot agreed 1 Jul | 5000 |  |  | Agreed for: fence move/repair labour, soakaway fix before decking (cancelled 1 Sep, nothing drawn), drainage by the garage (nothing drawn), additional curved-decking labour, cement and bricks.
Drawn (invoiced) | 12664.39 |  |  | Every Contingency invoice in the Invoice Register, paid or not.
of which paid | 12664.39
of which invoiced, not yet paid | 0 |  |  | Nothing outstanding: the Travis Perkins invoices were settled on 5 Oct and LG INV-0293 was paid on 9 Oct.
OVER THE POT BY | 7664.39
2. Where the money went
Driver | £ | Share | On the 1 Jul list? | What is in it
Extended deck & shed base | 8103.8 | 63.99% | No — arose later | The new decking area the fence move opened up, plus the shed base: V4 materials order, extra digging, extra frame and the first Travis Perkins blocks and cement for it. Also the £1,050 additional deck labour on LG INV-0293.
Main deck materials | 2760.44 | 21.8% | Partly — 'cement and bricks' | Travis Perkins bulk materials for the original decking (cement, ballast, sand, blocks, ply, small tools) plus V4 subframe screw top-ups. Luke's quote has materials paid directly, so they had to land somewhere. Also the £800 curved-deck labour on LG INV-0293.
Groundworks hire | 836.37 | 6.604% | No | Digger, dumper and clean-up. Used for both the main deck widening and the new shed area, so not split between them.
Fence relocation | 606.17 | 4.786% | Yes — fence move | Fence move labour (chimney side, boundary reclaim) and the fence materials.
Chimney & coping extras, shared items | 357.61 | 2.824% | No | Coping condensation-prep, chimney cowl upgrade, and one shared small-consumables invoice.
TOTAL DRAWN | 12664.39 | 100%
Check: total less Summary 'Invoiced' (must be 0.00) | 0
3. Inside the drivers
Line | £ |  | Purpose # | Source
V4 order — shed area / extended deck materials | 5322.74 |  | #24 | Placed and paid by phone 29 Sep (quote QUO-0031).
Extra digging — wider gate area + shed/additional deck | 1260 |  | #11 | Invoiced and paid 11 Sep.
Extra frame — wider deck gate area | 360 |  | #14 | Invoiced and paid 11 Sep.
Travis Perkins blocks and cement dated 21 Sep | 111.06 |  | #29, #30 | Two invoices, paid 5 Oct.
Extra deck labour — additional deck (LG INV-0293) | 1050 |  | #32 | Invoiced and paid 9 Oct (£1,050, bank transfer).
Extended deck & shed base — subtotal | 8103.8
Check against section 2 (must be 0.00) | 0
Travis Perkins bulk materials, main deck | 1592.15 |  | #16–#22, #25–#27 | Invoices dated before 21 Sep.
V4 subframe screw top-ups | 283.32 |  | #8, #9 | Two top-ups of 15 boxes.
Curved-decking labour (LG INV-0293) | 800 |  | #4 | Invoiced and paid 9 Oct (£800 of the £1,000 agreed 24 Sep).
Saw blades and drill bits (Toolstation) | 84.97 |  | #33 | Bought by Luke on his card 6 Oct; repaid in cash 13 Oct. Tagged Main deck, used throughout.
Digger hire | 378.58 |  | #10 | 3–8 Sep, on Luke's TP account.
Dumper hire | 277.79 |  | #28 | 2–8 Sep, on Luke's TP account.
Clean-up + small tree dig | 180 |  | #12 | Invoiced and paid 11 Sep.
Fence move labour | 315 |  | #13 | Chimney side / side (a) boundary. Paid 11 Sep.
Fence materials | 291.17 |  | #23 | Travis Perkins invoice 1051142985.
Check against section 2 (must be 0.00) | 0
4. Would the pot have held for what it was set up for?
Item | £ |  |  | Notes
Drawn on the 1 Jul purposes so far (fence + TP main-deck materials) | 2198.32 |  |  | Fence relocation plus 'cement and bricks'.
Plus: curved-decking labour (#4) — invoiced 9 Oct | 800 |  |  | Agreed 24 Sep at £1,000 full price / £900 cash; Luke invoiced £800 on INV-0293.
Total for the originally intended purposes | 2998.32
Pot | 5000
Headroom if only the original purposes had been drawn | 2001.68 |  |  | The pot would have held, with room to spare.
Everything else drawn (not on the 1 Jul list) | 9666.07 |  |  | New scope, hire, screw top-ups, chimney/coping extras and the additional deck labour (£1,050). Also Luke's saw blades and drill bits (£84.97).
5. How the pot was used up
Point in time | £ drawn | vs pot |  | Notes
Tracker view on 24 Sep (before the V4 order and the TP paper copies) | 4313.11 | Within |  | 86% of the pot — it looked on track.
On invoice dates, by 11 Sep | 5017.83 | Over |  | The pot was already used up by the extra digging, fence move and fence materials — before the V4 order, but not yet visible because Travis Perkins invoices were still being gathered.
After the V4 order, 29 Sep | 9635.85 | Over |  | The single biggest step.
After the TP paper copies were added, 3 Oct | 10729.42 | Over |  | Six more TP invoices (£1,093.57) added once Luke supplied the paper copies.
After INV-0293 (curves and additional deck), 9 Oct | 12579.42 | Over |  | The invoice for the extra curved and additional decking work (£1,850), paid 9 Oct. Travis Perkins was settled 5 Oct without changing the drawn figure.
After the Toolstation saw blades, 13 Oct | 12664.39 | Over |  | Luke's saw blades and drill bits (£84.97), repaid in cash 13 Oct.
6. Not yet in the figure
Item | £ |  | Status | Notes
Curved decking labour (#4) — resolved | 0 |  | Invoiced 9 Oct | Agreed £1,000; INV-0293 billed £800, so nothing pending. The other £200 is not expected unless Luke bills it later.
Additional lead work (#31, Gantt task 1.5a) | 200 |  | Estimate, not started | Part of Gate 2 — must finish before decking boards are laid.
V4 subframe screw top-up #3 (#15) | 141.66 |  | Payment unconfirmed | Logged in Cost Lines only.
Whole-house soft wash (#34, Gorgeous Cleaning Services) | 1200 |  | Booked, cash payable | £1,200 cash, from Contingency; starts Mon 19 Oct. Replaces the chimney + coping-only soft wash. Covers gutters, soffits, roof tiles, solar panels, render and windows.
Known pending | 1541.66
Luke's extended-deck labour still to come — low (3.5 days x £700) | 2450 |  | Not agreed or logged | From Luke's 2 Oct figures (2 people x 1 day = £700) and his 5–6 day estimate, less the 1.5 days now invoiced as the £1,050 additional deck on INV-0293. My arithmetic, not a quote. He suggested adding it to the remaining draw on the original deck labour.
Luke's extended-deck labour still to come — high (4.5 days x £700) | 3150 |  | Not agreed or logged | Same basis as above, at the top of his 5–6 day range.
Illustrative drawn if all of the above land in Contingency — low | 16656.05 |  |  | Depends on how Luke invoices the extended deck.
Illustrative drawn if all of the above land in Contingency — high | 17356.05
7. Scope added after the project began — and where each piece sits
Item | £ |  | Where it sits | Notes
Extended deck & shed base, and the fence relocation | 8709.97 |  | Contingency | Not on the 1 Jul list.
Roofline works — budget | 2100 |  | Own budget line (not Contingency) | The £2,140 quote (4 Sep) is £2,100 here plus £40 rubbish removal, which sits in the pooled skips fund.
Roofline works — invoiced and paid to date | 1984.93 |  | Own budget line | Labour INV-0291 plus four materials invoices.
Roofline works: the roofline works quote was also unseen at the start of the project. Although it now has its own budget line, it was not part of the original scope. It is kept out of Contingency, so it is not in the drawn figure above — but, like the extended deck, it is a later addition to the project.

## Contingency Drawdown
Contingency Drawdown — £5,000 pot (agreed Lara/Luke, 1 Jul 2026)
One row per named purpose (#1–#34), sorted by purpose number. Drawn and Paid come from the Invoice Register (matched on its 'Named purpose #' column); Pending comes from Cost Lines. Sort or filter freely: 'pot remaining' is worked out from the invoice dates, so it stays correct in any order. Travis Perkins invoices were settled on 5 Oct (net £2,169.04 after Luke's 6 Oct repayment — see TP Account).
Opening pot: | 5000 | Remaining: | -7664.39
Drawn: | 12664.39 | Paid: | 12664.39 | Pending: | 1541.66
|  | Check vs Register (must be 0.00): | 0
Named purpose # | Invoice date | Purpose | Supplier / detail | Drawn £ | Paid £ | Unpaid £ | Pending (not yet drawn) £ | Status | Scope | Pot remaining at this invoice date £ | Notes
1 |  | Fence move / repair labour | Luke (LG Building and Roofing) | 0 | 0 | 0 | 0 | Superseded by #13 | Fence relocation |  | On the 1 Jul list. Superseded by #13 (fence move, chimney side).
2 |  | Soakaway fix before decking | — | 0 | 0 | 0 | 0 | Cancelled 1 Sep |  |  | On the 1 Jul list. CANCELLED 1 Sep — cost-benefit not worth it. Nothing drawn.
3 |  | Drainage by the garage | — | 0 | 0 | 0 | 0 | Nothing drawn |  |  | On the 1 Jul list. Nothing drawn.
4 | 2026-10-09 | Additional curved-decking labour | Luke (LG Building and Roofing) | 800 | 800 | 0 | 0 | Paid | Main deck | -7664.39 | On the 1 Jul list. AGREED 24 Sep at £1,000 full price / £900 cash. INVOICED 9 Oct: £800 on INV-0293 (the curves), paid the same day by bank transfer — Luke billed £800, not the £1,000 agreed. The other £200 is not expected unless Luke bills it.
5 |  | Cement & bricks | — | 0 | 0 | 0 | 0 | Covered by #16–#30 |  |  | On the 1 Jul list. Actual draws are recorded under the specific Travis Perkins purposes #16–#30.
6 | 2026-08-13 | Coping condensation-prep (labour + DPC roll) | LG Building and Roofing Ltd — INV-0288; LG Building and Roofing Ltd (Travis Perkins account) — TP invoice 1048887075 | 276.42 | 276.42 | 0 | 0 | Paid | Chimney & coping | 4552.54 | Labour £250 (INV-0288, 14 Aug) + Damplas DPC roll £26.42 (17 Aug).
7 | 2026-08-10 | Chimney cowl upgrade — stainless steel | StoveWorldUK — Order #147399 | 62.9 | 62.9 | 0 | 0 | Paid | Chimney & coping | 4937.1
8 | 2026-08-24 | V4 subframe screw top-up | V4 Wood Flooring Ltd — V4FQ-17702 | 141.66 | 141.66 | 0 | 0 | Paid | Main deck | 3359.68 | 15 boxes of structural subframe screws.
9 | 2026-09-10 | V4 subframe screw top-up #2 | V4 Wood Flooring Ltd — TBC | 141.66 | 141.66 | 0 | 0 | Paid | Main deck | 2406.63 | 15 boxes of structural subframe screws. Paid 10 Sep.
10 | 2026-09-09 | Digger hire | Travis Perkins Hire (Luke's account) — 1051011143 | 378.58 | 378.58 | 0 | 0 | Paid | Groundworks (digger & dumper) | 2673.02 | 3–8 Sep, Travis Perkins Hire. Actual invoice £378.58 replaced the £530 estimate; no barrow loader charge appears on the invoice (flagged, not assumed).
11 | 2026-09-11 | Extra digging — wider gate area + shed/additional deck | LG Building and Roofing Ltd (cash) | 1260 | 1260 | 0 | 0 | Paid | Extended deck & shed base | -17.83 | Part of Luke's 11 Sep extras invoice (£2,350 quoted, £2,115 paid after the 10% cash discount).
12 | 2026-09-11 | Clean-up + small tree dig | LG Building and Roofing Ltd (cash) | 180 | 180 | 0 | 0 | Paid | Groundworks (digger & dumper) | -17.83 | Part of Luke's 11 Sep extras invoice.
13 | 2026-09-11 | Fence move — chimney side / side (a) boundary reclaim | LG Building and Roofing Ltd (cash) | 315 | 315 | 0 | 0 | Paid | Fence relocation | -17.83 | Part of Luke's 11 Sep extras invoice. Supersedes #1.
14 | 2026-09-11 | Extra frame — wider deck gate area | LG Building and Roofing Ltd (cash) | 360 | 360 | 0 | 0 | Paid | Extended deck & shed base | -17.83 | Part of Luke's 11 Sep extras invoice.
15 |  | V4 subframe screw top-up #3 | V4 Wood Flooring Ltd | 0 | 0 | 0 | 141.66 | Not yet invoiced | Main deck |  | 15 boxes. Invoice due 18 Sep, payment unconfirmed — logged in Cost Lines only until confirmed.
16 | 2026-08-18 | TP materials — cement, blade | Travis Perkins (Luke's account) — 1049651867 | 144.58 | 144.58 | 0 | 0 | Paid | Main deck | 4060.84 | Travis Perkins invoice 1049651867.
17 | 2026-08-19 | TP materials — plywood, drill bit, screws, gloves | Travis Perkins (Luke's account) — 1049757851 | 74.34 | 74.34 | 0 | 0 | Paid | Main deck | 3986.5 | Travis Perkins invoice 1049757851.
18 | 2026-08-20 | TP materials — ballast, cement, blocks, pallet deposit | Travis Perkins (Luke's account) — 1049844268 | 462.5 | 462.5 | 0 | 0 | Paid | Main deck | 3501.34 | Travis Perkins invoice 1049844268. Includes a £30.30 REFUNDABLE pallet deposit (not a final cost).
19 | 2026-08-20 | TP materials — flat packers | Travis Perkins (Luke's account) — 1049844267 | 22.66 | 22.66 | 0 | 0 | Paid | Main deck | 3501.34 | Travis Perkins invoice 1049844267.
20 | 2026-09-08 | TP materials — plywood, line marker | Travis Perkins (Luke's account) — 1050903283 | 58.62 | 58.62 | 0 | 0 | Paid | Main deck | 3051.6 | Travis Perkins invoice 1050903283.
21 | 2026-09-10 | TP materials — ballast, cement | Travis Perkins (Luke's account) — 1051072869 | 124.73 | 124.73 | 0 | 0 | Paid | Main deck | 2406.63 | Travis Perkins invoice 1051072869.
22 | 2026-09-11 | TP materials — gloves, woodscrews | Travis Perkins (Luke's account) — 1051162218 | 18.29 | 18.29 | 0 | 0 | Paid | Shared / site-wide | -17.83 | Travis Perkins invoice 1051162218.
23 | 2026-09-11 | TP fence materials — posts, Postcrete, rail brackets, pegs, timber | Travis Perkins (Luke's account) — 1051142985 | 291.17 | 291.17 | 0 | 0 | Paid | Fence relocation | -17.83 | Travis Perkins invoice 1051142985.
24 | 2026-09-29 | V4 materials — shed area / extended deck | V4 Wood Flooring Ltd — QUO-0031 | 5322.74 | 5322.74 | 0 | 0 | Paid | Extended deck & shed base | -5729.42 | Quote QUO-0031, placed and paid by phone 29 Sep. On its own larger than the whole pot.
25 | 2026-08-11 | TP materials — sand, white cement, Bosch blade | Travis Perkins (Luke's account) — 1049231418 | 108.14 | 108.14 | 0 | 0 | Paid | Main deck | 4828.96 | Travis Perkins invoice 1049231418. Paid from the £500 TP receipt of 11 Sep.
26 | 2026-08-17 | TP materials — ballast, building sand, 72 blocks | Travis Perkins (Luke's account) — 1049595624 | 347.12 | 347.12 | 0 | 0 | Paid | Main deck | 4205.42 | Travis Perkins invoice 1049595624. £247.01 paid from the £500 receipt; £100.11 balance paid by card 5 Oct.
27 | 2026-09-03 | TP materials — ballast x2, Mastercrete x10 | Travis Perkins (Luke's account) — 1050655200 | 249.46 | 249.46 | 0 | 0 | Paid | Main deck | 3110.22 | Travis Perkins invoice 1050655200.
28 | 2026-09-14 | TP plant hire — tracked dumper | Travis Perkins Hire (Luke's account) — 1051287675 | 277.79 | 277.79 | 0 | 0 | Paid | Groundworks (digger & dumper) | -295.62 | 2–8 Sep, Travis Perkins invoice 1051287675.
29 | 2026-09-21 | TP materials — blocks, cement, mallet, line marker | Travis Perkins (Luke's account) — 1051688095 | 60.3 | 60.3 | 0 | 0 | Paid | Extended deck & shed base | -406.68 | Travis Perkins invoice 1051688095.
30 | 2026-09-21 | TP materials — 20 blocks | Travis Perkins (Luke's account) — 1051708772 | 50.76 | 50.76 | 0 | 0 | Paid | Extended deck & shed base | -406.68 | Travis Perkins invoice 1051708772.
31 |  | Additional lead work — back-of-house gutters | Luke (LG Building and Roofing) | 0 | 0 | 0 | 200 | Not yet invoiced | Roofline |  | Gantt task 1.5a, part of Gate 2. Chase lead into the walls so the gutters work properly. Luke's estimate about £200 (2 Oct), not started.
32 | 2026-10-09 | Additional deck labour — extended deck & shed base | Luke (LG Building and Roofing) — INV-0293 | 1050 | 1050 | 0 | 0 | Paid | Extended deck & shed base | -7664.39 | Part of LG INV-0293 (£1,850, 9 Oct): the £1,050 for the additional deck. The other £800 is the curves (#4). Paid 9 Oct by bank transfer. Separate from the £17,600 main decking labour draws.
33 | 2026-10-06 | Saw blades and drill bits — Toolstation | Toolstation Ltd — YAC545477716 (bought by Luke) | 84.97 | 84.97 | 0 | 0 | Paid | Main deck | -5814.39 | Freud mitre saw blade, ROKTOR drill bits, DeWalt circular saw blade (£84.97). Luke paid by card 6 Oct; repaid in cash 13 Oct. Scope Main deck, although the tools will be used throughout the project.
34 |  | Whole-house soft wash — Gorgeous Cleaning Services | Gorgeous Cleaning Services | 0 | 0 | 0 | 1200 | Not yet invoiced | Shared / site-wide |  | £1,200 cash, from Contingency. Gutters, soffits, roof tiles, roof solar panels, render, windows etc. Starts Mon 19 Oct; all roofline works must be done first. Replaces the chimney + coping-only soft wash. Pending until paid.

## Scope View
Scope View — what the money was for
Cost centre = which budget pays; Scope = what it was for. Source: the Scope column on the Invoice Register. Amounts invoiced, inc VAT. Scope tags on Travis Perkins invoices are INFERRED: Luke's 2 Oct update says only 1 day (2 people) has been spent on the extended deck so far, so only TP invoices from 21 Sep are treated as extended; earlier ones are main deck. Digger/dumper hire served both and is not split. Confirm with Luke. LG INV-0293 (9 Oct) is split: £800 curves (Main deck) and £1,050 additional deck (Extended deck & shed base). Toolstation saw blades (13 Oct, £84.97) are tagged Main deck although used throughout.
A. Invoiced by scope and cost centre
Scope | Decking materials (V4) | Decking labour | Contingency | Roofline works | Chimney repair | Coping stones repair | Materials (pooled) | Rubbish removal (pooled skips) | Total invoiced £ | Total paid £ | Unpaid £
Main deck | 32228.99 | 8400 | 2760.44 | 0 | 0 | 0 | 0 | 680 | 44069.43 | 44069.43 | 0
Extended deck & shed base | 0 | 0 | 8103.8 | 0 | 0 | 0 | 0 | 0 | 8103.8 | 8103.8 | 0
Fence relocation | 0 | 0 | 606.17 | 0 | 0 | 0 | 0 | 0 | 606.17 | 606.17 | 0
Groundworks (digger & dumper) | 0 | 0 | 836.37 | 0 | 0 | 0 | 0 | 0 | 836.37 | 836.37 | 0
Roofline | 0 | 0 | 0 | 1984.93 | 0 | 0 | 0 | 0 | 1984.93 | 1984.93 | 0
Chimney & coping | 0 | 0 | 339.32 | 0 | 4700.01 | 5310 | 1120.69 | 0 | 11470.02 | 11470.02 | 0
Shared / site-wide | 0 | 0 | 18.29 | 0 | 0 | 0 | 0 | 780 | 798.29 | 798.29 | 0
TOTAL | 32228.99 | 8400 | 12664.39 | 1984.93 | 4700.01 | 5310 | 1120.69 | 1460 | 67869.01 | 67869.01 | 0
Summary 'Invoiced £' (same cost centre) | 32228.99 | 8400 | 12664.39 | 1984.93 | 4700.01 | 5310 | 1120.69 | 1460 | 67869.01
Check: difference (must be 0.00) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Headlines
Main deck — invoiced to date | 44069.43 | Original V4 order, decking labour, V4 screw top-ups, TP materials invoiced before 21 Sep, old-deck waste removal.
Extended deck & shed base + Fence relocation — invoiced | 8709.97 | New area enabled by the fence move: V4 order #24, extra digging/frame labour, TP materials from 21 Sep, fence materials and labour.
Groundworks — shared by both projects | 836.37 | Digger and dumper hire, clean-up and small tree dig — used for the main deck widening and the new shed area, not split.
Shared / site-wide (skips, small consumables) | 798.29 | Pooled skip hire and consumables that cannot be split between projects.
C. Contingency by scope — Register vs Contingency Drawdown
Scope | Invoice Register £ | Drawdown sheet £ | Difference £
Main deck | 2760.44 | 2760.44 | 0
Extended deck & shed base | 8103.8 | 8103.8 | 0
Fence relocation | 606.17 | 606.17 | 0
Groundworks (digger & dumper) | 836.37 | 836.37 | 0
Roofline | 0 | 0 | 0
Chimney & coping | 339.32 | 339.32 | 0
Shared / site-wide | 18.29 | 18.29 | 0
TOTAL | 12664.39 | 12664.39 | 0
Check: Register total vs Summary Contingency 'Invoiced £' (must be 0.00) | 0
D. Travis Perkins spend by scope (from TP Line Items)
Scope | TP spend £ | Share of TP spend
Main deck | 1592.15 | 49.49%
Extended deck & shed base | 111.06 | 3.452%
Fence relocation | 291.17 | 9.051%
Groundworks (digger & dumper) | 656.37 | 20.4%
Roofline | 0 | 0%
Chimney & coping | 547.88 | 17.03%
Shared / site-wide | 18.29 | 0.5686%
TOTAL | 3216.92 | 100%
Check: TP Account total invoiced less this total (must be 0.00) | 0
E. Pending — not yet invoiced (logged in Cost Lines only)
Item | Scope | Cost centre | Amount £ | Status
Additional curved-decking labour (purpose #4) | Main deck | Contingency | 0 | Invoiced 9 Oct (INV-0293, £800) and paid — no longer pending. £1,000 was agreed on 24 Sep; the other £200 is not expected unless Luke bills it.
Additional lead work (purpose #31) | Roofline | Contingency | 200 | Luke's estimate 2 Oct; not started.
Whole-house soft wash (purpose #34) | Shared / site-wide | Contingency | 1200 | Gorgeous Cleaning Services, £1,200 cash; starts Mon 19 Oct. Not yet paid.
TOTAL pending |  |  | 1400 | Luke's remaining extended-deck labour (about 3.5–4.5 days still to come, roughly £2,450–£3,150 on my arithmetic) is NOT logged until agreed.

## Invoicing Schedule
Invoicing Schedule — expected invoice events
Terms: 10% labour discount on all Luke phases except decking labour and scaffolding. Chimney & coping settle as SINGLE CASH PAYMENTS on phase completion (agreed Lara/Ryan 20 Jul; TBC with Luke 21 Jul). Log every payment on the Invoice Register — this sheet is expectations, the Register is the record.
# | Cost centre | Trigger event | Payee | Basis | Est. £ | Status | Notes
1 | Decking materials (V4) | Order placed — PAID IN FULL 9 Jul | V4 Wood Flooring Ltd | Invoice V4FQ-15584 | 32228.99 | Paid
2 | Chimney + Coping (scaffold) | Erection complete (17–18 Jul) — PAID | Scaffolder (via Trevor) | £2,000 cash (of £3,200 combined) | 2000 | Paid | Logged in Register: £937.50 chimney + £1,062.50 coping
3 | Chimney + Coping (scaffold) | Strike, after Gate 1 sign-off | Scaffolder (via Trevor) | £1,200 cash balance on strike | 1200 | Agreed | Log in Register: £562.50 chimney + £637.50 coping
4 | Chimney repair | INVOICED & PAID 24 Jul (non-cash) | LG Building and Roofing Ltd | £3,200 labour less £111.70 prepaid = £3,088.30. Full price — no discount. | 3200 | Paid | £3,200 labour invoiced & paid 24 Jul (£3,088.30 after £111.70 prepayment deduction). Rubbish removal (£80) transferred 10 Aug to pooled skip fund — no longer owed to Luke.
5 | Coping stones repair | 50% CASH — PAID 7 Aug | LG Building and Roofing Ltd | 50% of base labour (£1,710.00), 10% cash discount. Based on original £3,800 quote only. | 1710 | Paid | Excludes condensation-prep addition — price not yet finalised (see separate row).
6 | Coping stones repair | 50% INVOICED — due next week | LG Building and Roofing Ltd | 50% of base labour (£1,900.00) full price. Rubbish removal transferred to pooled skip fund 10 Aug. | 1900 | Paid 14 Aug | INVOICED 13 Aug as part of Luke's INV-0288 (£2,150 total, due 14 Aug) — that invoice also includes the £250 condensation-prep item, now tracked separately under Contingency. No longer includes rubbish removal — see Rubbish removal (pooled skips) row.
7 | Contingency | Additional scope — condensation-escape prep (price TBC) | LG Building and Roofing Ltd | Combined labour + materials, Luke's estimate — price NOT yet finalised | 0 | Paid 14 Aug | RECLASSIFIED: priced at £250, invoiced as part of Luke's INV-0288 (£2,150 total, 13 Aug), paid 14 Aug via bank transfer. Tracked as Contingency named purpose #6 — Est.£ shown as £0 here since it's a draw FROM the £5,000 pot (row 14), not additional money on top of it.
8 | Decking labour | Stage 1 (25%, INV-0289) PAID 20 Aug — 4 stages confirmed, flat 25% each | LG Building and Roofing Ltd | £17,600 labour total across stages, at quoted rates. CORRECTED 4 Sep: cash payments DO get the 10% discount (same as chimney/coping) — only invoiced stages are full price. Rubbish removal transferred to pooled skip fund. | 17600 | Stage 1 paid, 25% down | Stage 1 (£4,400) invoiced/paid 20 Aug, full price. Two cash instalments since (£2,000 each, 4 Sep + 18 Sep), 10% discount applies to both. £8,400 paid to date, £8,844.44 quoted value retired, £8,755.56 remaining. Exact milestone triggers for further stages still TBC.
9 | Materials (pooled) | Periodic — on receipts | Merchant trade accounts (Dry Lining Supplies, TP etc.) | Pooled £1,130 budget (chimney £480 + coping £650) | 1130 | Agreed in principle | Log each receipt in Register + Materials Receipts sheet
10 | Contingency | Rainy-day tasks 100% on completion; named extras as incurred | LG Building / merchants | £5,000 pot — fence labour, soakaway fix, garage drainage, curved-deck extras, cement & bricks. Labour at 10% discount | 5000 | Approved 20 Jul — first draw 14 Aug | Curved-decking extra labour discount TBC. First draw: coping condensation-prep (£250, named purpose #6), paid 14 Aug via bank transfer, INV-0288. The £5,000 pot has since been exceeded — see the Contingency Drawdown sheet. Each drawdown also on Contingency Drawdown sheet.
11 | Contingency | Additional material — stainless steel cowl | StoveWorldUK (paid direct, project account) | Order #147399, 10 Aug 2026 | 0 | Paid | 5" stainless steel chimney pot hanger cowl — replaces original spec (decision logged 7 Aug), prevents rusting. Contingency named purpose #7 — Est.£ shown as £0 here since it's a draw FROM the £5,000 pot (row 14), not additional money on top of it. Actually paid: £62.90 (see Invoice Register).
11 | Rubbish removal (pooled skips) | Periodic — as skips are needed | Skip Hire Comparison Ltd / future providers | Provisional £1,360 (transferred from chimney/coping/decking rubbish quotes) | 1360 | Approved 10 Aug | First skip £344.16 paid 10 Aug, delivery 11 Aug. More skips expected during decking — budget is provisional, watch like the materials pool. Log each skip in Register + Skip Hire Log sheet.
9 | Roofline works | New scope, own budget — estimate 4 Sep; started 29 Sep, main works done week of 5 Oct; remainder due Fri 16 Oct | LG Building and Roofing Ltd | £1,600 labour (no VAT) + £150 scaffold tower + £350 materials = £2,100 (the £2,140 quote less £40 rubbish removal, reclassified to the pooled Rubbish removal fund and not yet incurred). Tower not needed (Luke used his ladder) — the £150 benefit offsets £40.40 of additional materials. | 2100 | In progress — main works done w/c 5 Oct; remainder due Fri 16 Oct | Supersedes the earlier 'gutters included in Luke's price' understanding (old Gantt tasks 1.5 and 3.2, merged into task 1.5 on 4 Oct). The estimate has no front-of-house gutters; front tile repairs are covered by 'replace various broken slates'.
12 | Contingency | Named purpose #24 — V4 materials, expanded shed-area/fence-move decking scope | V4 Wood Flooring Ltd | Quote #QUO-0031, actioned + paid by phone 29 Sep | 0 | Paid | £5,322.74 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it, same convention as the other named-purpose rows. This single draw alone exceeds the pot; see Contingency Drawdown sheet and Summary for the resulting negative remaining balance.
13 | Contingency | Named purpose #25 — TP invoice 1049231418 | Travis Perkins (Luke's account) | Invoice 1049231418 (11 Aug) | 0 | Paid | £108.14 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Paid 11 Sep from the £500 TP receipt.
14 | Contingency | Named purpose #26 — TP invoice 1049595624 | Travis Perkins (Luke's account) | Invoice 1049595624 (17 Aug) | 0 | Paid | £347.12 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. £247.01 paid 11 Sep; £100.11 balance paid by card 5 Oct.
15 | Contingency | Named purpose #27 — TP invoice 1050655200 | Travis Perkins (Luke's account) | Invoice 1050655200 (3 Sep) | 0 | Paid | £249.46 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Paid by card 5 Oct (TP settlement).
16 | Contingency | Named purpose #28 — TP invoice 1051287675 | Travis Perkins (Luke's account) | Invoice 1051287675 (14 Sep) | 0 | Paid | £277.79 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Tracked dumper hire. Paid by card 5 Oct (TP settlement).
17 | Contingency | Named purpose #29 — TP invoice 1051688095 | Travis Perkins (Luke's account) | Invoice 1051688095 (21 Sep) | 0 | Paid | £60.30 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Paid by card 5 Oct (TP settlement).
18 | Contingency | Named purpose #30 — TP invoice 1051708772 | Travis Perkins (Luke's account) | Invoice 1051708772 (21 Sep) | 0 | Paid | £50.76 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Paid by card 5 Oct (TP settlement).
19 | Contingency | Named purpose #4 — curved-decking labour (INV-0293) | LG Building and Roofing Ltd | INV-0293, issued 9 Oct | 0 | Paid | £800 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Part of LG INV-0293 (£1,850); paid 9 Oct by bank transfer. The £1,000 agreed on 24 Sep was billed as £800.
20 | Contingency | Named purpose #32 — additional deck labour (extended deck & shed base) | LG Building and Roofing Ltd | INV-0293, issued 9 Oct | 0 | Paid | £1,050 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Part of LG INV-0293 (£1,850); paid 9 Oct by bank transfer.
21 | Contingency | Named purpose #33 — Toolstation saw blades and drill bits | Luke (card) | Toolstation order YAC545477716, 6 Oct | 0 | Paid | £84.97 actual — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Bought by Luke on his card 6 Oct; repaid in cash 13 Oct.
22 | Contingency | Named purpose #34 — whole-house soft wash (pending) | Gorgeous Cleaning Services | Gorgeous Cleaning Services, from Mon 19 Oct | 0 | Booked, cash | £1,200 cash expected — a draw FROM the £5,000 pot (row 14), not additional money on top of it. Not yet paid; logged in Cost Lines until paid.
|  |  |  | Schedule Total: | 69428.99
|  |  |  | Summary tab committed total: | 69428.99
|  |  |  | Difference (must be £0.00): | 0

## Invoice Register
Invoice & Payment Register — add a row per invoice received
Yellow cells are inputs. Cost centre must match the Summary sheet names exactly (dropdown-free by design — copy from row 5). Paid date empty = outstanding.
Invoice date | Cost centre | Supplier | Reference | Description | Amount £ (gross) | Paid date | Method | Notes | Scope | Scope basis | Named purpose #
2026-07-09 | Decking materials (V4) | V4 Wood Flooring Ltd | V4FQ-15584 | Millboard Ashwood decking + Plas-Pro subframe, fixings (144.9 m²) | 32228.99 | 2026-07-09 | Amex | Paid in full at order | Main deck | Quote: original V4 order.
2026-07-20 | Materials (pooled) | Dry Lining Supplies Ltd | RECB000NNIVB49XWEXOG | Render materials (shared chimney+coping): mesh, Weberend Aid ×6, beads, SBR, rubble sacks | 311.98 | 2026-07-20 | Pay By Link | Project-materials share of £423.69 receipt | Chimney & coping | Cost centre (chimney/coping pools).
2026-07-20 | Chimney repair | Dry Lining Supplies Ltd | RECB000NNIVB49XWEXOG | Folding work platform 600mm — Luke's equipment, non-project | 111.71 | 2026-07-20 | Pay By Link | PREPAYMENT vs chimney phase-start invoice: pay £1,528.29 of the £1,640 when it lands | Chimney & coping | Cost centre (chimney/coping pools).
2026-07-20 | Chimney repair | Scaffolder (via Trevor) | Cash | Scaffold erection payment — chimney share (pro-rata of £2,000 cash) | 937.5 | 2026-07-20 | Cash | £2,000 paid following erection 17–18 Jul; amend date cell if payment day differed | Chimney & coping | Cost centre (chimney/coping pools).
2026-07-24 | Chimney repair | LG Building and Roofing Ltd | INV-0286 | Chimney labour, invoiced (£3,200 less £111.70 work-platform prepayment). Rubbish removal £80 NOT included — outstanding. | 3088.3 | 2026-07-24 | Bank transfer | Invoiced (non-cash) — full price, no 10% discount. £80 rubbish removal still outstanding. | Chimney & coping | Cost centre (chimney/coping pools).
2026-07-22 | Materials (pooled) | Dry Lining Supplies | 914751798 | Weber Pral M Silver Pearl x10, Plastic 15mm Stop Bead 3m x3 (shared render finish) | 162.96 | 2026-07-22 | Pay By Link | Second pooled-materials trip | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-04 | Materials (pooled) | Dry Lining Supplies Ltd | RECB000NNIVB6DIPDFCW | Weberend Ocr x3, Weber Pral M Silver Pearl x4, Stop Bead x6, Drip Bead x2, Sikabond SBR x1 (coping render) | 148.53 | 2026-08-04 | Pay By Link | Coping stones render materials. Receipt received 4 Aug (till David, 07:31). | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-07 | Coping stones repair | LG Building and Roofing Ltd | Cash | Coping 50% cash labour payment (base labour only, 10% discount). Condensation-prep addition NOT included — price not yet finalised. | 1710 | 2026-08-07 | Cash | Confirmed 7 Aug: 50% cash / 50% invoice split on original £3,800 quote. Remainder £1,980.00 (incl. rubbish) to be invoiced next week. £250 addition separate, price TBC. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-10 | Contingency | StoveWorldUK | Order #147399 | 5" Stainless Steel Chimney Pot Hanger Cowl — replaces original spec | 62.9 | 2026-08-10 | Card (Ryan, project account) | Named purpose #7 (chimney cowl upgrade). RECLASSIFIED 17 Aug from Chimney repair — genuine scope addition beyond original quote. | Chimney & coping | Item: chimney cowl (purpose #7). | 7
2026-08-10 | Rubbish removal (pooled skips) | Skip Hire Comparison Ltd | D81F29CE-0002 | 8 cubic yard skip, delivery 11 Aug | 344.16 | 2026-08-10 | Card (Ryan, project account) | First skip. Replaces chimney/coping/decking rubbish-removal quotes — transferred to this pooled fund 10 Aug. CANCELLED 11 Aug — original supplier delayed delivery; refunded in full (receipt 3362-9782), see row below. | Shared / site-wide | Pooled skip hire serves all work.
2026-08-11 | Rubbish removal (pooled skips) | Skip Hire Comparison Ltd | Refund 3362-9782 (orig. inv. D81F29CE-0002) | Refund — original skip cancelled after supplier delivery delay | -344.16 | 2026-08-13 | — | Refund confirmed received 13 Aug 2026 — cleared in 2 working days, faster than the 5-10 day estimate. | Shared / site-wide | Pooled skip hire serves all work.
2026-08-11 | Rubbish removal (pooled skips) | Elmbridge Mini Skips | INV-11373 / ref 25996 | 8 cubic yard skip — delivery, replaces cancelled Skip Hire Comparison booking | 390 | 2026-08-12 | TBC | Settled 12 Aug 2026. Skip delivered filled 11 Aug; collected and swapped for empty 12 Aug. | Shared / site-wide | Pooled skip hire serves all work.
2026-08-12 | Rubbish removal (pooled skips) | Elmbridge Mini Skips | INV-11375 / ref 26030 | 8 cubic yard skip — exchange (collects filled skip, delivers empty) | 390 | 2026-08-12 | TBC | Settled 12 Aug 2026. | Shared / site-wide | Pooled skip hire serves all work.
2026-08-13 | Coping stones repair | LG Building and Roofing Ltd | INV-0288 | 50% invoiced balance — coping base labour | 1900 | 2026-08-14 | Bank transfer | Paid as part of INV-0288 (£2,150 total, also includes the £250 condensation-prep item — see Contingency row below). | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-13 | Contingency | LG Building and Roofing Ltd | INV-0288 | Named purpose #6 — coping condensation-escape prep (re-bed 3 bricks, fibreglass mesh, 4 weep holes) | 250 | 2026-08-14 | Bank transfer | Reclassified from Coping 13 Aug. Terms were originally agreed as 100% cash — confirmed 14 Aug this is instead paid via bank transfer as part of INV-0288, bundled with the £1,900 coping balance. | Chimney & coping | Item: coping condensation-prep (purpose #6). | 6
2026-08-16 | Materials (pooled) | SoftWash UK | Order F4UJ62VLQ | Render Cleaner Gel X Pro, 5 Litres | 47.99 | 2026-08-16 | Card (Mastercard ...4597) | Paid at checkout, order confirmed 16 Aug. Also logged on Materials Receipts sheet — pool detail. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-17 | Materials (pooled) | LG Building and Roofing Ltd (Travis Perkins account) | TP invoices 1047678330 / 1047972816 / 1048887075 | Render/masonry consumables + lead flashing — pooled, not split by workstream | 481.28 | 2026-08-18 | Bank transfer | PAID 18 Aug, confirmed as part of the full £547.88 TP account settlement (all 4 invoices). £0.02 rounding absorbed here so the three allocations reconcile exactly to the confirmed total. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-19 | Materials (pooled) | Dry Lining Supplies Ltd | Refund against 4 Aug order | Refund — 5 bags unused monocouche + other returned items, against original £148.53 order | -72.23 | 2026-08-19 | Bank transfer | Refund confirmed received 19 Aug — £72.23, slightly more than the £63.10 estimate (5 bags x £12.62), likely covered a few additional returned items beyond the monocouche. Actual figure used, not the estimate. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-17 | Contingency | LG Building and Roofing Ltd (Travis Perkins account) | TP invoice 1048887075 | Damplas DPC roll — coping condensation-prep material (named purpose #6) | 26.42 | 2026-08-18 | Bank transfer | PAID 18 Aug, part of the full £547.88 TP account settlement. Adds to the existing purpose #6 draw (£250 labour) — total now £276.42. | Chimney & coping | Item: coping DPC roll (purpose #6). | 6
2026-08-10 | Materials (pooled) | LG Building and Roofing Ltd (Travis Perkins account) | TP invoice 1049120278 | Cleaning/finishing consumables — pooled, not split by workstream | 40.18 | 2026-08-18 | Bank transfer | PAID 18 Aug, part of the full £547.88 TP account settlement. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-18 | Decking labour | LG Building and Roofing Ltd | INV-0289 | Decking labour — stage 1 (25% of £17,600 quoted labour) | 4400 | 2026-08-20 | Bank transfer | First stage payment — resolves the earlier open question about 4-5 stage triggers: appears to be a flat 25% per stage. 3 stages remaining (£13,200). | Main deck | Cost centre: decking labour.
2026-07-20 | Coping stones repair | Scaffolder (via Trevor) | Cash | Scaffold erection payment — coping share (pro-rata of £2,000 cash). CAUGHT 18 Aug: paid at the time, only now logged in the Register. | 1062.5 | 2026-07-20 | Cash | Matches chimney's already-logged share (row 8) — total £2,000 split £1,500/£1,700 chimney/coping ratio. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-18 | Chimney repair | Scaffolder (via Trevor) | — | Scaffold final balance — chimney share (pro-rata of £1,200) | 562.5 | 2026-08-18 | TBC | Scaffold strike complete 18 Aug, final balance paid. Full £3,200 now settled: £1,500 chimney + £1,700 coping. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-18 | Coping stones repair | Scaffolder (via Trevor) | — | Scaffold final balance — coping share (pro-rata of £1,200) | 637.5 | 2026-08-18 | TBC | Scaffold strike complete 18 Aug, final balance paid. | Chimney & coping | Cost centre (chimney/coping pools).
2026-08-24 | Contingency | V4 Wood Flooring Ltd | V4FQ-17702 | V4 screw top-up — 15 boxes structural subframe screws (named purpose #8) | 141.66 | 2026-08-24 | Bank transfer | Requested by Luke 20 Aug, ordered and paid 24 Aug. | Main deck | Item: structural subframe screws (V4 top-up #1). | 8
2026-09-04 | Decking labour | LG Building and Roofing Ltd | Cash | Decking labour — cash instalment (10% discount applies) | 2000 | 2026-09-04 | Cash | Retires £2,222.22 of quoted value at the 10% cash discount (£2,000 paid = 90%). Not a full 25% stage — partial/interim payment. Total paid to date: £6,400 (Stage 1 £4,400 invoiced + this £2,000 cash). Quoted value remaining: £10,977.78. | Main deck | Cost centre: decking labour.
2026-09-10 | Contingency | V4 Wood Flooring Ltd | TBC (no invoice number given) | V4 screw top-up #2 — 15 boxes structural subframe screws (named purpose #9) | 141.66 | 2026-09-10 | TBC | Invoice received and paid 10 Sep, delivery scheduled 11 Sep. Amount inferred from purpose #8's confirmed rate — no invoice number/exact figure given; flag if actual differs. | Main deck | Item: structural subframe screws (V4 top-up #2). | 9
2026-09-11 | Rubbish removal (pooled skips) | TBC | N/A (cash) | Old decking substructure wood collection — corrected to £680 (was £350 est.), charged per trip, 2 trips | 680 | 2026-09-11 | Cash | Same job as the earlier £350 estimate — supplier charges per trip, not a flat rate. Not a separate/additional charge. | Main deck | Item: old decking substructure wood collection.
2026-09-11 | Contingency | LG Building and Roofing Ltd | Cash | Extra digging — wider gate area + shed/additional deck (named purpose #11) | 1260 | 2026-09-11 | Cash | Quoted £1,400, 10% cash discount applied. Part of Luke's 11 Sep extras, £2,115 total across 4 items. | Extended deck & shed base | Item: extra digging for the wider gate area + shed/additional deck (mixed, both extended scope). | 11
2026-09-11 | Contingency | LG Building and Roofing Ltd | Cash | Cleanup after machines + dig up small tree (named purpose #12) | 180 | 2026-09-11 | Cash | Quoted £200, 10% cash discount applied. | Groundworks (digger & dumper) | Item: clean-up after the machines + small tree dig. | 12
2026-09-11 | Contingency | LG Building and Roofing Ltd | Cash | Fence move, chimney side/side a boundary reclaim (named purpose #13) | 315 | 2026-09-11 | Cash | Quoted £700 for move+spurs, but spurs (3.3, side b) didn't happen — only £350 charged, 10% cash discount applied. | Fence relocation | Item: fence move, chimney side / side (a) boundary reclaim. | 13
2026-09-11 | Contingency | LG Building and Roofing Ltd | Cash | Extra frame, wider deck gate area (named purpose #14) | 360 | 2026-09-11 | Cash | Quoted £400, 10% cash discount applied. | Extended deck & shed base | Item: extra frame for the wider deck gate area. | 14
2026-09-18 | Decking labour | LG Building and Roofing Ltd | Cash | Decking labour — second cash instalment (10% discount applies) | 2000 | 2026-09-18 | Cash | Retires £2,222.22 of quoted value at the 10% cash discount. Total paid to date: £8,400 (Stage 1 £4,400 invoiced + £2,000 cash 4 Sep + £2,000 cash 18 Sep). Quoted value retired: £8,844.44. Remaining: £8,755.56. | Main deck | Cost centre: decking labour.
2026-08-18 | Contingency | Travis Perkins (Luke's account) | 1049651867 | TP materials — cement, blade (named purpose #16) | 144.58 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 16
2026-08-19 | Contingency | Travis Perkins (Luke's account) | 1049757851 | TP materials — plywood, drill bit, screws, gloves (named purpose #17) | 74.34 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 17
2026-08-20 | Contingency | Travis Perkins (Luke's account) | 1049844268 | TP materials — ballast x2, cement, blocks, pallet deposit (named purpose #18) | 462.5 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). Includes £30.30 REFUNDABLE pallet deposit — not a final cost. PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 18
2026-08-20 | Contingency | Travis Perkins (Luke's account) | 1049844267 | TP materials — Broadfix flat packers (named purpose #19) | 22.66 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 19
2026-09-08 | Contingency | Travis Perkins (Luke's account) | 1050903283 | TP materials — plywood, line marker (named purpose #20) | 58.62 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 20
2026-09-09 | Contingency | Travis Perkins Hire (Luke's account) | 1051011143 | Digger hire — excavator, waiver, diesel, transport (named purpose #10, corrects £530 est.) | 378.58 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). No barrow loader charge on this invoice — flagged, not confirmed either way. PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split. | 10
2026-09-10 | Contingency | Travis Perkins (Luke's account) | 1051072869 | TP materials — ballast, cement (named purpose #21) | 124.73 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 21
2026-09-11 | Contingency | Travis Perkins (Luke's account) | 1051162218 | TP materials — gloves, woodscrews (named purpose #22) | 18.29 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Shared / site-wide | Small consumables (gloves + woodscrews) — cannot be split between projects. INFERRED. | 22
2026-09-11 | Contingency | Travis Perkins (Luke's account) | 1051142985 | TP fence materials — posts, postcrete, rail brackets, pegs, treated timber, gloves (named purpose #23) | 291.17 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). Two-page invoice, both pages verified (£242.64 goods + £48.53 VAT = £291.17). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Fence relocation | Item: fence materials (posts, rails, brackets, Postcrete, pegs). | 23
2026-09-29 | Contingency | V4 Wood Flooring Ltd | QUO-0031 (quote number used as invoice ref — no formal invoice/order confirmation received) | V4 materials — expanded shed-area/fence-move decking scope (named purpose #24), actioned + paid by phone 29 Sep | 5322.74 | 2026-09-29 | Card (paid over the phone) | Delivery expected 30 Sep or 1 Oct. Routed to Contingency per Ryan's steer 29 Sep — covers expanded scope beyond the original V4 order, not the base decking quote. | Extended deck & shed base | Quote: V4 order for the expanded shed-area / fence-move decking scope. | 24
2026-09-29 | Roofline works | Graham (The Plumbers' Merchant), via Luke's cash trade account | SI19670857 | Guttering/fascia materials — rear-of-house gutters (FloPlast Hi-Cap black system): gutter pipe, fascia brackets, running outlet, external stopend, downpipe | 256.78 | 2026-09-29 | Cash (via Luke) — £260 handed over, £3.22 of which was Luke's own coin top-up to round the figure | Replaces the £350 generic materials placeholder in Cost Lines for Roofline works. Further materials invoices may follow as the job extends to other elevations. | Roofline | Cost centre: Roofline works.
2026-09-30 | Roofline works | Graham (The Plumbers' Merchant), via Luke's cash trade account | SI19687572 | Union bracket (RUH1BL) — additional guttering fitting | 9.74 | 2026-10-02 | Cash (via Luke) — £90 combined with TFP 0001458493, paid 2 Oct | Part of a combined £90 cash payment (with TFP 0001458493): £87.75 of invoices + £2.25 Luke's coin top-up. Reimbursed to Luke in cash 2 Oct. | Roofline | Cost centre: Roofline works.
2026-09-30 | Roofline works | The Fascia Place (TFP), Guildford | 0001458493 | Fascia board, soffit board, fascia joints, soffit trim (white) | 78.01 | 2026-10-02 | Cash (via Luke) — £90 combined with Graham SI19687572, paid 2 Oct | Part of a combined £90 cash payment (with Graham SI19687572): £87.75 of invoices + £2.25 Luke's coin top-up. Reimbursed to Luke in cash 2 Oct. Invoice marked 'Payment has been received with thanks'. | Roofline | Cost centre: Roofline works.
2026-10-01 | Roofline works | The Fascia Place (TFP), Guildford | 0001458792 | Soffit board — 250mm x 9mm pre-vented, white (SM250WV) | 40.4 | 2026-10-02 | Cash (via Luke) — £40.40, paid 2 Oct | Invoice marked 'payment has been received' (Luke paid at the TP counter). Reimbursed to Luke in cash 2 Oct. | Roofline | Cost centre: Roofline works.
2026-08-11 | Contingency | Travis Perkins (Luke's account) | 1049231418 | Sand, white Snowcrete cement, Bosch blade (named purpose #25) | 108.14 | 2026-09-11 | Bank transfer (part of £500 TP receipt) | On Luke's TP trade account (NH4276), Net Monthly terms. Cleared by the £500 receipt of 11 Sep (taken from bank 12 Sep) per TP transaction history CSV. | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. NB white Snowcrete cement + sand may relate to the coping work (13 Aug). | 25
2026-08-17 | Contingency | Travis Perkins (Luke's account) | 1049595624 (part paid) | Ballast, building sand, 72 blocks (named purpose #26) — paid portion | 247.01 | 2026-09-11 | Bank transfer (part of £500 TP receipt) | On Luke's TP trade account (NH4276), Net Monthly terms. Part 1 of 2: £247.01 is the remainder of the £500 receipt after the five invoices listed in TP's CSV (inferred by elimination). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 26
2026-08-17 | Contingency | Travis Perkins (Luke's account) | 1049595624 (balance) | Ballast, building sand, 72 blocks (named purpose #26) — balance | 100.11 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276), Net Monthly terms. Part 2 of 2: the £100.11 balance, confirmed outstanding by Luke, paid by card 5 Oct as part of the £2,313.89 TP settlement. Part 1 (£247.01) was paid 11 Sep. | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 26
2026-09-03 | Contingency | Travis Perkins (Luke's account) | 1050655200 | Ballast x2, Mastercrete cement x10 (named purpose #27) | 249.46 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke. | 27
2026-09-14 | Contingency | Travis Perkins Hire (Luke's account) | 1051287675 | Tracked dumper hire 2–8 Sep (named purpose #28) | 277.79 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split. | 28
2026-09-21 | Contingency | Travis Perkins (Luke's account) | 1051688095 | Blocks x6, cement x4, rubber mallet, line marker (named purpose #29) | 60.3 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke. | 29
2026-09-21 | Contingency | Travis Perkins (Luke's account) | 1051708772 | Blocks x20 (named purpose #30) | 50.76 | 2026-10-05 | Card (TP settlement, 5 Oct) | On Luke's TP trade account (NH4276). PAID 5 Oct 2026 by card — part of the £2,313.89 TP settlement (see TP Account). | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke. | 30
2026-10-02 | Roofline works | LG Building and Roofing Ltd | INV-0291 | Roofline works labour — gutter replacement, fascia/soffit extension, slate replacement, barge board trim (per 4 Sep estimate; labour only, no VAT) | 1600 | 2026-10-03 | Bank transfer | Issued 2 Oct, due 2 Oct. Confirmed correct by Ryan 3 Oct and paid by bank transfer 3 Oct — full price, so no cash discount applies. Matches the labour line of the 4 Sep estimate exactly. | Roofline | Cost centre: Roofline works.
2026-10-09 | Contingency | LG Building and Roofing Ltd | INV-0293 (curves) | Extra decking labour — curves (named purpose #4); part of LG INV-0293 (curve and additional decking) | 800 | 2026-10-09 | Bank transfer | LG invoice INV-0293, £1,850 in total (no VAT), issued and due 9 Oct 2026 for the extra work carried out (curve and additional decking); paid in full 9 Oct by bank transfer. Full price, no cash discount. Separate from the £17,600 decking labour draws. | Main deck | Curves = named purpose #4 (Main deck scope). Ryan split INV-0293 into £800 curves + £1,050 additional deck on 9 Oct. | 4
2026-10-09 | Contingency | LG Building and Roofing Ltd | INV-0293 (additional deck) | Extra decking labour — additional deck, extended deck & shed base (named purpose #32); part of LG INV-0293 | 1050 | 2026-10-09 | Bank transfer | LG invoice INV-0293, £1,850 in total (no VAT), issued and due 9 Oct 2026 for the extra work carried out (curve and additional decking); paid in full 9 Oct by bank transfer. Full price, no cash discount. Separate from the £17,600 decking labour draws. | Extended deck & shed base | Additional deck = extended deck & shed base scope. Ryan split INV-0293 into £800 curves + £1,050 additional deck on 9 Oct. | 32
2026-10-06 | Contingency | Toolstation Ltd (bought by Luke, on his card) | YAC545477716 | Toolstation — Freud mitre saw blade (£71.99), ROKTOR HSS drill bits (£2.99), DeWalt circular saw blade (£9.99) (named purpose #33) | 84.97 | 2026-10-13 | Cash (reimbursed to Luke) | Ordered 6 Oct and paid by Luke by card (£70.80 + £14.17 VAT); Luke repaid in cash by Ryan on 13 Oct. Tools will be used throughout the project. | Main deck | Saw blades and drill bits — scope set as Main deck by Ryan 13 Oct, although they will be used throughout the project. | 33

## Cost Lines
Cost Lines — every line item from LG estimates and the V4 invoice
Source documents: LG chimney estimate 2 Jun 2026 · LG coping estimate 3 Jun 2026 · LG decking estimate 3 Jun 2026 · V4 invoice V4FQ-15584, 9 Jul 2026. · V4 quote #QUO-0031, actioned 29 Sep (Contingency named purpose #24). · TP invoices #5/#6/#11/#17/#18/#19 and TFP 0001458792 added 3 Oct.
Cost centre | Supplier | Line item | Qty | Unit £ | Line total £ | VAT | Payment route | Notes
Chimney repair | LG Building | Labour — remove render, k-rend sealer, base + top coat, render crown, storm-dry cream |  |  | 3200 | No VAT | LG invoice | INVOICED 24 Jul (INV-0286), full price £3,200 less £111.70 prepaid = £3,088.30. Non-cash, so 10% discount does not apply. Rubbish removal £80 outstanding.
Chimney repair | Scaffolder (direct) | Tubular scaffolding — all four sides of chimney and crown |  |  | 1500 | Inc VAT | Paid directly | Combined £3,200, cash terms (20 Jul): £2,000 paid following erection; £1,200 balance on strike.
Materials (pooled) | Merchant trade accounts | Materials (chimney estimate — pooled 20 Jul) |  |  | 480 | Inc VAT | Trade accounts — cleared on receipts
Chimney repair | LG Building | Rubbish removal |  |  | 0 | Inc VAT | LG invoice | TRANSFERRED 10 Aug to pooled Rubbish removal (skips) fund — family now supplies skips directly rather than Luke arranging disposal. No longer owed to Luke.
Coping stones repair | LG Building | Labour — remove/reset copings, slate cap, render, lead flashings to parapet rear |  |  | 3610 | No VAT | LG invoice | CONFIRMED 7 Aug, based on original £3,800 quote: 50% cash (£1710.00 @ 10% discount) due same day, 50% invoiced (£1900.00 full price) due next week, timed after back gutters are complete — see Invoicing Schedule. RISK: coping-stone damage on removal could substantially increase cost. Condensation-prep addition (£250) reclassified to Contingency 13 Aug — no longer part of this total.
Coping stones repair | Scaffolder (direct) | Tubular scaffolding with winch system |  |  | 1700 | Inc VAT | Paid directly | Combined £3,200, cash terms (20 Jul): £2,000 paid following erection; £1,200 balance on strike.
Materials (pooled) | Merchant trade accounts | Materials (coping estimate — pooled 20 Jul) |  |  | 650 | Inc VAT | Trade accounts — cleared on receipts
Coping stones repair | LG Building | Rubbish removal |  |  | 0 | Inc VAT | LG invoice | TRANSFERRED 10 Aug to pooled Rubbish removal (skips) fund. Removed from next week's invoice (now £1,900, not £1,980).
Decking labour | LG Building | Labour — remove old decking & frame, construct composite frame, install deck to spec |  |  | 17600 | No VAT | LG invoice | RISK: pending structure/ground assessment. Cash payments get the 10% discount (same as chimney/coping) — only invoiced stages are full price. Progress: Stage 1 (£4,400) invoiced 20 Aug + two £2,000 cash instalments (4 Sep, 18 Sep) — £8,400 cash paid to date, £8,844.44 quoted value retired, £8,755.56 quoted value remaining.
Decking labour | LG Building | Rubbish removal (8-yard skips ×2, possibly 3) |  |  | 0 | Inc VAT | LG invoice | TRANSFERRED 10 Aug to pooled Rubbish removal (skips) fund.
Decking materials (V4) | V4 Wood Flooring | Millboard Ashwood 176mm Moulded Lastane (144.90 m²) | 230 | 66.49 | 15292.7 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MFN360H | 18 | 58.09 | 1045.62 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MEBB360H (flexible bullnose) | 15 | 72.25 | 1083.75 | In net | V4 invoice — PAID | For curved upper level
Decking materials (V4) | V4 Wood Flooring | Millboard Step Edge — Ashwood Moulded Lastane | 15 | 59.89 | 898.35 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | Stainless steel screws 45mm — boxes | 24 | 32.08 | 770 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | Durafix Trimhead 35mm SS screws — box of 100 (FT35P100) | 6 | 10.25 | 61.5 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | Plas-Pro bearer/joist black 3.0m 50×125mm composite (P1205B300) | 266 | 28.4 | 7554.4 | In net | V4 invoice — PAID | Subframe — the bulk of the tonnage
Decking materials (V4) | V4 Wood Flooring | Subframe hexhead screws — box of 50 (FH90P050) | 16 | 7.87 | 125.92 | In net | V4 invoice — PAID | Original 16 boxes delivered in full, confirmed 12 Aug. TOP-UP REQUESTED 20 Aug: Luke has asked for 15 more boxes (same item, FH90P050) — substructure screw consumption running ahead of the original estimate. Not yet ordered/invoiced. Estimated cost £141.66 inc VAT (15 x £7.87 + 20% VAT, matching original per-unit price) — treat as V4 Phase 3 once ordered. Not yet added to committed total.
Decking materials (V4) | V4 Wood Flooring | Millboard touch-up paint — Ashwood (AP500H) | 1 | 15 | 15 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | Millboard multi-spacer — pack of 10 (FP36P010) | 1 | 10.25 | 10.25 | In net | V4 invoice — PAID
Decking materials (V4) | V4 Wood Flooring | VAT on order |  |  | 5371.5 | VAT | V4 invoice — PAID | Net £26,857.49 + VAT = £32,228.99
Contingency | TBC | Contingency pot — fence labour, garage drainage, curved-deck labour, cement & bricks, coping condensation-prep (£250, reclassified 13 Aug). Soakaway fix cancelled 1 Sep, nothing drawn. Pipe investigation resolved 4 Sep — no leak, no repair needed, no draw required. |  |  | 5000 | — | As incurred | Track on Contingency Drawdown sheet. Labour invoices from this pot at 10% discount (extended 20 Jul); materials (cement/bricks) full price. Curved-decking extra labour: discount status TBC with Luke. Coping condensation-prep (£250) added as named purpose #6, 13 Aug — payment method (cash vs invoice) pending confirmation.
Contingency | LG Building and Roofing Ltd | Named purpose #6 — Coping condensation-escape prep: re-bed 3 bricks; reinforce parapet corners with fibreglass mesh; fit 4 weep holes to front face above internal damp-course membrane (slate DPC capped in plastic DPM). Reclassified from Coping 13 Aug — same item, moved to keep coping's committed total accurate rather than inflate it. |  |  | 250 | TBC | Contingency drawdown | PRICED 13 Aug via Luke's invoice INV-0288: £250. Terms originally agreed as 100% cash; confirmed 14 Aug instead paid via bank transfer, bundled with the coping £1,900 balance. PAID 14 Aug.
Contingency | StoveWorldUK | Named purpose #7 — Chimney cowl upgrade: 5" Stainless Steel Chimney Pot Hanger Cowl (order #147399), replaces original spec | 1 | 62.9 | 62.9 | Inc VAT | Paid direct by Ryan (project account) | Decision logged 7 Aug (stainless steel, prevent rusting). Cost finalised 10 Aug, received 12 Aug, fitted 17 Aug. RECLASSIFIED 17 Aug from Chimney to Contingency — genuine scope addition beyond the original quote, same treatment as coping condensation-prep (#6). Paid direct by Ryan.
Materials (pooled) | LG Building and Roofing Ltd (Travis Perkins account) | Luke's Travis Perkins account materials, 3 invoices 17 Jul-5 Aug (render/masonry consumables + lead flashing) — pooled with chimney+coping materials, same simplified treatment as Dry Lining Supplies. |  |  | 481.26 | Inc VAT | Reimbursement to Luke | SIMPLIFIED 18 Aug: previously split chimney/coping 50/50 — now pooled as one line, consistent with how Dry Lining Supplies purchases were always treated (not split by workstream). DPC roll (£26.42) stays separately in Contingency (purpose #6, condensation-prep) as it's additional scope, not pool materials.
|  | (merged into row above, 18 Aug) |  |  | 0 | Inc VAT | Reimbursement to Luke | RECLASSIFIED 17 Aug: lead flashing reattributed from chimney to coping (original quote explicitly scopes 'lead flashings to parapet rear' under coping's labour). Both items within originally-quoted scope, so routed through Materials pool per agreed rule rather than Coping's own Cost Lines.
Contingency | V4 Wood Flooring Ltd | Named purpose #8 — V4 screw top-up: 15 more boxes of Timberfix structural subframe screws (FH90P050), quote V4FQ-17702 |  |  | 141.66 | Inc VAT | Bank transfer | Requested by Luke 20 Aug, ordered 24 Aug, PAID. Substructure screw consumption ran ahead of the original 16-box estimate. Same item/supplier as the original V4 order, but treated as an additional-scope purchase per Ryan's direction — routed through Contingency rather than inflating the Decking materials (V4) line, which stays matched to its original proforma.
Contingency | V4 Wood Flooring Ltd | Named purpose #9 — V4 screw top-up #2: 15 more boxes of Timberfix structural subframe screws (FH90P050), separate order from purpose #8 |  |  | 141.66 | Paid | Paid, delivery scheduled 11 Sep | PAID 10 Sep — invoice received. £141.66 used (matching purpose #8's confirmed rate: 15 x £7.87 + 20% VAT) — no invoice number/exact figure given this time, so this is inferred from the established pattern rather than confirmed from a document. Flag if the actual invoice differs. Delivery scheduled 11 Sep.
Contingency | Plant hire company (TBC) | Named purpose #10 — digger + barrow loader hire, one week (on hire until Thu 10 Sep). Mixed purpose: excavation for decking widening, side (a), AND new shed area, perpendicular to side (a) |  |  | 530 | Estimate | On hire, not yet invoiced | 8 Sep: digger on hire until Thursday, used for both the side (a) decking excavation and the new shed area excavation. Cost is an estimate ("should be about £530") — actual invoice will confirm. Genuinely mixed-purpose, doesn't cleanly split between the two uses.
Rubbish removal (pooled skips) | TBC (cash) | Old decking substructure wood collection — PAID 11 Sep, £680 cash (was estimated £350; charged per trip, 2 trips) |  |  | 680 | Cash | Paid | Original £350 estimate corrected 11 Sep — supplier charges per trip, and 2 trips were needed for this volume of wood. Same job, not a separate charge. From the decking quote scope, so pooled here per Ryan's confirmation.
Roofline works | LG Building and Roofing Ltd | Labour — gutter replacement (both parapet sides + lower rear elevation), fascia/soffit extension, slate replacement, barge board trim |  |  | 1600 | No VAT | Paid | Estimate dated 4 Sep. Started 29 Sep. INV-0291 (2 Oct, £1,600, no VAT, labour only) confirmed correct and PAID 3 Oct by bank transfer — full price, so no cash discount applies. Matches the labour line of the estimate exactly.
Roofline works | LG Building and Roofing Ltd | Scaffolding — portable tower |  |  | 0 | Inc VAT | Not required | Per estimate 4 Sep. NOT REQUIRED — Luke used his own ladder, so no tower was hired or paid (confirmed 3 Oct). Shown at £0 actual; the £150 benefit offsets the £40.40 of additional materials (net £109.60 under the £2,100 budget). The quote itself stays at £2,140.
Roofline works | LG Building and Roofing Ltd | Materials |  |  | 260 | Cash | Paid | Invoice SI19670857 (Graham, 29 Sep): £256.78 (Net £213.98 + VAT £42.80). Luke topped up with £3.22 coin to round to £260 cash, which Ryan paid to Luke 29 Sep. Replaces the generic £350 materials estimate — further materials invoices may follow as the job extends to other elevations.
Rubbish removal (pooled skips) | LG Building and Roofing Ltd | Roofline works rubbish removal — £40, paid directly per the 4 Sep estimate. Reclassified from Roofline works into the pooled fund, avoiding a separate cost centre for what is genuinely the same category of waste-removal spend. |  |  | 40 | Inc VAT | Expected — not yet incurred | Per estimate 4 Sep. RECLASSIFIED 8 Sep from Roofline works into the pooled Rubbish removal fund — same rationale as the other pooled items (chimney/coping/decking rubbish already share this fund). Not yet incurred as of 9 Oct (no rubbish removal invoice received) — expected, not drawn.
Contingency | LG Building and Roofing Ltd | Named purpose #11 — extra digging: wider deck gate area (1 day x2 people) + additional deck/shed area (1 day x2 people) |  |  | 1260 | Cash (10% disc.) | Paid | Quoted £1,400, cash-discounted to £1,260. Tied to tasks 2.2 (wider gate area) + 2.6 (shed/additional deck) — mixed purpose, doesn't cleanly split between the two. Part of Luke's 11 Sep extras invoice, £2,115 total across 4 items.
Contingency | LG Building and Roofing Ltd | Named purpose #12 — cleanup after machines (2hrs) + dig up small tree (2hrs) |  |  | 180 | Cash (10% disc.) | Paid | Quoted £200, cash-discounted to £180. Tied to tasks 2.2/2.6 excavation cleanup. Small tree dig — distinct from task 3.4's external tree/bush clearing company. Part of the same 11 Sep extras invoice.
Contingency | LG Building and Roofing Ltd | Named purpose #13 — fence move, chimney side (side a boundary reclaim from neighbour, to enable the wider decking area) |  |  | 315 | Cash (10% disc.) | Paid | Quoted £700 for 'move fence and do spurs to make a full day', but spurs (task 3.3, side b) did NOT happen — only £350 charged for the fence move itself, cash-discounted to £315. NOT the same fence as 3.3 (side b, concrete spurs) or 3.5 (TPO/tree-dependent). New task — see Gantt.
Contingency | LG Building and Roofing Ltd | Named purpose #14 — extra frame for wider deck gate area (1 person; no extra charge for boarding) |  |  | 360 | Cash (10% disc.) | Paid | Quoted £400, cash-discounted to £360. Tied to task 2.2 (decking side a widening substructure/framing).
Contingency | V4 Wood Flooring Ltd | Named purpose #15 — V4 screw top-up #3: 15 more boxes of Timberfix structural subframe screws (FH90P050), separate order from purposes #8 and #9 |  |  | 141.66 | Invoice due | Not yet paid | Invoice received 18 Sep for another 15 boxes at the established rate (£7.87/box + 20% VAT = £141.66, matching purposes #8/#9 exactly). Not yet paid.
Contingency | Travis Perkins (Luke's account) | Named purpose #16 — Invoice 1049651867 (18 Aug): Mastercrete cement 25kg x12 |  |  | 102.1 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #16 — Invoice 1049651867 (18 Aug): Trend Craft Blade CC 305mm |  |  | 42.48 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #17 — Invoice 1049757851 (19 Aug): Shuttering plywood 18mm CE2 |  |  | 30.79 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #17 — Invoice 1049757851 (19 Aug): Dewalt drill bit |  |  | 10.86 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #17 — Invoice 1049757851 (19 Aug): Stick-Fit woodscrews 5.0x80mm x200 |  |  | 17.88 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #17 — Invoice 1049757851 (19 Aug): Wonder Grip gloves size 9 |  |  | 14.81 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #18 — Invoice 1049844268 (20 Aug): Ballast bulk bag |  |  | 82.19 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #18 — Invoice 1049844268 (20 Aug): Mastercrete cement 25kg x10 |  |  | 85.08 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #18 — Invoice 1049844268 (20 Aug): Solid dense block 100mm x72 |  |  | 182.74 | Inc VAT | Paid 5 Oct (card, TP settlement) | Printed unit rate on the invoice (£21.15/TN) doesn't reconcile to the £152.28 net charged for 72 blocks — effective rate is £2.115/block. Likely a mislabelled unit on the supplier's invoice; the charged total is internally consistent. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #18 — Invoice 1049844268 (20 Aug): Block pallet deposit — REFUNDABLE |  |  | 30.3 | Inc VAT | Paid 5 Oct (card, TP settlement) | REFUNDABLE when pallet returned — not a final cost. Flagged here so it isn't forgotten; should be reversed out once returned/confirmed. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #18 — Invoice 1049844268 (20 Aug): Ballast bulk bag (2nd) |  |  | 82.19 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #19 — Invoice 1049844267 (20 Aug): Broadfix flat packers, tub of 300 |  |  | 22.66 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #20 — Invoice 1050903283 (8 Sep): Shuttering plywood 12mm CE2 x2 |  |  | 53.26 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #20 — Invoice 1050903283 (8 Sep): Prosolve line marker |  |  | 5.36 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #10 (UPDATED) — Invoice 1051011143 (9 Sep): 1.5T excavator, 1 week hire |  |  | 227.98 | Inc VAT | Paid 5 Oct (card, TP settlement) | Actual invoice received — corrects the earlier £530 estimate. No barrow loader charge appears on this invoice anywhere — flagged, not assumed either hired-but-unbilled or genuinely not needed. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #10 (UPDATED) — Invoice 1051011143 (9 Sep): Loss and damage waiver, 1 week |  |  | 34.2 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #10 (UPDATED) — Invoice 1051011143 (9 Sep): Diesel, 12L |  |  | 32.4 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #10 (UPDATED) — Invoice 1051011143 (9 Sep): Transport, delivered |  |  | 42 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #10 (UPDATED) — Invoice 1051011143 (9 Sep): Transport, collected |  |  | 42 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #21 — Invoice 1051072869 (10 Sep): Ballast bulk bag |  |  | 82.19 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #21 — Invoice 1051072869 (10 Sep): Mastercrete cement 25kg x5 |  |  | 42.54 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #22 — Invoice 1051162218 (11 Sep): Wonder Grip gloves (L) + Stick-Fit woodscrews 5.0x40mm x200 |  |  | 18.29 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: BSW Sawn Green Treated 22x150mm x3.0m (qty 3) |  |  | 23.87 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: Green Treated UC4 Fence Post 100x100mm x3.0m (qty 3) |  |  | 59.87 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: Pegs Pointed Sawn Treated 47x50mm x0.6m (qty 4) |  |  | 10.27 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: Blue Circle Postcrete 20kg (qty 6) |  |  | 44.78 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: Treated Timber 25x50mm x4.8m (qty 1) |  |  | 6.29 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: 4Trade Arris Rail Fixing Bracket Galvanised (qty 18) |  |  | 138.24 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #23 — Invoice 1051142985 (11 Sep), FENCE MATERIALS: Wonder Grip Duo Gloves (XL) (qty 1) |  |  | 7.85 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276). Paid 5 Oct by card as part of the TP settlement.
Contingency | LG Building and Roofing Ltd | Named purpose #4 — additional curved-decking labour: preparing curved structures for the top level of decking. AGREED 24 Sep at £1,000 full price / £900 cash; INVOICED 9 Oct as £800 on INV-0293 (the curves), paid by bank transfer. |  |  | 800 | No VAT | Paid 9 Oct (bank transfer) | Luke billed £800 for the curves rather than the £1,000 agreed on 24 Sep; the other £200 is not expected unless Luke bills it later. Paid in full price by bank transfer, so no cash discount. See Invoice Register (INV-0293).
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — Millboard Enhanced Grain 176mm Ashwood decking boards (MDE176H) | 35 | 69.21 | 2422.35 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep | For the new shed-area / expanded decking scope
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — Plas-Pro Bearer, sub-frame (P1205B300) | 44 | 34.02 | 1496.88 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — Hexhead Screws 6.3x90mm, box of 50 (FH90P050) | 5 | 7.87 | 39.35 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep | Same unit price as the original July order — unchanged
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — Bullnose Board Ashwood (MEBB360H) | 3 | 75.46 | 226.38 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — DuoSpan 99 Flexible Bracket Sets, 10/box (K99FP010) | 2 | 35.95 | 71.9 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep | For the curved sections
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — DuoSpan-to-Plas-Pro Screws 5x25mm, 100/box (FD25P100) | 1 | 15.79 | 15.79 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — Flexible Bullnose Step Edge Ashwood (MEBF50H) | 3 | 54.32 | 162.96 | In net | V4 (quote QUO-0031) — PAID by phone 29 Sep | Qty 3 supplied vs 5 originally requested by Luke — flagged, not resolved
Contingency | V4 Wood Flooring Ltd | Named purpose #24 — VAT on order |  |  | 887.13 | VAT | V4 (quote QUO-0031) — PAID by phone 29 Sep | Net £4,435.61 + VAT £887.13 = £5,322.74. Quote #QUO-0031 (28 Sep), actioned and paid by phone with Jon 29 Sep — no formal invoice/order confirmation received, quote number used as reference. Delivery expected 30 Sep or 1 Oct. Routed to Contingency (not Decking materials) per Ryan's steer 29 Sep: this order covers the EXPANDED scope — new shed-area decking plus the extra area freed up by the fence move — not the original quoted decking scope. This single draw alone exceeds the £5,000 Contingency pot; logged in full, not capped or hidden. See Contingency Drawdown sheet.
Roofline works | Graham (Plumbers' Merchant) | Materials — Union Bracket (RUH1BL), additional guttering fitting |  |  | 9.74 | Inc VAT | Cash | Invoice SI19687572, 30 Sep. Reimbursed to Luke in cash 2 Oct as part of £90.
Roofline works | The Fascia Place (TFP) | Materials — fascia board, soffit board, fascia joints, soffit trim (white) |  |  | 78.01 | Inc VAT | Cash | Invoice 0001458493, 30 Sep. Payment received with thanks (per invoice). Reimbursed to Luke in cash 2 Oct as part of £90.
Roofline works | Luke | Cash rounding / coin top-up to make up £90 cash, covering invoices SI19687572 + 0001458493 |  |  | 2.25 | Rounding | Cash | Luke provided coins so the combined £87.75 across both invoices rounded to £90 cash. Paid 2 Oct.
Roofline works | The Fascia Place (TFP) | Materials — 250mm x 9mm pre-vented soffit board, white (SM250WV). Invoice 0001458792 (1 Oct) | 1 |  | 40.4 | Inc VAT | Cash | Net £33.67 + VAT £6.73. Invoice marked 'payment received' (Luke paid at TP counter). Reimbursed to Luke in cash 2 Oct. Roofline materials to date £390.40 cash vs the £350 allowance (£40.40 over).
Contingency | Travis Perkins (Luke's account) | Named purpose #25 — Invoice 1049231418 (11 Aug): Sharp/grit sand trade pack | 2 |  | 8.86 | Inc VAT | Paid 11 Sep (from £500 TP receipt) | On Luke's TP trade account (NH4276), Net Monthly terms. Cleared by the £500 TP receipt of 11 Sep.
Contingency | Travis Perkins (Luke's account) | Named purpose #25 — Invoice 1049231418 (11 Aug): Building sand trade pack | 4 |  | 17.71 | Inc VAT | Paid 11 Sep (from £500 TP receipt) | Same invoice/account as above.
Contingency | Travis Perkins (Luke's account) | Named purpose #25 — Invoice 1049231418 (11 Aug): Blue Circle Snowcrete white Portland cement 25kg | 2 |  | 45.14 | Inc VAT | Paid 11 Sep (from £500 TP receipt) | Same invoice/account as above.
Contingency | Travis Perkins (Luke's account) | Named purpose #25 — Invoice 1049231418 (11 Aug): Bosch Pro multi-material demolition blade (5 pcs) | 1 |  | 36.43 | Inc VAT | Paid 11 Sep (from £500 TP receipt) | Same invoice/account as above.
Contingency | Travis Perkins (Luke's account) | Named purpose #26 — Invoice 1049595624 (17 Aug): Ballast bulk bag | 1 |  | 82.19 | Inc VAT | Paid: £247.01 on 11 Sep, £100.11 on 5 Oct (card) | On Luke's TP trade account (NH4276), Net Monthly terms. Part payment of £247.01 inferred by elimination from TP's CSV; the £100.11 balance was paid by card on 5 Oct (TP settlement).
Contingency | Travis Perkins (Luke's account) | Named purpose #26 — Invoice 1049595624 (17 Aug): Building sand bulk bag | 1 |  | 82.19 | Inc VAT | Paid: £247.01 on 11 Sep, £100.11 on 5 Oct (card) | Same invoice/account as above.
Contingency | Travis Perkins (Luke's account) | Named purpose #26 — Invoice 1049595624 (17 Aug): Solid dense block 100mm 7.3N | 72 |  | 182.74 | Inc VAT | Paid: £247.01 on 11 Sep, £100.11 on 5 Oct (card) | Same invoice/account as above.
Contingency | Travis Perkins (Luke's account) | Named purpose #27 — Invoice 1050655200 (03 Sep): Ballast bulk bag | 2 |  | 164.38 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #27 — Invoice 1050655200 (03 Sep): Mastercrete cement 25kg | 10 |  | 85.08 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #28 — Invoice 1051287675 (14 Sep): Tracked dumper 500kg, 7 days (2–8 Sep) | 1 |  | 163.3 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #28 — Invoice 1051287675 (14 Sep): Loss and damage waiver | 1 |  | 24.49 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #28 — Invoice 1051287675 (14 Sep): Wear charge, fleeted refuel | 1 |  | 6 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #28 — Invoice 1051287675 (14 Sep): Hire delivery | 1 |  | 42 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins Hire (Luke's account) | Named purpose #28 — Invoice 1051287675 (14 Sep): Hire collection | 1 |  | 42 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #29 — Invoice 1051688095 (21 Sep): Solid dense block 100mm | 6 |  | 15.23 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #29 — Invoice 1051688095 (21 Sep): Blue Circle Mastercrete cement 25kg | 4 |  | 34.03 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #29 — Invoice 1051688095 (21 Sep): Minotaur rubber mallet 16oz | 1 |  | 5.68 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #29 — Invoice 1051688095 (21 Sep): Prosolve line marker 750ml | 1 |  | 5.36 | Inc VAT | Paid 5 Oct (card, TP settlement) | Same invoice/account as above. Paid 5 Oct by card as part of the TP settlement.
Contingency | Travis Perkins (Luke's account) | Named purpose #30 — Invoice 1051708772 (21 Sep): Solid dense block 100mm | 20 |  | 50.76 | Inc VAT | Paid 5 Oct (card, TP settlement) | On Luke's TP trade account (NH4276), Net Monthly terms. Paid 5 Oct by card as part of the TP settlement.
Contingency | LG Building and Roofing Ltd | Named purpose #31 — additional lead work: chase lead into walls so the gutters work properly (issue found during the Roofline works) |  |  | 200 | Estimate | Estimated, not started | Luke's estimate 2 Oct (WhatsApp), approx £200; job not started. Additional scope arising from the Roofline works, to be drawn from Contingency (Ryan, 3 Oct). Gantt task 1.5a — part of Gate 2, must finish before decking boards are laid. Logged in Cost Lines only — not in the Invoice Register or Drawdown until invoiced.
Contingency | LG Building and Roofing Ltd | Named purpose #32 — additional deck labour (extended deck & shed base): the additional decking carried out, part of INV-0293 (curve and additional decking) |  |  | 1050 | No VAT | Paid 9 Oct (bank transfer) | Invoiced 9 Oct as part of INV-0293 (£1,850: £800 curves + £1,050 additional deck) and paid the same day by bank transfer. Separate from the £17,600 main decking labour draws.
Contingency | Toolstation Ltd (bought by Luke) | Named purpose #33 — Invoice YAC545477716 (6 Oct): Freud mitre saw blade | 1 |  | 71.99 | Inc VAT | Paid 13 Oct (cash to Luke) | Bought by Luke on his card 6 Oct; repaid in cash 13 Oct. Scope Main deck, though the tools will be used throughout.
Contingency | Toolstation Ltd (bought by Luke) | Named purpose #33 — Invoice YAC545477716 (6 Oct): ROKTOR HSS titanium multi-material drill bits | 1 |  | 2.99 | Inc VAT | Paid 13 Oct (cash to Luke) | Bought by Luke on his card 6 Oct; repaid in cash 13 Oct. Scope Main deck, though the tools will be used throughout.
Contingency | Toolstation Ltd (bought by Luke) | Named purpose #33 — Invoice YAC545477716 (6 Oct): DeWalt construction circular saw blade | 1 |  | 9.99 | Inc VAT | Paid 13 Oct (cash to Luke) | Bought by Luke on his card 6 Oct; repaid in cash 13 Oct. Scope Main deck, though the tools will be used throughout.
Contingency | Gorgeous Cleaning Services | Named purpose #34 — whole-house soft wash: gutters, soffits, roof tiles, roof solar panels, render, windows etc. |  |  | 1200 | Quoted | Booked, not yet paid (cash) | £1,200 cash, drawn from Contingency (Ryan, 13 Oct). Starts Mon 19 Oct. Replaces the chimney + coping-only soft wash (Gantt 1.6): cheaper to use a previous supplier for the whole house than to spot clean with Luke. All roofline works must be finished first (hard deadline, due Fri 16 Oct). Logged in Cost Lines only until paid.
|  | TOTAL (all lines) |  |  | 83870.28

## TP Account
Travis Perkins (TP) account — invoices, payments and settlement
Luke's TP trade account NH4276. Amounts inc VAT. Built 3 Oct 2026 from the paper invoices and TP's transaction history CSV (2 Oct). Updated 9 Oct 2026: account settled (5 Oct card payment; 6 Oct repayment from Luke).
# | Invoice no. | Invoice date | Description | Amount £ | Paid £ | Balance £ | Status | Cost centre / purpose | Line items check £ (must be 0.00) | Notes | Scope
1–3 | 1047678330 / 1047972816 / 1048887075 | 17 Jul – 5 Aug | Render/masonry consumables + lead flashing; DPC roll (grouped, not itemised) | 507.7 | 507.7 | 0 | Paid | Materials (pooled) £481.28; Contingency #6 £26.42 | 0 | Paid 18 Aug — part of £547.88 settlement (bank transfer) | Chimney & coping
4 | 1049120278 | 2026-08-10 | Cleaning/finishing consumables (pooled, not itemised) | 40.18 | 40.18 | 0 | Paid | Materials (pooled) | 0 | Paid 18 Aug — part of £547.88 settlement (bank transfer) | Chimney & coping
5 | 1049231418 | 2026-08-11 | Sand, white Snowcrete cement, Bosch blade | 108.14 | 108.14 | 0 | Paid | Contingency #25 | 0 | Paid 11 Sep from the £500 TP receipt (TP CSV) | Main deck
6 | 1049595624 | 2026-08-17 | Ballast, building sand (bulk bags), 72 blocks | 347.12 | 347.12 | 0 | Paid | Contingency #26 | 0 | £247.01 paid 11 Sep from the £500 receipt (inferred by elimination); the £100.11 balance was paid by card 5 Oct. | Main deck
7 | 1049651867 | 2026-08-18 | Mastercrete cement x12, Trend blade | 144.58 | 144.58 | 0 | Paid | Contingency #16 | 0 | Paid by card 5 Oct (settlement) | Main deck
8 | 1049757851 | 2026-08-19 | Plywood 18mm, drill bit, woodscrews, gloves | 74.34 | 74.34 | 0 | Paid | Contingency #17 | 0 | Paid by card 5 Oct (settlement) | Main deck
9 | 1049844267 | 2026-08-20 | Broadfix flat packers | 22.66 | 22.66 | 0 | Paid | Contingency #19 | 0 | Paid by card 5 Oct (settlement) | Main deck
10 | 1049844268 | 2026-08-20 | Ballast x2, cement x10, 72 blocks, pallet deposit | 462.5 | 462.5 | 0 | Paid | Contingency #18 | 0 | Includes £30.30 refundable pallet deposit. Paid by card 5 Oct (settlement) | Main deck
11 | 1050655200 | 2026-09-03 | Ballast x2, Mastercrete x10 | 249.46 | 249.46 | 0 | Paid | Contingency #27 | 0 | Paid by card 5 Oct (settlement) | Main deck
12 | 1050903283 | 2026-09-08 | Plywood 12mm x2, line marker | 58.62 | 58.62 | 0 | Paid | Contingency #20 | 0 | Paid by card 5 Oct (settlement) | Main deck
13 | 1051011143 | 2026-09-09 | Digger hire 3–8 Sep (1.5T excavator) | 378.58 | 378.58 | 0 | Paid | Contingency #10 | 0 | Paid by card 5 Oct (settlement) | Groundworks (digger & dumper)
14 | 1051072869 | 2026-09-10 | Ballast, Mastercrete x5 | 124.73 | 124.73 | 0 | Paid | Contingency #21 | 0 | Paid by card 5 Oct (settlement) | Main deck
15 | 1051142985 | 2026-09-11 | Fence materials | 291.17 | 291.17 | 0 | Paid | Contingency #23 | 0 | The purchase the £500 receipt enabled. Paid by card 5 Oct (settlement) | Fence relocation
16 | 1051162218 | 2026-09-11 | Gloves + woodscrews | 18.29 | 18.29 | 0 | Paid | Contingency #22 | 0 | Paid by card 5 Oct (settlement) | Shared / site-wide
17 | 1051287675 | 2026-09-14 | Tracked dumper hire 2–8 Sep | 277.79 | 277.79 | 0 | Paid | Contingency #28 | 0 | Paid by card 5 Oct (settlement) | Groundworks (digger & dumper)
18 | 1051688095 | 2026-09-21 | Blocks x6, cement x4, mallet, line marker | 60.3 | 60.3 | 0 | Paid | Contingency #29 | 0 | Paid by card 5 Oct (settlement) | Extended deck & shed base
19 | 1051708772 | 2026-09-21 | Blocks x20 | 50.76 | 50.76 | 0 | Paid | Contingency #30 | 0 | Paid by card 5 Oct (settlement) | Extended deck & shed base
| TOTAL (17 lines = 19 invoices) |  |  | 3216.92 | 3216.92 | 0 |  |  | 0
Payments to TP
| Date | Payment | Detail | Amount £ | Method
| 2026-08-18 | TP account settlement | Covers invoices #1–4 (bank transfer) | 547.88 | Bank transfer
| 2026-09-11 | TP account receipt | Ref 3357*NH4276*21439*1; taken from bank 12 Sep. Allocated below (TP transaction history CSV) | 500 | Bank transfer
| 2026-10-05 | TP settlement payment | Balance of #6 (£100.11) plus #7–#19 (£2,213.78). Card. Settles the account | 2313.89 | Card
| TOTAL PAID TO TP (gross) |  |  | 3361.77
| 2026-10-06 | Repayment from Luke | The part of the 11 Sep £500 that cleared other jobs' invoices (Chris / Wendy), repaid to us | -144.85 | Repayment
| NET PAID TO TP (gross less repayment) |  |  | 3216.92
How the £500 (11 Sep) was applied — per TP's CSV
| Invoice no. | Invoice date | PO ref on invoice | Amount applied £ | Project invoice?
| 1047365656 | 2026-07-13 | CHRIS | 69.8 | No — other job
| 1047453677 | 2026-07-14 | CHRIS | 30.65 | No — other job
| 1047531278 | 2026-07-15 | WENDY | 30.69 | No — other job
| 1047531279 | 2026-07-15 | WENDY | 13.71 | No — other job
| 1049231418 | 2026-08-11 | LARA | 108.14 | Yes — our #5
| 1049595624 | 2026-08-17 | LARA | 247.01 | Yes — part payment on our #6 (inferred by elimination; CSV does not list #6)
| TOTAL APPLIED |  |  | 500
| Check: £500 less total applied (must be 0.00) |  |  | 0
| Of which: other jobs (not project spend) |  |  | 144.85
| Of which: this project |  |  | 355.15
Settlement of our TP involvement — SETTLED 5–6 Oct (approach agreed with Luke, 3 Oct)
| Item |  |  | Amount £
| Balance still owing on #6 (invoice less the £247.01 paid 11 Sep) |  |  | 100.11
| Plus: total of invoices #7 to #19 |  |  | 2213.78
| Less: our £500 used on other jobs' invoices (Wendy / Chris) |  |  | -144.85
| AMOUNT TO SETTLE |  |  | 2169.04
| If the £30.30 pallet deposit is refunded (possible credit still to come) |  |  | 2138.74
| Net paid in settlement: 5 Oct card payment less 6 Oct repayment from Luke |  |  | 2169.04
| Check: amount to settle less net paid in settlement (must be 0.00) |  |  | 0
| Check: Invoice Register total for Travis Perkins suppliers less ledger total (must be 0.00) |  |  | 0
| Check: total invoiced less net paid to TP — balance outstanding (must be 0.00) |  |  | 0
Covers the 19 invoices held at 3 Oct. Settled in full 5 Oct; any further TP invoices from Luke would be additional.

## TP Spend by Item
TP Spend by Item — combined spend on each material across all TP invoices
Calculated from the TP Line Items tab. Amounts inc VAT; 'spend' = invoiced, regardless of payment status. First/last dates are invoice dates.
Item | What's in it | Spend £ (inc VAT) | First invoice | Last invoice | Invoices (# in TP Account) | Qty / detail
Ballast | Bulk bags | 493.14 | 2026-08-17 | 2026-09-10 | #6, #10, #11, #14 | 6 bulk bags (~£82.19 each)
Concrete blocks | 100mm solid dense | 431.47 | 2026-08-17 | 2026-09-21 | #6, #10, #18, #19 | 170 blocks (72 + 72 + 6 + 20)
Cement | Mastercrete 25kg and white Snowcrete | 393.97 | 2026-08-11 | 2026-09-21 | #5, #7, #10, #11, #14, #18 | 43 bags: 41 Mastercrete (~£8.51) + 2 Snowcrete (~£22.57)
Fence materials | Posts, rail brackets, Postcrete, pegs, treated timber | 283.32 | 2026-09-11 | 2026-09-11 | #15 | One invoice, 11 Sep
Tools, PPE, screws & small consumables | Blades, drill bit, mallet, line markers, gloves, woodscrews, flat packers | 187.66 | 2026-08-11 | 2026-09-21 | #5, #7, #8, #9, #12, #15, #16, #18 | Small items across 8 invoices
Sand | Building, sharp/grit sand; bulk bag | 108.76 | 2026-08-11 | 2026-08-17 | #5, #6 | 7 units (1 bulk bag, 4 + 2 trade packs)
Shuttering plywood | 18mm and 12mm CE2 | 84.05 | 2026-08-19 | 2026-09-08 | #8, #12 | 18mm + 2 x 12mm
Plant hire | Digger £378.58 (hired 3–8 Sep) + tracked dumper £277.79 (hired 2–8 Sep) | 656.37 | 2026-09-09 | 2026-09-14 | #13, #17 | Invoice dates, not hire dates
Refundable pallet deposit | Block pallet deposit — not a final cost if the pallet is returned | 30.3 | 2026-08-20 | 2026-08-20 | #10 | Refundable
SUBTOTAL — invoices #5–19 |  | 2669.04
Invoices #1–4 (not itemised) | Render/masonry consumables + lead flashing £481.28; DPC roll £26.42; cleaning/finishing consumables £40.18 | 547.88 | 17 Jul 2026 | 10 Aug 2026 | #1–#4 | Settled 18 Aug; no item breakdown held
TOTAL INVOICED |  | 3216.92
Check: TP Account total less this total (must be 0.00) |  | 0
Formulas:
First invoice = MINIFS('TP Line Items'!$B:$B,'TP Line Items'!$D:$D,[Item])
Last invoice = MAXIFS('TP Line Items'!$B:$B,'TP Line Items'!$D:$D,[Item])

## TP Line Items
TP Line Items — every item on every Travis Perkins invoice
Source for the TP Account and TP Spend by Item tabs. Amounts inc VAT. Invoices #1–4 were settled as a group and are not itemised. Built 3 Oct 2026 from paper invoices and the tracker.
Invoice no. | Invoice date | Item | Category | Qty | Amount £ (inc VAT) | Scope | Scope basis
1047678330 / 1047972816 / 1048887075 | 17 Jul – 5 Aug | Render/masonry consumables + lead flashing (pooled, not itemised) | Invoices #1–4 (not itemised) |  | 481.28 | Chimney & coping | Cost centre (chimney/coping pools).
1047678330 / 1047972816 / 1048887075 | 17 Jul – 5 Aug | Damplas DPC roll (invoice 1048887075) | Invoices #1–4 (not itemised) |  | 26.42 | Chimney & coping | Cost centre (chimney/coping pools).
1049120278 | 2026-08-10 | Cleaning/finishing consumables (pooled, not itemised) | Invoices #1–4 (not itemised) |  | 40.18 | Chimney & coping | Cost centre (chimney/coping pools).
1049231418 | 2026-08-11 | Sharp/grit sand trade pack | Sand | 2 | 8.86 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049231418 | 2026-08-11 | Building sand trade pack | Sand | 4 | 17.71 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049231418 | 2026-08-11 | Blue Circle Snowcrete white Portland cement 25kg | Cement | 2 | 45.14 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049231418 | 2026-08-11 | Bosch Pro multi-material demolition blade (5 pcs) | Tools, PPE, screws & small consumables | 1 | 36.43 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049595624 | 2026-08-17 | Ballast bulk bag | Ballast | 1 | 82.19 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049595624 | 2026-08-17 | Building sand bulk bag | Sand | 1 | 82.19 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049595624 | 2026-08-17 | Solid dense block 100mm 7.3N | Concrete blocks | 72 | 182.74 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049651867 | 2026-08-18 | Blue Circle Mastercrete cement 25kg | Cement | 12 | 102.1 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049651867 | 2026-08-18 | Trend Craft blade CC 305mm | Tools, PPE, screws & small consumables | 1 | 42.48 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049757851 | 2026-08-19 | Shuttering plywood 18mm CE2 | Shuttering plywood |  | 30.79 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049757851 | 2026-08-19 | Dewalt drill bit | Tools, PPE, screws & small consumables | 1 | 10.86 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049757851 | 2026-08-19 | Stick-Fit woodscrews 5.0x80mm (pack of 200) | Tools, PPE, screws & small consumables | 1 | 17.88 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049757851 | 2026-08-19 | Wonder Grip gloves size 9 | Tools, PPE, screws & small consumables | 1 | 14.81 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049844267 | 2026-08-20 | Broadfix flat packers, tub of 300 | Tools, PPE, screws & small consumables | 1 | 22.66 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049844268 | 2026-08-20 | Ballast bulk bag | Ballast | 1 | 82.19 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049844268 | 2026-08-20 | Mastercrete cement 25kg | Cement | 10 | 85.08 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049844268 | 2026-08-20 | Solid dense block 100mm | Concrete blocks | 72 | 182.74 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049844268 | 2026-08-20 | Block pallet deposit — REFUNDABLE | Refundable pallet deposit | 1 | 30.3 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1049844268 | 2026-08-20 | Ballast bulk bag (2nd) | Ballast | 1 | 82.19 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1050655200 | 2026-09-03 | Ballast bulk bag | Ballast | 2 | 164.38 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1050655200 | 2026-09-03 | Mastercrete cement 25kg | Cement | 10 | 85.08 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1050903283 | 2026-09-08 | Shuttering plywood 12mm CE2 | Shuttering plywood | 2 | 53.26 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1050903283 | 2026-09-08 | Prosolve line marker | Tools, PPE, screws & small consumables | 1 | 5.36 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1051011143 | 2026-09-09 | 1.5T excavator, 6 days (3–8 Sep) | Plant hire | 1 | 227.98 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051011143 | 2026-09-09 | Loss and damage waiver | Plant hire | 1 | 34.2 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051011143 | 2026-09-09 | Diesel in tank, 12L | Plant hire | 12 | 32.4 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051011143 | 2026-09-09 | Transport (delivered) | Plant hire | 1 | 42 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051011143 | 2026-09-09 | Transport (collected) | Plant hire | 1 | 42 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051072869 | 2026-09-10 | Ballast bulk bag | Ballast | 1 | 82.19 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1051072869 | 2026-09-10 | Mastercrete cement 25kg | Cement | 5 | 42.54 | Main deck | Date rule: invoiced before 21 Sep → main deck. Luke (2 Oct): only 1 day (2 people) spent on the extended deck so far — half last week, half this week. INFERRED — confirm with Luke.
1051142985 | 2026-09-11 | BSW Sawn Green Treated 22x150mm x3.0m | Fence materials | 3 | 23.87 | Fence relocation | Item: fence materials.
1051142985 | 2026-09-11 | Green Treated UC4 Fence Post 100x100mm x3.0m | Fence materials | 3 | 59.87 | Fence relocation | Item: fence materials.
1051142985 | 2026-09-11 | Pegs Pointed Sawn Treated 47x50mm x0.6m | Fence materials | 4 | 10.27 | Fence relocation | Item: fence materials.
1051142985 | 2026-09-11 | Blue Circle Postcrete 20kg | Fence materials | 6 | 44.78 | Fence relocation | Item: fence materials.
1051142985 | 2026-09-11 | Treated Timber 25x50mm x4.8m | Fence materials | 1 | 6.29 | Fence relocation | Item: fence materials.
1051142985 | 2026-09-11 | 4Trade Arris Rail Fixing Bracket Galvanised | Fence materials | 18 | 138.24 | Fence relocation | Item: fence materials.
1051142985 | 2026-09-11 | Wonder Grip Duo Gloves (XL) | Tools, PPE, screws & small consumables | 1 | 7.85 | Fence relocation | Item: fence materials.
1051162218 | 2026-09-11 | Wonder Grip gloves (L) + Stick-Fit woodscrews 5.0x40mm (x200) — combined line | Tools, PPE, screws & small consumables |  | 18.29 | Shared / site-wide | Small consumables — cannot be split between projects. INFERRED.
1051287675 | 2026-09-14 | Tracked dumper 500kg, 7 days (2–8 Sep) | Plant hire | 1 | 163.3 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051287675 | 2026-09-14 | Loss and damage waiver | Plant hire | 1 | 24.49 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051287675 | 2026-09-14 | Wear charge, fleeted refuel | Plant hire | 1 | 6 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051287675 | 2026-09-14 | Hire delivery | Plant hire | 1 | 42 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051287675 | 2026-09-14 | Hire collection | Plant hire | 1 | 42 | Groundworks (digger & dumper) | Hire used for both the main deck widening and the new shed area (Luke, 8 Sep) — mixed, not split.
1051688095 | 2026-09-21 | Solid dense block 100mm | Concrete blocks | 6 | 15.23 | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke.
1051688095 | 2026-09-21 | Blue Circle Mastercrete cement 25kg | Cement | 4 | 34.03 | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke.
1051688095 | 2026-09-21 | Minotaur rubber mallet 16oz | Tools, PPE, screws & small consumables | 1 | 5.68 | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke.
1051688095 | 2026-09-21 | Prosolve line marker 750ml | Tools, PPE, screws & small consumables | 1 | 5.36 | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke.
1051708772 | 2026-09-21 | Solid dense block 100mm | Concrete blocks | 20 | 50.76 | Extended deck & shed base | Concrete/blocks dated 21 Sep — fits the first extended-deck work (Luke, 2 Oct: 1 day x2 people so far, half last week, half this week). INFERRED — confirm with Luke.
TOTAL |  | 51 lines |  |  | 3216.92

## Skip Hire Log
Skip Hire Log — pooled rubbish-removal drawdown
Provisional pooled budget £1,360 (transferred 10 Aug from chimney £80 + coping £80 + decking £1,200 rubbish-removal quotes). Family now supplies skips directly rather than Luke arranging disposal. Log every skip here AND on the Invoice Register (cost centre: Rubbish removal (pooled skips)) — this sheet is skip detail, the Register is the money record. Unlike the materials pool, more skips are expected — budget may need topping up. £40 Roofline works rubbish removal is expected but not yet incurred, so it is shown on its own row and not drawn.
Opening pool: | 1360 | Remaining: | -100
Date | Provider | Skip details | Phase / use | Amount £ | Running remaining £
2026-08-10 | Skip Hire Comparison Ltd | 8 cubic yard, general waste, delivery 11 Aug (ref D81F29CE-0002) — CANCELLED 11 Aug (supplier delayed), refunded in full (receipt 3362-9782) | Above-ground works (chimney/coping) | 344.16 | 1015.84
2026-08-11 | Skip Hire Comparison Ltd | Refund — cancelled booking, receipt 3362-9782, 5-10 working days to clear | Refund (cancelled skip) | -344.16 | 1360
2026-08-11 | Elmbridge Mini Skips | 8 cubic yard, delivery — filled, awaiting exchange (INV-11373, ref 25996) | Above-ground works (chimney/coping) | 390 | 970
2026-08-12 | Elmbridge Mini Skips | 8 cubic yard, exchange — collects filled skip, delivers empty (INV-11375, ref 26030) | Above-ground works (chimney/coping) | 390 | 580
2026-09-11 | TBC (cash) | Old decking substructure wood collection — PAID 11 Sep, £680 cash (was estimated £350; supplier charges per trip, 2 trips required) | Decking substructure, both sides | 680 | -100
2026-09-04 | LG Building and Roofing Ltd | EXPECTED, NOT YET INCURRED — Roofline works rubbish removal, £40 per the 4 Sep estimate. Reclassified 8 Sep from Roofline works into this pooled fund. Not counted in the running balance until incurred; if it is, the pool would be £140 over. | Roofline works

## Materials Receipts
Materials Receipts — pooled budget drawdown
Pooled budget £1,130 (chimney £480 + coping £650, pooled 20 Jul). Log every merchant receipt here AND on the Invoice Register (cost centre: Materials (pooled)) — this sheet is the pool detail, the Register is the money record. NOTE: pool is over cap after adding Luke's Travis Perkins account materials (now paid in full, 18 Aug) — flagged deliberately, not hidden; cap left at £1,130 rather than raised. PENDING 18 Aug: 5 bags of unused monocouche (Weber Pral M) returned to Dry Lining Supplies — refund expected within a couple of working days. Calculated from receipts: Weber Pral M Silver Pearl consistently £12.62/bag inc VAT (£126.20/10 on 22 Jul, £50.48/4 on 4 Aug) × 5 bags = £63.10 expected refund. Not yet logged as received — add Paid date once the credit note actually lands.
Opening pool: | 1130 | Remaining: | -62.9
Date | Merchant | Items (summary) | Phase / use | Amount £ | Running remaining £
2026-07-20 | Dry Lining Supplies Ltd | Render mesh, Weberend Aid ×6, angle/stop beads, rubble sacks, Bond It SBR 5l (project share; £111.71 platform excluded — Luke's equipment) | Render (chimney + coping, shared) | 311.98 | 818.02
2026-07-22 | Dry Lining Supplies | Weber Pral M Silver Pearl x10 (£126.20), Plastic 15mm Stop Bead 3m x3 (£9.60), inc VAT | Render finish (chimney + coping, shared) | 162.96 | 655.06
2026-08-04 | Dry Lining Supplies Ltd | Weberend Ocr x3 (£29.13), Weber Pral M Silver Pearl x4 (£50.48), Stop Bead x6 (£19.20), Drip Bead x2 (£7.42), Sikabond SBR (£17.54), inc VAT | Render (coping stones) | 148.53 | 506.53
2026-08-16 | SoftWash UK | Render Cleaner Gel X Pro, 5 Litres (order F4UJ62VLQ) | Render cleanup (chimney + coping, shared) | 47.99 | 458.54
2026-08-17 | LG Building and Roofing Ltd (Travis Perkins account) | Render/masonry consumables + lead flashing, 3 invoices 17 Jul-5 Aug (1047678330 / 1047972816 / 1048887075) — pooled, not split by workstream | Render (chimney + coping, pooled) | 481.26 | -22.72
2026-08-10 | LG Building and Roofing Ltd (Travis Perkins account, INV 1049120278) | Cleaning/finishing consumables (trigger spray, decorating cloth) — pooled, not split by workstream | Render (chimney + coping, pooled) | 40.18 | -62.9