## Summary
Spinney External Works — Budget Summary
Last updated: | 2026-07-13 | All figures gross (as payable). Invoiced / Paid pull automatically from the Invoice Register; Contingency remaining pulls from the Drawdown sheet.
Cost centre | Supplier | Committed £ | Invoiced £ | Paid £ | Remaining vs committed £ | Notes
Decking materials | V4 Wood Flooring Ltd | 32228.99 | 32228.99 | 32228.99 | 0 | Order amended to all Ashwood + flexible bullnose (1 Jul). PAID IN FULL 9 Jul, ref V4FQ-15584. 25% restocking on over-ordering — unlikely given curved design + offcuts project, but noted.
Decking labour & rubbish | LG Building and Roofing Ltd | 18800 | 0 | 0 | 18800 | £17,600 labour (no VAT) + £1,200 rubbish removal. RISK: price 'fairly accurate' pending Luke's structure/ground assessment.
Contingency | — | 5000 | 0 | 0 | 5000 | Covers: fence move/repair labour; soakaway fix before decking; drainage by garage; extra curved-decking labour; cement & bricks. Luke's labour drawn from this pot attracts the 10% discount (extended 20 Jul). See Contingency Drawdown sheet.
Chimney repair | LG Building and Roofing Ltd | 4460 | 1049.21 | 1049.21 | 3410.79 | Quoted separately (2 Jun). Labour £2,880 (10% discount, 20 Jul) no VAT + £80 rubbish; scaffolding £1,500 share of combined invoice; materials in pooled budget.
Coping stones repair | LG Building and Roofing Ltd | 5200 | 1062.5 | 1062.5 | 4137.5 | Quoted separately (3 Jun). Labour £3,420 (10% discount, 20 Jul) no VAT + £80 rubbish; scaffolding £1,700 share. RISK: damage to coping stones on removal could substantially increase cost. Materials in pooled budget.
Materials (pooled) | Merchant trade accounts | 1130 | 311.98 | 311.98 | 818.02 | Pooled chimney (£480) + coping (£650) materials budget — decision 20 Jul. Purchased via merchant trade accounts (Dry Lining Supplies, Travis Perkins etc.), cleared on receipts. Detail on Materials Receipts sheet.
Core project (Luke's ~£56,800 outline) |  | 56028.99 | 32228.99 | 32228.99 | 23800
Chimney + coping incl. pooled materials |  | 10790 | 2423.69 | 2423.69 | 8366.31
PROJECT TOTAL |  | 66818.99 | 34652.68 | 34652.68 | 32166.31
Contingency remaining: | 5000

## Invoicing Schedule
Invoicing Schedule — expected invoice events
Terms: 10% labour discount on all Luke phases except decking labour and scaffolding. Chimney & coping settle as SINGLE CASH PAYMENTS on phase completion (agreed Lara/Ryan 20 Jul; TBC with Luke 21 Jul). Log every payment on the Invoice Register — this sheet is expectations, the Register is the record.
# | Cost centre | Trigger event | Payee | Basis | Est. £ | Status | Notes
1 | Decking materials | Order placed — PAID IN FULL 9 Jul | V4 Wood Flooring Ltd | Invoice V4FQ-15584 (Register row 1) | 32228.99 | Paid | All-Ashwood + flexible bullnose; 144.9 m²
2 | Chimney + Coping (scaffold) | Erection complete (17–18 Jul) — PAID | Scaffolder (direct) | £2,000 in cash (of £3,200 combined) | 2000 | Paid | Logged in Register: £937.50 chimney + £1,062.50 coping (pro-rata of £1,500/£1,700)
3 | Chimney + Coping (scaffold) | Strike, after Gate 1 sign-off | Scaffolder (direct) | £1,200 cash balance on strike | 1200 | Agreed | Log in Register: £562.50 chimney + £637.50 coping
4 | Chimney repair | Phase completion — SINGLE cash payment | LG Building and Roofing Ltd | Labour £2,880 (10% disc.) + rubbish £80 = £2,960; less £111.71 prepaid (work platform) | 2960 | Lara/Ryan agreed — TBC Luke 21 Jul | CASH DUE ON COMPLETION: £2,848.29. One-week phase — no interim invoice
5 | Coping stones repair | Phase completion — SINGLE cash payment | LG Building and Roofing Ltd | Labour £3,420 (10% disc.) + rubbish £80 = £3,500 | 3500 | Lara/Ryan agreed — TBC Luke 21 Jul | CASH DUE ON COMPLETION: £3,500.00
6 | Decking labour & rubbish | 4–5 stages — triggers TBC with Luke/Lara | LG Building and Roofing Ltd | £18,800 total across stages. EXCLUDED from 10% labour discount | 18800 | Approved 20 Jul | Suggested triggers: start / substructure (a) / Gate 2 / substructure (b) / Gate 3 — to be pinned
7 | Materials (pooled) | Periodic — on receipts | Merchant trade accounts (Dry Lining Supplies, TP etc.) | Pooled £1,130 budget (chimney £480 + coping £650) | 1130 | Agreed in principle | Log each receipt in Register + Materials Receipts sheet
8 | Contingency | Rainy-day tasks 100% on completion; named extras as incurred | LG Building / merchants | £5,000 pot — fence labour, soakaway fix, garage drainage, curved-deck extras, cement & bricks. Labour at 10% discount | 5000 | Approved 20 Jul | Curved-decking extra labour discount TBC (decking exclusion boundary). Each drawdown also on Contingency Drawdown sheet
9 | Materials (pooled) | Periodic — on receipts | Merchant trade accounts (Dry Lining Supplies, TP etc.) | SCHEDULE TOTAL (all rows): | 66818.99 | Agreed in principle | Pooled £1,130 budget — log each receipt in Register + Materials Receipts sheet
10 | Contingency | Rainy-day tasks invoiced 100% on completion; named extras as incurred | LG Building / Travis Perkins | Summary tab committed total: | 66818.99 | Approved 20 Jul | Rainy-day tasks invoiced 100% on completion, labour less 10%. Curved-decking extra labour discount TBC. Each drawdown also logged on Contingency Drawdown sheet
|  |  |  | Difference (must be £0.00): | 0
|  |  |  | Summary tab committed total: | 66818.99
|  |  |  | Difference (must be £0.00): | -66818.99

## Cost Lines
Cost Lines — every line item from LG estimates and the V4 invoice
Source documents: LG chimney estimate 2 Jun 2026 · LG coping estimate 3 Jun 2026 · LG decking estimate 3 Jun 2026 · V4 invoice V4FQ-15584, 9 Jul 2026.
Cost centre | Supplier | Line item | Qty | Unit £ | Line total £ | VAT | Payment route | Notes
Chimney repair | LG Building | Labour — remove render, k-rend sealer, base + top coat, render crown, storm-dry cream |  |  | 2880 | No VAT | LG invoice | Original quote £3,200; 10% labour discount agreed 20 Jul (Ryan/Luke): −£320
Chimney repair | Scaffolder (direct) | Tubular scaffolding — all four sides of chimney and crown |  |  | 1500 | Inc VAT | Paid directly | Combined £3,200, cash terms (20 Jul): £2,000 paid following erection; £1,200 balance on strike.
Materials (pooled) | Merchant trade accounts | Materials (chimney estimate — pooled 20 Jul) |  |  | 480 | Inc VAT | Trade accounts — cleared on receipts
Chimney repair | LG Building | Rubbish removal |  |  | 80 | Inc VAT | LG invoice
Coping stones repair | LG Building | Labour — remove/reset copings, slate cap, render, lead flashings to parapet rear |  |  | 3420 | No VAT | LG invoice | Original quote £3,800; 10% labour discount agreed 20 Jul (Ryan/Luke): −£380. RISK: stone damage on removal could substantially increase cost
Coping stones repair | Scaffolder (direct) | Tubular scaffolding with winch system |  |  | 1700 | Inc VAT | Paid directly | Combined £3,200, cash terms (20 Jul): £2,000 paid following erection; £1,200 balance on strike.
Materials (pooled) | Merchant trade accounts | Materials (coping estimate — pooled 20 Jul) |  |  | 650 | Inc VAT | Trade accounts — cleared on receipts
Coping stones repair | LG Building | Rubbish removal |  |  | 80 | Inc VAT | LG invoice
Decking labour & rubbish | LG Building | Labour — remove old decking & frame, construct composite frame, install deck to spec |  |  | 17600 | No VAT | LG invoice | RISK: pending structure/ground assessment. EXCLUDED from 10% labour discount (20 Jul).
Decking labour & rubbish | LG Building | Rubbish removal (8-yard skips ×2, possibly 3) |  |  | 1200 | Inc VAT | LG invoice
Decking materials | V4 Wood Flooring | Millboard Ashwood 176mm Moulded Lastane (144.90 m²) | 230 | 66.49 | 15292.7 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MFN360H | 18 | 58.09 | 1045.62 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard Ashwood Moulded Lastane — MEBB360H (flexible bullnose) | 15 | 72.25 | 1083.75 | In net | V4 invoice — PAID | For curved upper level
Decking materials | V4 Wood Flooring | Millboard Step Edge — Ashwood Moulded Lastane | 15 | 59.89 | 898.35 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Stainless steel screws 45mm — boxes | 24 | 32.08 | 770 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Durafix Trimhead 35mm SS screws — box of 100 (FT35P100) | 6 | 10.25 | 61.5 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Plas-Pro bearer/joist black 3.0m 50×125mm composite (P1205B300) | 266 | 28.4 | 7554.4 | In net | V4 invoice — PAID | Subframe — the bulk of the tonnage
Decking materials | V4 Wood Flooring | Subframe hexhead screws — box of 50 (FH90P050) | 16 | 7.87 | 125.92 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard touch-up paint — Ashwood (AP500H) | 1 | 15 | 15 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | Millboard multi-spacer — pack of 10 (FP36P010) | 1 | 10.25 | 10.25 | In net | V4 invoice — PAID
Decking materials | V4 Wood Flooring | VAT on order |  |  | 5371.5 | VAT | V4 invoice — PAID | Net £26,857.49 + VAT = £32,228.99
Contingency | TBC | Contingency pot — fence labour, soakaway fix, garage drainage, curved-deck labour, cement & bricks |  |  | 5000 | — | As incurred | Track on Contingency Drawdown sheet. Labour invoices from this pot at 10% discount (extended 20 Jul); materials (cement/bricks) full price. Curved-decking extra labour: discount status TBC with Luke (decking exclusion boundary).
|  | TOTAL (all lines) |  |  | 66818.99

## Invoice Register
Invoice & Payment Register — add a row per invoice received
Yellow cells are inputs. Cost centre must match the Summary sheet names exactly (dropdown-free by design — copy from row 5). Paid date empty = outstanding.
Invoice date | Cost centre | Supplier | Reference | Description | Amount £ (gross) | Paid date | Method | Notes
2026-07-09 | Decking materials | V4 Wood Flooring Ltd | V4FQ-15584 | Millboard Ashwood decking + Plas-Pro subframe, fixings (144.9 m²) | 32228.99 | 2026-07-09 | Amex | Paid in full at order
2026-07-20 | Materials (pooled) | Dry Lining Supplies Ltd | RECB000NNIVB49XWEXOG | Render materials (shared chimney+coping): mesh, Weberend Aid ×6, beads, SBR, rubble sacks | 311.98 | 2026-07-20 | Pay By Link | Project-materials share of £423.69 receipt
2026-07-20 | Chimney repair | Dry Lining Supplies Ltd | RECB000NNIVB49XWEXOG | Folding work platform 600mm — Luke's equipment, non-project | 111.71 | 2026-07-20 | Pay By Link | PREPAYMENT vs chimney phase-start invoice: pay £1,528.29 of the £1,640 when it lands
2026-07-20 | Chimney repair | Scaffolder (via Trevor) | Cash | Scaffold erection payment — chimney share (pro-rata of £2,000 cash) | 937.5 | 2026-07-20 | Cash | £2,000 paid following erection 17–18 Jul; amend date cell if payment day differed
2026-07-20 | Coping stones repair | Scaffolder (via Trevor) | Cash | Scaffold erection payment — coping share (pro-rata of £2,000 cash) | 1062.5 | 2026-07-20 | Cash | Balance £1,200 due on strike

## Materials Receipts
Materials Receipts — pooled budget drawdown
Pooled budget £1,130 (chimney £480 + coping £650, pooled 20 Jul). Log every merchant receipt here AND on the Invoice Register (cost centre: Materials (pooled)) — this sheet is the pool detail, the Register is the money record.
Opening pool: | 1130 | Remaining: | 818.02
Date | Merchant | Items (summary) | Phase / use | Amount £ | Running remaining £
2026-07-20 | Dry Lining Supplies Ltd | Render mesh, Weberend Aid ×6, angle/stop beads, rubble sacks, Bond It SBR 5l (project share; £111.71 platform excluded — Luke's equipment) | Render (chimney + coping, shared) | 311.98 | 818.02

## Contingency Drawdown
Contingency Drawdown — £5,000 pot (agreed Lara/Luke, 1 Jul 2026)
Named purposes: fence move/repair labour · soakaway fix before decking · drainage by the garage · additional curved-decking labour · cement & bricks. Luke's labour from this pot invoiced at 10% discount (extended 20 Jul); materials full price. Curved-decking extra labour discount status TBC.
Opening pot: | 5000 | Remaining: | 5000
Date | Purpose | Supplier / detail | Amount £ | Running remaining £