## Gantt
Spinney External Works — Project Gantt (v3 — replanned 10 Aug, parallel execution)
Last updated: | 2026-08-10 | Crew basis: Luke +1. Works now running in PARALLEL (chimney/coping/soakaway simultaneously), superseding the original one-phase-at-a-time model. Luke's 22–29 Aug holiday is the binding constraint on decking start, not sequential dependencies.
Legend: teal bar = task · gold = milestone / stage gate · grey column = Luke holiday · blue text on yellow = edit these cells (Start / End dates drive the bars)
ID | Task | Owner | Depends on | Days | Status | Start | End | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30
PHASE 1 — SCAFFOLD & AT-HEIGHT WORKS
1.0 | Site setup & garden segregation fencing (family access preserved) | Luke +1 | — | 2 | Complete | 2026-07-13 | 2026-07-14
1.1 | Scaffold A + B erection (incl. discrete decking demolition at footing points) | Trevor | 1.0 | 2 | Complete | 2026-07-17 | 2026-07-18
1.2 | Chimney repair — cut render to substrate, realign, re-render. Cowl fitted 17 Aug. Sealant applied 18 Aug — COMPLETE. | Luke +1 | 1.1 | 7 | Complete | 2026-07-20 | 2026-08-18
1.3 | Coping stones — cut back, lead flashing, replace stones, watertight. Sealant applied 18 Aug — COMPLETE. | Luke +1 | 1.2 | 10 | Complete | 2026-08-03 | 2026-08-18
1.4 | Back-of-house gutters — realign, lead flashing, hedgehog brushes. DELAYED 19 Aug: decking substructure (old boards/substructure removal, new substructure install) prioritised this week instead. Not starting this week — new date TBC. Gates new decking BOARD installation, either side, and coping's remaining invoice (already paid 13 Aug). | Luke +1 | 1.5 | 3 | Delayed — decking substructure prioritised, new date TBC
G1 | STAGE GATE 1 — At-height works sign-off: cowl fitted, chimney + coping finished, "everything looks great" (Lara / Neels / Ryan) | Family | 1.2, 1.3 |  | CLEARED 18 Aug — chimney + coping both complete | 2026-08-17 | 2026-08-17
1.5 | Scaffold strike (A + B) — COMPLETE 18 Aug. Final £1,200 payment paid — full £3,200 now settled (£1,500 chimney + £1,700 coping). | Trevor | G1 | 1 | Complete | 2026-08-18 | 2026-08-18
PHASE 2 — GROUNDWORKS & DECKING
2.1 | Soakaway drainage, side (a) — investigation phase COMPLETE 18 Aug. Excavation phase resumes after Luke's holiday (~1 Sep+) rather than completing by 21 Aug as originally planned — no longer a tight pre-holiday squeeze. New pipework, reposition existing pipe, realign pump as backup drainage still to come. | Luke +1 | — | 5 | Investigation complete — excavation resumes after holiday | 2026-08-10
V1 | V4 Phase 1 — COMPLETE 12 Aug (notified 10 Aug): all items received, including joists (Plas-Pro Bearer/Joist — confirmed via two deliveries same day). Only 228 decking boards (Milboard Enhanced Grain) outstanding, rolled into Phase 2, as planned. | Ryan | — |  | Complete | 2026-08-10 | 2026-08-12
V2 | V4 Phase 2 — 228 decking boards (Milboard Enhanced Grain), only outstanding item from Phase 1. To be ordered on request when needed (date TBC, not before decking (a) underway) | V4 Flooring | On request | — | Floating | 2026-08-27 | 2026-08-28
2.3 | Decking side (a) — strip out, new substructure, lay Millboard per design (access: gate a only) | Luke +1 | 1.4, 1.5, 2.1 | 13 | Not started | 2026-09-01 | 2026-09-17
G2 | STAGE GATE 2 — Decking (a) sign-off | Family | 2.3 |  | Not started | 2026-09-18 | 2026-09-18
2.4 | Decking side (b) — lay Millboard boards per design (strip-out and new substructure already complete, 16-18 Aug — see 2.0b). Board-laying still gated on gutters, V4's remaining boards, and Luke's holiday. | Luke +1 | G2, 3.3 | 13 | Not started | 2026-09-21 | 2026-10-07
G3 | STAGE GATE 3 — Decking (b) sign-off | Family | 2.4 |  | Not started | 2026-10-08 | 2026-10-08
2.5 | Bonus — BBQ & shed area from offcuts / excess, side (a) | Luke +1 | G3 | 3 | Not started | 2026-10-09 | 2026-10-13
G4 | PROJECT COMPLETION — snagging & final sign-off | Family | All |  | Not started | 2026-10-14 | 2026-10-14
PHASE 3 — FLOATING / RAINY-DAY POOL (pivot here when weather or hold-ups stall the spine)
3.1 | Driveway channel — lift cobbles, dig waste channel, connect softener discharge to natural drainage, reinstate | Luke +1 | — | 4 | Floating
3.2 | Front-of-house gutters, minor roof repairs and tile repairs — repair / realignment (ladder work). Tile repairs confirmed via WhatsApp (10 Aug), same no-separate-charge basis. | Luke +1 | — | 2 | Floating
3.3 | Fence spurring, side (b) — MUST complete before decking side (b) starts (latest finish: Sat 19 Sep on current plan) | Luke +1 | → before 2.4 | 3 | Floating
3.4 | Tree / bush clearing back to fence boundary — EXTERNAL company; scope & cost outside this project | External co. | — | — | External
3.5 | Fence relocation — route per TPO outcome (original line or divert around tree) | Luke +1 | 3.4 + TPO | 4 | Floating
3.6 | Skip 2 — triggered by Luke's request when decking work needs it (not on a fixed cycle; skip 1 arrived 11 Aug) | Skip Hire Comparison Ltd | On request | — | Floating
T1 | TPO appeal decision — date TBC (branch point for 3.5) | External | — |  | Floating | TBC
3.7 | Pipe investigation & replacement — leaking house waste pipe beneath chimney, found via wet ground at Scaffold A erection | Luke +1 | 1.5, 2.3 (decking a strip-out) | TBC | Not started |  |  | Confirmed 10 Aug: chimney = Scaffold A, and 2.1's partial deck demo is also on side (a) — same location. Earliest start: once scaffold struck (~18 Aug) AND old decking/substructure removed on side (a), during 2.3's strip-out (~early Sept, exact day TBC). Duration and cost unknown until exposed and assessed. COST: contingency-funded, no figure yet.
2.0b | Decking substructure, side (b) — CORRECTED 18 Aug: this is side (b), not side (a) as first logged 17 Aug. Old boards + substructure removed 17-18 Aug. New substructure underway — concrete mixed onsite 18 Aug for brick pier supports. Travis Perkins order (F49820, 17/08/26): ballast, sand, 72x solid dense blocks. Cost TBC. | Luke +1 | — | TBC | In progress | 2026-08-17
Non-working: Luke holiday w/c 27 Jul & w/c 24 Aug (grey columns); UK bank holiday Mon 31 Aug (w/c 31 Aug is a 4-day week).
Rule: work proceeds only with Luke onsite. As of 10 Aug, works run in PARALLEL (chimney/coping/soakaway simultaneously) — the original one-phase-at-a-time model has been superseded by faster real-world pace. Rainy-day pool absorbs weather losses on render/roof work.
Decking start (1 Sep) is set by Luke's 22–29 Aug holiday, not by sequential dependencies — at-height works, gutters, strike and soakaway all complete well ahead of that date.
V4 Phase 1 (substructure, fixings, 2 boards) notified and delivered 10–12 Aug, ahead of the old formula-driven milestone. V4 Phase 2 (remaining boards) is ordered on request when needed, mirroring Skip 2's trigger logic.
Luke's outline (1 Jul): render, coping and roofing ~3 working weeks total — v1 durations are more conservative; await his corrections before compressing.

## Task Register
Task Register — locations, access discipline & pivot flags
Access rule: side (a) works use gate (a) exclusively (top-left entrance, lower/green deck); side (b) works use gate (b) exclusively (bottom-right entrance). No material movement over newly laid Millboard. Orange = upper level to summer house (see Decking_plan.pdf).
ID | Workstream | Task | Location | Access route | Weather-sensitive | Rainy-day eligible | Est. days | Notes / assumptions
1.0 | Site setup | Garden segregation fencing & site setup | Garden (both sides) | n/a | N | N | 2 | Keeps garden usable by family through Summer — working areas fenced, not a building site.
1.1 | Scaffolding | Erect Scaffold A (chimney) + Scaffold B (coping/gutters); discrete decking demolition at footing points | Roof perimeter, two locations | n/a | Y | N | 2 | Trevor's team. Fixed: Fri 17 – Sat 18 Jul. Both towers up together; remain until Gate 1 sign-off.
1.2 | Chimney | Cut render back to substrate, fix alignment, re-render | Chimney (Scaffold A) | Scaffold A | Y | N | 7 | Render weather-sensitive: no rain, not too hot. Target: complete before 22 Aug — first in queue to protect this.
1.3 | Coping stones | Cut back, lead flashing, replace coping stones, make watertight | Separate elevation (Scaffold B) | Scaffold B | Y | N | 10 | Independent scaffold structure from chimney.
1.4 | Guttering (back) | Re-align, lead flashing, clean & tie down hedgehog brushes | Back of house | Ladder — BLOCKED until scaffold struck | Y | N | 3 | Scaffold not required for the gutters work itself (ladder access), but comes down first as it's in the way. DELAYED 19 Aug: decking substructure work (old boards/substructure removal, new substructure install) prioritised this week — gutters not starting this week, new date TBC. Still gates: (1) new decking board installation, either side; (2) coping's remaining 50% invoice (already paid 13 Aug).
1.5 | Scaffolding | Strike Scaffold A + B | Both locations | n/a | N | N | 1 | Only after Gate 1 sign-off (Lara/Neels/Ryan).
2.1 | Drainage (soakaway) | Partial demolition of existing decking, new pipework off downpipes, reposition existing pipe | Back garden, side (a) | Gate (a) | Y | N | 5 | Started 10 Aug (top-layer partial deck removal), running in parallel with chimney/coping. Investigation phase COMPLETE 18 Aug. Excavation phase resumes after Luke's holiday (~1 Sep+) — no longer completing before the holiday as originally planned.
2.2 | Decking | V4 Flooring delivery — 6t+ Millboard & substructure | Delivery / landing zone | TBC with Luke | N | N | 2 | PAID IN FULL 9 Jul 2026 (£32,228.99, ref V4FQ-15584). Notify V4 14 calendar days ahead (M1). Landing zone must not breach gate segregation. 25% restocking on over-ordered materials.
2.3 | Decking (a) | Remove existing decking & substructure; install new substructure; lay Millboard per design | Soakaway side (a) — green lower + share of orange upper | Gate (a) ONLY | N | N | 13 | Begins only after scaffold removed. Entrance = top-left of green deck on plan.
2.4 | Decking (b) | As 2.3 | Driveway side (b) | Gate (b) ONLY | N | N | 13 | Entrance = bottom-right of green deck on plan. No crossing over side (a) new boards.
2.5 | Decking (bonus) | Lay offcuts / excess for new BBQ & shed area | Side (a) | Gate (a) | N | Y | 3 | Only when decking complete; uses surplus material.
3.1 | Driveway channel | Lift bricks/cobbles, dig waste channel, connect water-softener discharge to natural drainage, reinstate cobbles | Front driveway | Front | N | Y | 4 | Active problem — softener currently free-flooding driveway. Prime rainy-day pivot.
3.2 | Guttering (front) & tile repairs | Repair / re-alignment, tile repairs | Front of house | Ladder only | N | Y | 2 | No scaffold dependency. Tile repairs confirmed in scope via WhatsApp (10 Aug), same no-separate-charge basis as gutters.
3.3 | Fencing | Fence spurring, side (b) first | Garden boundary | Garden | N | Y | 3 | HARD CONSTRAINT (as designed): side (b) spurring should complete before decking side (b) begins — access otherwise sub-optimal. STATUS 18 Aug: not yet done, but propped up temporarily and confirmed not to impact substructure laying. Deliberately deferred — Luke prefers wet weather for manipulating the fencing when actually fixing it. Rainy-day eligible, no fixed deadline pressure.
3.4 | Fencing | Tree / bush clearing back to fence boundary — EXTERNAL company | Garden boundary | Garden | N | Y | 2 | Outside project scope and budget; details and costs handled separately. Prerequisite for fence relocation (3.5) only.
3.5 | Fencing | Fence relocation — original line (TPO appeal succeeds) or divert around tree (fails) | Garden boundary | Garden | N | Y | 4 | Gated on TPO decision (T1, date TBC). Both routes pre-planned.
3.7 | Plumbing/drainage | Investigate and replace leaking house waste pipe beneath chimney | Beneath chimney, side (a) — same location as Scaffold A and 2.1's deck demo | Side (a), post-strip-out | N | N | TBC | Confirmed 10 Aug: chimney = Scaffold A = side (a). Earliest start: scaffold struck (~18 Aug) AND old decking/substructure removed on side (a) (during 2.3 strip-out, ~early Sept). Duration/cost unknown until exposed — contingency-funded.

## Reference
Reference — contacts, rules, assumptions, sign-off log
CONTACTS (fill in yellow cells — phone / email are placeholders)
Name | Role | Team | Phone | Email
EXAMPLE — Jane Doe | Example row — format guide | — | 07700 900123 | jane.doe@example.com
Lara | Key Decision Maker & Budget Holder | Family | 07791 528837 | larakriek@gmail.com
Neels | Project management support | Family | 07880 688027 | neels.kriek@gmail.com
Ryan | Project manager | Family | 07851 601499 | ryanbishop23@gmail.com
Luke | Chief builder, head of company | L.G Building and Roofing Ltd | 07799 748123
Ross | Right-hand man | L.G Building and Roofing Ltd
Max | Right-hand man | L.G Building and Roofing Ltd
Roy | Right-hand man | L.G Building and Roofing Ltd
Trevor | Scaffold team contact | L.G Building and Roofing Ltd
V4 Flooring | Decking materials storage & delivery | V4 Flooring | 01276 488099
WORKING RULES
• Work proceeds only if Luke is onsite.
• SUPERSEDED 10 Aug: works now run in PARALLEL (chimney, coping, soakaway simultaneously) — the original one-phase-at-a-time model no longer reflects actual practice.
• Crew planning basis: Luke +1 (conservative). Additional hands = schedule upside, never assumed.
• Working days: Monday–Friday, excluding Luke's holidays and UK bank holidays.
• Luke holidays: 25 Jul – 1 Aug and 22 – 29 Aug 2026. Bank holiday: Mon 31 Aug 2026.
• Stage gates signed off by Lara, Ryan and Neels before the next stage begins.
• Weather rule: if render/roof work is unfavourable (rain, or too hot to render), crew pivots to the rainy-day pool (Phase 3).
• Access discipline: side (a) via gate (a) only; side (b) via gate (b) only. No materials over new Millboard.
• V4 Flooring: notify 2 weeks (14 calendar days) before decking materials are required onsite.
KEY ASSUMPTIONS (open — to be confirmed)
• A1 RESOLVED (10 Aug): scaffold erection found wet ground at the chimney tower — not a soakaway pipe-run obstruction, but evidence suggesting a leaking house waste pipe beneath the chimney. See new finding below.
• NEW (10 Aug): Wet ground beneath chimney scaffold suggests a leaking waste pipe from the house. Investigation can only happen once scaffold is struck AND old decking/substructure removed in that specific area — timing depends on which decking side (a/b) sits beneath the chimney (TBC with Ryan). Cost: contingency-funded, no figure yet — would be named purpose #7 (coping condensation-prep took #6, 13 Aug).
• A2: All durations are planning estimates pending Luke's review of this v1.
• A3: Decking (a)/(b) split ≈ 2.5 weeks each within the 5-week decking ceiling.
• A4: V4 landing zone to be agreed with Luke without breaching gate segregation.
• A5: TPO appeal decision date unknown — fence relocation (3.5) floats until known.
STAGE GATE SIGN-OFF LOG
Gate | Description | Date signed | Lara | Neels | Ryan
G1 | At-height works (chimney, coping, back gutters) — scaffold may strike
G2 | Decking side (a) complete
G3 | Decking side (b) complete
G4 | Project completion — snagging & final sign-off
HOW TO UPDATE THIS WORKBOOK
• Edit only blue-on-yellow cells: task Start/End dates (Gantt), Last updated, contact details, and the sign-off log.
• Gantt bars redraw automatically from Start/End dates — never colour grid cells by hand.
• V4 Phase 1 (V1) and Phase 2 (V2) are fixed/on-request entries, not formulas, since the 10 Aug replan — Phase 1 delivered 12 Aug; Phase 2 ordered on request when needed.
• To activate a floating task: give it Start/End dates and change Status from 'Floating' to 'In progress'.
• Status values: Not started / In progress / Complete / Blocked / Floating.
• Back gutters & front tile repairs (10 Aug): WhatsApp record predating the written estimates confirms both are included in Luke's overall roof-work scope, no separate charge — resolves the open cost-coverage question. Neither needs a contingency line.
• EXCLUDED from Luke's scope (per same WhatsApp): work to the summer house ("out house") at the top deck — Luke made no assessment/notes on it. Distinct from the new decking build (separately quoted, proceeding). Do not assume any summer-house fabric work is covered.